## 1_INPUT
STEP BY STEP WORKOVER TIME FOR COMPANYMAN
[15 empty] | HIDDEN COL | HIDDEN COL | HIDDEN COL | HIDDEN COL | HIDDEN COL | HIDDEN COL | HIDDEN COL | HIDDEN COL | HIDDEN COL | HIDDEN COL | HIDDEN COL | HIDDEN COL | HIDDEN COL | HIDDEN COL | HIDDEN COL
STEP 1). WATCH OUT THE CELLS COLOR
| BE CAREFULL !!! ACTUNG !!! ATI-ATI !!! SLOW DOWN !!! LER'B DWEHLN !!! BE CAREFULL !!! ACTUNG !!! ATI-ATI !!!BE CAREFULL !!! | Mandatory Input
Automatic Calculated Cell
Border Line
NPT / Other Red Alert
Special Assignment
STEP 2). INPUT GENERAL DATA
| AFE NO. |  |  | 23-190-221-OO |  |  |  | SURFACE COORD. (X) |  |  | 330343.4411
| WELL |  |  | SPA-034 |  |  |  | SURFACE COORD. (Y) |  |  | 9639877.6688
| LOCATION |  |  | SOPA |  |  |  | SUB SURFACE COORD. (X) |  |  | -
| FIELD STRUCTURE |  |  | PENDOPO |  |  |  | SUB SURFACE COORD. (Y) |  |  | -
[8 empty] | ELEVATION |  |  | 1.43
| SPUD DATE |  |  | 2023-01-17 19:00
RELEASE DATE
| WELL TYPE |  |  | DIRECTIONAL | 11-3129 | 11-3129 | q
| PROJECT TYPE |  |  | WORKOVER | 11-3129 | 11-3129 | q
| PLANNED TOTAL DEPTH |  |  | 1112
| RIG NAME / OWNER |  |  | GJE #11 (450 HP)
| TINGGI RIG FLOOR |  |  | 5.5
| AFE BUDGET |  |  | 470258.4928
STEP 3). DEFINE YOUR SECTION LEVEL
| SECTION LEVEL #1 |  | SECTION LEVEL #2 |  | SECTION LEVEL #3 |  |  |  |  | USED OR NOT ? |  | NOTE: Nama Caracter antar level harus berbeda. Misal, pada level 2 : COMPLETION jika pada level 1 namanya sama COMPLETION maka formula akan ERROR, sebaiknya dibedakan minimal sperti ini : Level 2: COMPLETION, Level 1: COMPLETIONS
UNTUK TABEL ''STEP 7). EVALUATE YOUR DRILLING TIME''
MARKER: SECT #3 DIPAKAI ATAU TDK
| 1 | PRE-OPERATION JOB | [12 empty] | 0 | 0 | 0 | #N/A |  |  |  | xxxx |  | 1 | PREPARATION
|  |  | 11 | PREPARATION | [10 empty] | 11000 | PREPARATION | 11 | PREPARATION-PREPARATION | 3 |  |  | 11 | 1 | 2 | WORKOVER SECTION
[5 empty] | 11001 | Preparation |  |  |  | USED |  |  |  |  | 11001 | Preparation | 11 | PREPARATION-Preparation | 3 | V |  |  |  | 3 | RELEASE
| 2 | WORKOVER | [12 empty] | 0 | 0 | 0 | #N/A |  |  |  | xxxx |  | 4
|  |  | 21 | WORKOVER SECTION | [10 empty] | 21000 | WORKOVER SECTION | 21 | WORKOVER SECTION-WORKOVER SECTION |  |  |  | 21 | 2 | 5
[5 empty] | 21001 | PreSPUD |  |  |  | USED |  |  |  |  | 21001 | PreSPUD | 21 | WORKOVER SECTION-PreSPUD | 16 | V |  |  |  | 6
[5 empty] | 21002 | WORKOVER #1 |  |  |  | USED |  |  |  |  | 21002 | WORKOVER #1 | 21 | WORKOVER SECTION-WORKOVER #1 | 116 | V |  |  |  | 7
[5 empty] | 21003 | WORKOVER #2 |  |  |  | USED |  |  |  |  | 21003 | WORKOVER #2 | 21 | WORKOVER SECTION-WORKOVER #2 | 132 | V |  |  |  | 8
[5 empty] | 21004 | WORKOVER #3 |  |  |  | USED |  |  |  |  | 21004 | WORKOVER #3 | 21 | WORKOVER SECTION-WORKOVER #3 | 171 | V |  |  |  | 9
[5 empty] | 21005 | WORKOVER #4 |  |  |  | USED |  |  |  |  | 21005 | WORKOVER #4 | 21 | WORKOVER SECTION-WORKOVER #4 | 184 | V |  |  |  | 10
| 3 | RELEASE | [13 empty] | 0 |  | -0 | [5 empty] | 11
|  |  | 31 | RELEASE | [10 empty] | 31000 | RELEASE | 31 | RELEASE-RELEASE |  |  |  | 31 | 3 | 12
[5 empty] | 31001 | Rig Release |  |  |  | USED |  |  |  |  | 31001 | Rig Release | 31 | RELEASE-Rig Release | 186 | V |  |  |  | 13
[16 empty] | 0 |  | -0 | [5 empty] | 14
[16 empty] | 0 |  | -0 | [5 empty] | 15
[16 empty] | 0 |  | -0 | [5 empty] | 16
[16 empty] | 0 |  | -0 | [5 empty] | 17
[16 empty] | 0 |  | -0 | [5 empty] | 18
[16 empty] | 0 |  | -0 | [5 empty] | 19
[15 empty] | 0 | 0 | 0 | #N/A | [5 empty] | 20
[16 empty] | 0 |  | -0 | [5 empty] | 21
| xxxxxxxxxxxxx | xxxxxxxxxxxxx | xxxxxxxxxxxxx | xxxxxxxxxxxxx | xxxxxxxxxxxxx | xxxxxxxxxxxxx | xxxxxxxxxxxxx | xxxxxxxxxxxxx | xxxxxxxxxxxxx | xxxxxxxxxxxxx |  |  |  |  | xxxxxxxxxxxxx | xxxxxxxxxxxxx | xxxxxxxxxxxxx | xxxxxxxxxxxxx | xxxxxxxxxxxxx | xxxxxxxxxxxxx |  | xxxxxxxxxxxxx | xxxxxxxxxxxxx | xxxxxxxxxxxxx | xxxxxxxxxxxxx
STEP 4). DESCRIBE YOUR JOB SUMMARY FOR GRAPH
| NO | SECTION LEVEL #2 |  | SECTION LEVEL #3 |  | PLAN |  | ACTUAL |  | RESUME JOB |  |  |  |  | INTERVAL |  | SECTION LEVEL #1 | SECTION LEVEL #1 (dalam angka) |  | SECTION LEVEL #2 (dalam angka) |  | MIX RESULT |  | COLUMNS FOR SHEET GRAPH
[6 empty] | DAYS | CUM. DAYS | DAYS | CUM. DAYS | [5 empty] | START | END | [7 empty] | COLUMN #1 | COLUMN #2 | COLUMN #3 | COLUMN #4 | COLUMN #5 | COLUMN #6 | COLUMN #7 | COLUMN #8
| 1 | PREPARATION |  | Preparation |  | 0 | 0 | 0 | 0 | Rig Move & Rig Up |  |  |  |  | A | B | PRE-OPERATION JOB | 1 | 10000 | PREPARATION-Preparation | 11000 | 10000 | PRE-OPERATION JOB |  |  |  | PRE-OPERATION JOB
| 2 | WORKOVER SECTION |  | PreSPUD |  | 1.0208 | 1.0208 | 1.1667 | 1.1667 | Preparation (Kill well & POOH existing string) |  |  |  |  | B | C | WORKOVER | 2 | 20000 | WORKOVER SECTION-PreSPUD | 21001 | 11000 | PREPARATION | A | - | B | Rig Move & Rig Up | 0 | 0 | 0 | 0
| 3 | WORKOVER SECTION |  | WORKOVER #1 |  | 3.8333 | 4.8542 | 16.5417 | 17.7083 | Squeeze lapisan Eksisting. Run Scraper. Run GR-CBL-CNL |  |  |  |  | C | D | WORKOVER | 2 |  | WORKOVER SECTION-WORKOVER #1 | 21002 | 20000 | WORKOVER |  |  |  | WORKOVER
| 4 | WORKOVER SECTION |  | WORKOVER #2 |  | 5.4375 | 10.2917 | 0.0625 | 17.7708 | Perbaikan bonding. DOC. Run Scraper. Re run GR-CBL-VDL |  |  |  |  | D | E | WORKOVER | 2 |  | WORKOVER SECTION-WORKOVER #2 | 21003 | 21001 | WORKOVER SECTION | B | - | C | Preparation (Kill well & POOH existing string) | 1.0208 | 1.0208 | 1.1667 | 1.1667
| 5 | WORKOVER SECTION |  | WORKOVER #3 |  | 6.1667 | 16.4583 | 2.4375 | 20.2083 | Perforasi Produksi. Stimulation Job. RIH RPP. Swab Job. POOH RPP |  |  |  |  | E | F | WORKOVER | 2 |  | WORKOVER SECTION-WORKOVER #3 | 21004 | 21002 | WORKOVER SECTION | C | - | D | Squeeze lapisan Eksisting. Run Scraper. Run GR-CBL-CNL | 3.8333 | 4.8542 | 16.5417 | 17.7083
| 6 | WORKOVER SECTION |  | WORKOVER #4 |  | 2.25 | 18.7083 | 2.75 | 22.9583 | RIH RPP. Put well on production |  |  |  |  | F | G | WORKOVER | 2 |  | WORKOVER SECTION-WORKOVER #4 | 21005 | 21003 | WORKOVER SECTION | D | - | E | Perbaikan bonding. DOC. Run Scraper. Re run GR-CBL-VDL | 5.4375 | 10.2917 | 0.0625 | 17.7708
| 7 | RELEASE |  | Rig Release |  | 0 | 18.7083 | 0 | 22.9583 | Rig Release |  |  |  |  | G | H | RELEASE | 3 | 30000 | RELEASE-Rig Release | 31001 | 21004 | WORKOVER SECTION | E | - | F | Perforasi Produksi. Stimulation Job. RIH RPP. Swab Job. POOH RPP | 6.1667 | 16.4583 | 2.4375 | 20.2083
| 8 |  |  |  |  | #N/A | #N/A | #N/A | #N/A | [5 empty] | H | I | #N/A |  |  | - |  | 21005 | WORKOVER SECTION | F | - | G | RIH RPP. Put well on production | 2.25 | 18.7083 | 2.75 | 22.9583
| 9 |  |  |  |  | #N/A | #N/A | #N/A | #N/A | [5 empty] | I | J | #N/A |  |  | - |  | 30000 | RELEASE |  |  |  | RELEASE
| 10 |  |  |  |  | #N/A | #N/A | #N/A | #N/A | [5 empty] | J | K | #N/A |  |  | - |  | 31001 | RELEASE | G | - | H | Rig Release | 0 | 18.7083 | 0 | 22.9583
| 11 |  |  |  |  | #N/A | #N/A | #N/A | #N/A | [5 empty] | K | L | #N/A |  |  | -
| 12 |  |  |  |  | #N/A | #N/A | #N/A | #N/A | [5 empty] | L | M | #N/A |  |  | -
| 13 |  |  |  |  | #N/A | #N/A | #N/A | #N/A | [5 empty] | M | N | #N/A |  |  | -
| 14 |  |  |  |  | #N/A | #N/A | #N/A | #N/A | [5 empty] | N | O | #N/A |  |  | -
| 15 |  |  |  |  | #N/A | #N/A | #N/A | #N/A | [5 empty] | O | P | #N/A |  |  | -
| 16 |  |  |  |  | #N/A | #N/A | #N/A | #N/A | [5 empty] | P | Q | #N/A |  |  | -
| 17 |  |  |  |  | #N/A | #N/A | #N/A | #N/A | [5 empty] | Q | R | #N/A |  |  | -
| 18 |  |  |  |  | #N/A | #N/A | #N/A | #N/A | [5 empty] | R | S | #N/A |  |  | -
| 19 |  |  |  |  | #N/A | #N/A | #N/A | #N/A | [5 empty] | S | T | #N/A |  |  | -
| 20 |  |  |  |  | #N/A | #N/A | #N/A | #N/A | [5 empty] | T | 0 | #N/A |  |  | -
| xxxxxxxxxxxxx | xxxxxxxxxxxxx | xxxxxxxxxxxxx | xxxxxxxxxxxxx | xxxxxxxxxxxxx | xxxxxxxxxxxxx | xxxxxxxxxxxxx | xxxxxxxxxxxxx | xxxxxxxxxxxxx | xxxxxxxxxxxxx | xxxxxxxxxxxxx | xxxxxxxxxxxxx | xxxxxxxxxxxxx | xxxxxxxxxxxxx
STEP 5). INPUT DATA CASING SECTION & TOP OF LINER
| NO | CASING (INCH) | DEPTH |  |  | TOL | DEPTH (mMD)
|  |  | PLAN | ACTUAL |  |  | PLAN | ACTUAL
| 1 | 20 |  | 98.69 |  | 7 |  | 1433.34
| 2 | 13.375 |  | 698.86 |  | 4.5 |  | 2249
| 3 | 9.625 |  | 1495.27
| 4 | 7 |  | 2305
| 5 | 4.5 |  | 2399
| 6 |  |  | 2400
7
8
9
10
11
STEP 6). INPUT DATA FORMATION LAYER
| NO | LAYER NAME |  | ABBR. | DEPTH
1
2
3
4
5
6
7
8
STEP 7). EVALUATE YOUR DRILLING TIME
| HIDE THIS ROW PLZ!!! |  |  | 5 |  |  | 9 | 14 |  |  | 15 | 21 | 22 | 22
| NO | SECTION |  | PLAN |  |  |  | ACTUAL |  |  |  | DSR |  | DATE & DAY FINISHED
|  |  |  | HOURS | DAYS | CUM. DAYS | DEPTH | HOURS | DAYS | CUM. DAYS | DEPTH | HRS | (Days:Hrs: Mins)
| 1 | PREPARATION |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| 2 | WORKOVER SECTION |  | 449 | 18.7083 | 18.7083 | 1112 | 551 | 22.9583 | 22.9583 | 2374.8 | -102 | 1900-01-03 06:00 | 2023-02-09 18:00
| 3 | RELEASE |  | 0 | 0 | 18.7083 | 1112 | 0 | 0 | 22.9583 | 2374.8 |  |  | 2023-02-09 18:00
| 4 |  |  | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A
| 5 |  |  | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A
| 6 |  |  | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A
| 7 |  |  | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A
| 8 |  |  | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A
| 9 |  |  | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A
| 10 |  |  | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A
| 11 |  |  | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A
Add Row  | 12 |  |  | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A
| THE HELPER COLUMN |  |  | COMPLETION | TEST PASTE HERE
| FOR MIX & RANK |  |  | #N/A | MATCH
| 10000 | 1 |  | #N/A | VLOOKUP
| 20000 | 3 |  | -1 | COUNTIF
|  |  |  | #N/A | OFFSET
|  |  |  | Production Test | DROPDOWN LIST, TEST
|  |  |  | #N/A | MIX FORMULA
DROPDOWN LIST, TEST
| 30000 | 9
| 11000 | 2
| 21001 | 4
| 21002 | 5
| 21003 | 6
| 21004 | 7
| 21005 | 8
| 31001 | 10
| XXXXXXXX | XXXXXXXX
Formulas:
xxxxxxxxxxxxx = VLOOKUP([WELL],INDIRECT(ADDRESS(9,2,,,"2_DATA")):INDIRECT(ADDRESS(1000,COLUMN('2_DATA'!$AA9),,,"2_DATA")),N121,FALSE)

## BUDGET
MONITORING BUDGET PEMBORAN SUMUR SPA-034
AFE NO. |  | : 23-190-221-OO | [7 empty] | 6812.1951
BUDGET. |  | 470258.4928
SPUD DATE |  | 2023-01-17 19:00
HARI |  | TANGGAL | PLAN |  |  | ACTUAL
|  |  | DAILY COST | CUMM COST | % REAL | DAILY COST | CUMM COST | % REAL
0 | 0 | 2023-01-16 19:00 | 18426.5305 | 18426.5305 | 3.918% |  | 0 | 0% | 1 | 4007.5601 |  |  |  | 281.3897 | 281.3897 | 36.2931 | [9 empty] | 4606.6326
1 | 0.20833 | 2023-01-17 19:00 | 67163.514 | 85590.0445 | 18.2% | 77734.9296 | 77734.9296 | 16.53% | 2 | 4007.5601 |  |  |  | 281.3897 | 281.3897 | 36.2931 | [9 empty] | 4606.6326
2 | 1.2083 | 2023-01-18 19:00 | 12075.8882 | 97665.9326 | 20.77% | 6467.6008 | 84202.5305 | 17.91% | 3 | 4007.5601 |  |  |  | 281.3897 | 281.3897 | 36.2931 | [9 empty] | 4606.6326
3 | 2.2083 | 2023-01-19 19:00 | 17725.8007 | 115391.7334 | 24.54% | 6467.6008 | 90670.1313 | 19.28% | 1 | 39324.3243 | 2967.9997 | 5138.693 | 6335.1628 | 281.3897 | 281.3897 | 36.2931 | 62.5963 | 119.3788 | 112.1438 | 4000.5292 | 4915.5405 | 266.8039 | 1137.807 | 289.3054 | 1894.1567 | 67163.514
4 | 3.2083 | 2023-01-20 19:00 | 7725.8007 | 123117.5341 | 26.18% | 6467.6008 | 97137.7322 | 20.66% | 2 | 4350.0874 |  | 5138.693 |  | 281.3897 | 281.3897 | 36.2931 | 62.5963 | 119.3788 | 112.1438 |  |  | 266.8039 | 1137.807 | 289.3054 |  | 12075.8882
5 | 4.2083 | 2023-01-21 19:00 | 28960.9359 | 152078.4699 | 32.34% | 6467.6008 | 103605.333 | 22.03% | 3 | 10000 |  | 5138.693 |  | 281.3897 | 281.3897 | 36.2931 | 62.5963 | 119.3788 | 112.1438 |  |  | 266.8039 | 1137.807 | 289.3054 |  | 17725.8007
6 | 5.2083 | 2023-01-22 19:00 | 7725.8007 | 159804.2707 | 33.98% | 6467.6008 | 110072.9338 | 23.41% | 4 |  |  | 5138.693 |  | 281.3897 | 281.3897 | 36.2931 | 62.5963 | 119.3788 | 112.1438 |  |  | 266.8039 | 1137.807 | 289.3054 |  | 7725.8007
7 | 6.2083 | 2023-01-23 19:00 | 38693.7061 | 198497.9768 | 42.21% | 25020.0408 | 135092.9747 | 28.73% | 5 | 21235.1351 |  | 5138.693 |  | 281.3897 | 281.3897 | 36.2931 | 62.5963 | 119.3788 | 112.1438 |  |  | 266.8039 | 1137.807 | 289.3054 |  | 28960.9359
8 | 7.2083 | 2023-01-24 19:00 | 30539.9899 | 229037.9667 | 48.7% | 4853.5806 | 139946.5552 | 29.76% | 6 |  |  | 5138.693 |  | 281.3897 | 281.3897 | 36.2931 | 62.5963 | 119.3788 | 112.1438 |  |  | 266.8039 | 1137.807 | 289.3054 |  | 7725.8007
9 | 8.2083 | 2023-01-25 19:00 | 7725.8007 | 236763.7674 | 50.35% | 13267.6008 | 153214.1561 | 32.58% | 7 | 30967.9054 |  | 5138.693 |  | 281.3897 | 281.3897 | 36.2931 | 62.5963 | 119.3788 | 112.1438 |  |  | 266.8039 | 1137.807 | 289.3054 |  | 38693.7061
10 | 9.2083 | 2023-01-26 19:00 | 7725.8007 | 244489.5681 | 51.99% | 8698.0654 | 161912.2214 | 34.43% | 8 | 12000 | 10814.1892 | 5138.693 |  | 281.3897 | 281.3897 | 36.2931 | 62.5963 | 119.3788 | 112.1438 |  |  | 266.8039 | 1137.807 | 289.3054 |  | 30539.9899
11 | 10.2083 | 2023-01-27 19:00 | 52065.7257 | 296555.2938 | 63.06% | 6733.04 | 168645.2615 | 35.86% | 9 |  |  | 5138.693 |  | 281.3897 | 281.3897 | 36.2931 | 62.5963 | 119.3788 | 112.1438 |  |  | 266.8039 | 1137.807 | 289.3054 |  | 7725.8007
12 | 11.2083 | 2023-01-28 19:00 | 7725.8007 | 304281.0946 | 64.71% | 6733.04 | 175378.3015 | 37.29% | 10 |  |  | 5138.693 |  | 281.3897 | 281.3897 | 36.2931 | 62.5963 | 119.3788 | 112.1438 |  |  | 266.8039 | 1137.807 | 289.3054 |  | 7725.8007
13 | 12.2083 | 2023-01-29 19:00 | 7725.8007 | 312006.8953 | 66.35% | 6733.04 | 182111.3415 | 38.73% | 11 | 20421.4524 | 8188.7428 | 5138.693 | 15729.7297 | 281.3897 | 281.3897 | 36.2931 | 62.5963 | 119.3788 | 112.1438 |  |  | 266.8039 | 1137.807 | 289.3054 |  | 52065.7257
14 | 13.2083 | 2023-01-30 19:00 | 26583.9087 | 338590.804 | 72% | 6733.04 | 188844.3815 | 40.16% | 12 |  |  | 5138.693 |  | 281.3897 | 281.3897 | 36.2931 | 62.5963 | 119.3788 | 112.1438 |  |  | 266.8039 | 1137.807 | 289.3054 |  | 7725.8007
15 | 14.2083 | 2023-01-31 19:00 | 7725.8007 | 346316.6047 | 73.64% | 7723.52 | 196567.9016 | 41.8% | 13 |  |  | 5138.693 |  | 281.3897 | 281.3897 | 36.2931 | 62.5963 | 119.3788 | 112.1438 |  |  | 266.8039 | 1137.807 | 289.3054 |  | 7725.8007
16 | 15.2083 | 2023-02-01 19:00 | 61725.8007 | 408042.4054 | 86.77% | 14893.04 | 211460.9416 | 44.97% | 14 | 18858.108 |  | 5138.693 |  | 281.3897 | 281.3897 | 36.2931 | 62.5963 | 119.3788 | 112.1438 |  |  | 266.8039 | 1137.807 | 289.3054 |  | 26583.9087
17 | 16.2083 | 2023-02-02 19:00 | 7725.8007 | 415768.2061 | 88.41% | 6733.04 | 218193.9816 | 46.4% | 15 |  |  | 5138.693 |  | 281.3897 | 281.3897 | 36.2931 | 62.5963 | 119.3788 | 112.1438 |  |  | 266.8039 | 1137.807 | 289.3054 |  | 7725.8007
18 | 17.2083 | 2023-02-03 19:00 | 46764.4859 | 462532.692 | 98.36% | 6842.5707 | 225036.5523 | 47.85% | 16 | 54000 |  | 5138.693 |  | 281.3897 | 281.3897 | 36.2931 | 62.5963 | 119.3788 | 112.1438 |  |  | 266.8039 | 1137.807 | 289.3054 |  | 61725.8007
18.7083 | 18.2083 | 2023-02-04 19:00 | 7725.8007 | 470258.4928 | 100% | 6733.04 | 231769.5924 | 49.29% | 17 |  |  | 5138.693 |  | 281.3897 | 281.3897 | 36.2931 | 62.5963 | 119.3788 | 112.1438 |  |  | 266.8039 | 1137.807 | 289.3054 |  | 7725.8007
| 19.2083 | 2023-02-05 19:00 |  |  |  | 6835.9325 | 238605.5249 | 50.74% | 18 | 5941.9351 | 33096.7501 | 5138.693 |  | 281.3897 | 281.3897 | 36.2931 | 62.5963 | 119.3788 | 112.1438 |  |  | 266.8039 | 1137.807 | 289.3054 |  | 46764.4859
| 20.2083 | 2023-02-06 19:00 |  |  |  | 7097.8669 | 245703.3918 | 52.25% | 18.9 |  |  | 5138.693 |  | 281.3897 | 281.3897 | 36.2931 | 62.5963 | 119.3788 | 112.1438 |  |  | 266.8039 | 1137.807 | 289.3054 |  | 7725.8007
| 21.2083 | 2023-02-07 19:00 |  |  |  | 32049.6616 | 277753.0534 | 59.06% | 1 | 4007.5601 |  |  |  | 281.3897 | 281.3897 | 36.2931 | [9 empty] | 4606.6326
| 22.2083 | 2023-02-08 19:00 |  |  |  | 32921.6435 | 310674.697 | 66.06% | [17 empty] | 470258.4928
| 23.2083 | 2023-02-09 19:00 |  |  |  | 5243.1752 | 315917.8721 | 67.18%
|  | 2023-02-10 19:00 | [8 empty] | 5496.8032 | 19
|  | 2023-02-11 19:00 | [9 empty] | 289.3054
2023-02-12 19:00
2023-02-13 19:00
2023-02-14 19:00
2023-02-15 19:00
2023-02-16 19:00
2023-02-17 19:00
2023-02-18 19:00
2023-02-19 19:00
2023-02-20 19:00
2023-02-21 19:00
2023-02-22 19:00
2023-02-23 19:00
2023-02-24 19:00
2023-02-25 19:00
2023-02-26 19:00
2023-02-27 19:00
2023-02-28 19:00
2023-03-01 19:00
2023-03-02 19:00
2023-03-03 19:00
2023-03-04 19:00
2023-03-05 19:00
2023-03-06 19:00
2023-03-07 19:00
2023-03-08 19:00
2023-03-09 19:00
2023-03-10 19:00
2023-03-11 19:00
2023-03-12 19:00
2023-03-13 19:00
2023-03-14 19:00
2023-03-15 19:00
2023-03-16 19:00
2023-03-17 19:00
2023-03-18 19:00
Formulas:
TANGGAL = [TANGGAL, row above]+1

## 2_DATA
WORK DESCRIPTION PLAN VS ACTUAL
WELL : SPA-034
LOCATION : SOPA
SPUD DATE : 17/01/2023 19:00
SUB SECTION | NO. SECTION | PLAN | [7 empty] | ACTUAL | [5 empty] | ACTUAL BREAKDOWN | [7 empty] | HIDE | FOR GRAPH |  |  |  | HELPER | HELPER | [5 empty] | HELPER: MARKER SECT LEVEL #2
|  | SEQUENCE NO / SECTION | OPERATION | IADC CODE | HOURS | CUM. HRS/SECT | AFE |  | DEPTH | WORK DESCRIPTION | IADC CODE | HRS | CUM. HRS/SECT | DEPTH | NPT | DAYS | CUM DAYS | DATE & DAY | GAIN / LOSS |  | DAILY NPT (%) |  | CUM NPT (%) | HIDE | PLAN AFE |  | ACTUAL AFE |  | ROP for Header Gain/Loss | SECTION | SUB-SECTION | SUB-SECTION | SUB-SECTION ISTEXT | SUB-SECTION ISTEXT | CUM
[7 empty] | DAYS | CUM. | [5 empty] | DEPTH | DEPTH | DAYS | CUMM. |  | HOUR | DD:HH:MM |  |  |  | HIDE | DAYS CUM. | DEPTH | DAYS CUM. | DEPTH | [7 empty] | SECT #2 | MATCH | VLOOKUP | VLOOKUP | OFFSET | SECT #2
HIDE
|  | 1 | Rig Move & Rig up |  | 0 | 0 | 0 | 0 | 0 | Rig Move & Rig up |  |  | 0 | 0 |  | 0 | 0 | [6 empty] | HIDE | 0 | 0 | 0 | 0 |  | 1 | 1 |  |  |  | 0 | PREPARATION | 3 | 11 | 1 | Preparation
Preparation | 1 | PREPARATION |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | ---------------------- | ---------------------- | HIDE | 0 | 0 | 0 | 0 |  | 1 | 1 | 1 | PREPARATION | Preparation | 0 | PREPARATION | 3 | 11 | 1 | Preparation | PREPARATION-Preparation
|  | 2 | Preparation and Killing Well |  | 4 | 4 | 0.16667 | 0.16667 | 0 | Rig GJE #11 (450 HP) dinyatakan mulai operasi di sumur SPA-034 TMT 17 Januari 2023 pukul 19:00 WIB. PJSM. Cek tekanan string 0 psi dan annulus 0 psi. | 2e | 1 | 1 | 0 | 0 | 0.041667 | 0.041667 | 2023-01-17 20:00 | 3 | 0.125 | 2023-01-18 | - | 0% | HIDE | 0.16667 | 0 | 0.041667 | 0 | 0 | 2 | 2 |  |  |  | 0.16667 | WORKOVER SECTION | 6 | 21 | 5 | #VALUE!
[6 empty] | 4 | 0 | 0.16667 | 0 | Fill up annulus dengan 150 bbl AA 1.01 SG. Fill up string sampai penuh dengan 30 bbl AA 1.01 SG. - Pressure test RPP ESP dengan 500 psi/5 menit, baik. | 5a | 2 | 3 | 0 | 0 | 0.083333 | 0.125 | 2023-01-17 22:00 | 1 | 0.041667 | 2023-01-18 | - | 0% | HIDE | 0.16667 | 0 | 0.125 | 0 | 0 | 2 | 2 |  |  |  | 0.33333 | WORKOVER SECTION | 6 | 21 | 5 | #VALUE!
|  | 3 | Observasi Well |  | 1 | 5 | 0.041667 | 0.20833 | 0 | Observasi terbuka. | 6h | 1 | 4 | 0 | 0 | 0.041667 | 0.16667 | 2023-01-17 23:00 | 1 | 0.041667 | 2023-01-18 | - | 0% | HIDE | 0.20833 | 0 | 0.16667 | 0 | 0 | 2 | 2 |  |  |  | 0.54167 | WORKOVER SECTION | 6 | 21 | 5 | #VALUE!
|  | 4 | N/D X Mass Tree |  | 4 | 9 | 0.16667 | 0.375 | 0 |  |  |  | 4 | 0 | 0 | 0 | 0.16667 | 2023-01-17 23:00 | 5 | 0.20833 | 2023-01-18 | - | - | HIDE | 0.375 | 0 | 0.16667 | 0 | 0 | 2 | 2 |  |  |  | 0.91667 | WORKOVER SECTION | 6 | 21 | 5 | #VALUE!
|  | 5 | N/D Wellhead & Production Line |  | 2 | 11 | 0.083333 | 0.45833 | 0 | N/D ESP wellhead hercules 7-1/16" x 3000 psi + master valve 3-1/8" x 3000 psi. | 14a | 1 | 5 | 0 | 0 | 0.041667 | 0.20833 | 2023-01-18 | 6 | 0.25 | 2023-01-18 | - | 0% | HIDE | 0.45833 | 0 | 0.20833 | 0 | 0 | 2 | 2 |  |  |  | 1.375 | WORKOVER SECTION | 6 | 21 | 5 | #VALUE!
[6 empty] | 11 | 0 | 0.45833 | 0 | Lanjut N/D ESP wellhead hercules 7-1/16" x 3000 psi + master valve 3-1/8" x 3000 psi. - Potong kabel ESP dan capilar tube. - Pasang dan dudukan tubing bowl di THS 7-1/16" x 3000 psi. | 14a | 1 | 6 | 0 | 0 | 0.041667 | 0.25 | 2023-01-18 01:00 | 5 | 0.20833 | 2023-01-19 | - | 0% | HIDE | 0.45833 | 0 | 0.25 | 0 | 0 | 2 | 2 |  |  |  | 1.8333 | WORKOVER SECTION | 6 | 21 | 5 | #VALUE!
|  | 6 | N/U BOP 7-1/16" x 3000 psi & BOP Test |  | 6 | 17 | 0.25 | 0.70833 | 0 | N/U DSAF 7-1/16" x 3000 psi - 5000 psi + BOP group 7-1/16" x 5000 psi + bell nipple. | 14b | 2 | 8 | 0 | 0 | 0.083333 | 0.33333 | 2023-01-18 03:00 | 9 | 0.375 | 2023-01-19 | - | 0% | HIDE | 0.70833 | 0 | 0.33333 | 0 | 0 | 2 | 2 |  |  |  | 2.5417 | WORKOVER SECTION | 6 | 21 | 5 | #VALUE!
[6 empty] | 17 | 0 | 0.70833 | 0 | Function dan pressure test BOP group 7-1/16" x 5000 psi. - Function test BOP group, baik. - Pressure test Annular, Low : 500 psi/5 menit, High : 1500 psi/10 menit, baik. - Pressure test Pipe ram, Low : 500 psi/5 menit, High : 1500 psi/10 menit, baik. | 15a | 1 | 9 | 0 | 0 | 0.041667 | 0.375 | 2023-01-18 04:00 | 8 | 0.33333 | 2023-01-19 | - | 0% | HIDE | 0.70833 | 0 | 0.375 | 0 | 0 | 2 | 2 |  |  |  | 3.25 | WORKOVER SECTION | 6 | 21 | 5 | #VALUE!
|  | 7 | Unset Packer |  | 1 | 18 | 0.041667 | 0.75 | 1112 |  |  |  | 9 | 1814.13 | 0 | 0 | 0.375 | 2023-01-18 04:00 | 9.6314 | 0.40069 | 2023-01-19 | - | - | HIDE | 0.75 | 1112 | 0.375 | 1814.13 | 1112 | 2 | 2 |  |  |  | 4 | WORKOVER SECTION | 6 | 21 | 5 | #VALUE!
|  | 8 | Circulation Condition Mud |  | 2 | 20 | 0.083333 | 0.83333 | 1112 |  |  |  | 9 | 1814.13 | 0 | 0 | 0.375 | 2023-01-18 04:00 | 11 | 0.45833 | 2023-01-19 | - | - | HIDE | 0.83333 | 1112 | 0.375 | 1814.13 | 0 | 2 | 2 |  |  |  | 4.8333 | WORKOVER SECTION | 6 | 21 | 5 | #VALUE!
|  | 9 | POOH Production String + Packer 7" to Surface |  | 4.5 | 24.5 | 0.1875 | 1.0208 | 1112 | Drop bar ke dalam string untuk putuskan BV. Observasi tertutup 30 menit, SITP 0 psi. Isi string 1x volume pastikan pin dari BV sudah putus. Observasi terbuka, tidak ada aliran. | 2e | 1 | 10 | 1814.13 | 0 | 0.041667 | 0.41667 | 2023-01-18 05:00 | 14.5 | 0.60417 | 2023-01-19 | - | 0% | HIDE | 1.0208 | 1112 | 0.41667 | 1814.13 | 0 | 2 | 2 |  |  |  | 5.8542 | WORKOVER SECTION | 6 | 21 | 5 | #VALUE!
[6 empty] | 24.5 | 0 | 1.0208 | 1112 | Cabut L/D RPP ESP Wespi dan capilar tube dari 1814.13 m sampai 56 m. - Aksesoris ESP WSEPI : Cable band : 150 ea, Protector : 140 pcs. Note : 2 titik didapati capilar tube bocor. - L/D 1 jt 3-1/2" tubing (bekas) + 128 jts 2-7/8" tubing (bekas). - Rack back 60 jts 2-7/8" tubing (bekas). | 26b | 12.5 | 22.5 | 1814.13 | 0 | 0.52083 | 0.9375 | 2023-01-18 17:30 | 2 | 0.083333 | 2023-01-19 | - | 0% | HIDE | 1.0208 | 1112 | 0.9375 | 1814.13 | 0 | 2 | 2 |  |  |  | 6.875 | WORKOVER SECTION | 6 | 21 | 5 | #VALUE!
PreSPUD | [5 empty] | 24.5 | 0 | 1.0208 | 1112 | L/D ESP Wespi dari 56 m sampai permukaan. - Disconnect pump UT, putaran shaft free. - Disconnect Pump LT, putaran shaft free. - Disconnect GS dan intake gas separator, putaran shaft free. - Disconnect protector PFDB, putaran shaft free, oli clear tidak bercampur air. - Disconnect protector 66L, putaran shaft free, oli clear tidak bercampur air. - L/D motor, putaran shaft free, oli clear tidak bercampur air. - RPP ESP eksisting : 1 jt 3-1/2" tubing (bekas) + 184 jts 2-7/8" tubing (bekas) + BV + 1 jt 2-7/8" tubing (bekas) + CV + 3 jts 2-7/8" tubing (bekas) + Pump head + Upper pump FLCT 400 S TD 750-190 STG + Lower pump FLCT 400 S TD 750-152 STG + Gas separator intake 540 S + Upper protector PFDB 540 S + Lower Protector 66 L 540 SL + Motor 80 HP C1150. 45. 540.S + Centralizer - Hasil pengukuran - Motor + Cable - PP : 4.7/4.7/4.7 0hm - Balance - PG : 20 M ohm - Motor - PP : 0.8 ohm - PG : 2000 M.ohm - Cable : 2000 M.ohm. | 26b | 5.5 | 28 | 1814.13 | 0 | 0.22917 | 1.1667 | 2023-01-18 23:00 | -3.5 | 0.14583 | 2023-01-19 | - | 0% | HIDE | 1.0208 | 1112 | 1.1667 | 1814.13 | 0 | 2 | 2 | 2 | WORKOVER SECTION | PreSPUD | 7.8958 | WORKOVER SECTION | 6 | 21 | 5 | #VALUE! | WORKOVER SECTION-PreSPUD
|  | 10 | RIH TCB 6" |  | 7 | 31.5 | 0.29167 | 1.3125 | 1112 | Persiapan masuk ROE (3-1/4" saw tooth + 2-3/8" DP + X/O + 2-7/8" DP + X/O + 3-1/2" DP). | 6g | 1 | 29 | 1814.13 | 0 | 0.041667 | 1.2083 | 2023-01-19 | 2.5 | 0.10417 | 2023-01-19 | - | 0% | HIDE | 1.3125 | 1112 | 1.2083 | 1814.13 | 0 | 2 | 3 |  |  |  | 1.3125 | WORKOVER SECTION | 6 | 21 | 5 | #VALUE!
[6 empty] | 31.5 | 0 | 1.3125 | 1112 | Masuk ROE (3-1/4" saw tooth + 20 jts 2-3/8" DP + X/O + 170 jts 2-7/8" DP + 52 jts 3-1/2" DP) sampai 2335.3 m. - Sablon dan hammering semua tubular. - Masuk joint per joint. - Break sirkulasi setiap 20 joint, belum ada return. - Rangkaian duduk 2 klbs di 2335.3 m. | 6g | 21.5 | 50.5 | 2335.3 | 0 | 0.89583 | 2.1042 | 2023-01-19 21:30 | -19 | 0.79167 | 2023-01-20 | - | 0% | HIDE | 1.3125 | 1112 | 2.1042 | 2335.3 | 0 | 2 | 3 |  |  |  | 2.625 | WORKOVER SECTION | 6 | 21 | 5 | #VALUE!
[6 empty] | 31.5 | 0 | 1.3125 | 1112 | Sirkulasi dengan GPM/SPP : 168/0 psi, tidak ada return. - Ambil 310 bbl AA dengan vakum truck di SPA-019 (injection well). | 5a | 1 | 51.5 | 2335.3 | 0 | 0.041667 | 2.1458 | 2023-01-19 22:30 | -20 | 0.83333 | 2023-01-20 | - | 0% | HIDE | 1.3125 | 1112 | 2.1458 | 2335.3 | 0 | 2 | 3 |  |  |  | 3.9375 | WORKOVER SECTION | 6 | 21 | 5 | #VALUE!
[6 empty] | 31.5 | 0 | 1.3125 | 1112 | Wash down dengan 3-1/4" saw tooth dari 2335.3 m sampai 2335.7 m. - WOB/GPM/SPP : 1-3 klbs/168/0 psi. - Kumm loss : 380 bbl AA. | 3a | 1.5 | 53 | 2335.7 | 0 | 0.0625 | 2.2083 | 2023-01-20 | -21.5 | 0.89583 | 2023-01-20 | - | 0% | HIDE | 1.3125 | 1112 | 2.2083 | 2335.7 | 0 | 2 | 3 |  |  |  | 5.25 | WORKOVER SECTION | 6 | 21 | 5 | #VALUE!
[6 empty] | 31.5 | 0 | 1.3125 | 1112 | M/U kelly dan 4" rotary hose. | 6g | 1 | 54 | 2335.7 | 0 | 0.041667 | 2.25 | 2023-01-20 01:00 | -22.5 | 0.9375 | 2023-01-21 | - | 0% | HIDE | 1.3125 | 1112 | 2.25 | 2335.7 | 0 | 2 | 3 |  |  |  | 6.5625 | WORKOVER SECTION | 6 | 21 | 5 | #VALUE!
[6 empty] | 31.5 | 0 | 1.3125 | 1112 | Reaming down dengan 3-1/4" saw tooth dari 2335.7 m sampai 2372 m. - WOB/GPM/SPP/RPM/TQ : 1-2 klbs/100/0 psi/30/400-500 ft-lbs. - Selama reaming tidak ada return. - Total loss : 400 bbl, Kumm loss : 780 bbl AA. | 3a | 4.5 | 58.5 | 2372 | 0 | 0.1875 | 2.4375 | 2023-01-20 05:30 | -27 | 1899-12-31 03:00 | 2023-01-21 | - | 0% | HIDE | 1.3125 | 1112 | 2.4375 | 2372 | 0 | 2 | 3 |  |  |  | 7.875 | WORKOVER SECTION | 6 | 21 | 5 | #VALUE!
|  | 11 | Sirkulasi |  | 2 | 33.5 | 0.083333 | 1.3958 | 1112 | Sirkulasi dengan GPM/SPP : 100/0 psi. - Selama sirkulasi tidak ada return. - Total loss : 50 bbl, Kumm loss : 830 bbl AA. | 5a | 0.5 | 59 | 2372 | 0 | 0.020833 | 2.4583 | 2023-01-20 06:00 | -25.5 | 1899-12-31 01:30 | 2023-01-21 | - | 0% | HIDE | 1.3958 | 1112 | 2.4583 | 2372 | 0 | 2 | 3 |  |  |  | 9.2708 | WORKOVER SECTION | 6 | 21 | 5 | #VALUE!
[6 empty] | 33.5 | 0 | 1.3958 | 1112 | N/D kelly dan 4" rotary hose. - Ambil 375 bbl AA dengan vakum truck di SPA-019 (injection well). | 6g | 1 | 60 | 2372 | 0 | 0.041667 | 2.5 | 2023-01-20 07:00 | -26.5 | 1899-12-31 02:30 | 2023-01-21 | - | 0% | HIDE | 1.3958 | 1112 | 2.5 | 2372 | 0 | 2 | 3 |  |  |  | 10.6667 | WORKOVER SECTION | 6 | 21 | 5 | #VALUE!
|  | 12 | POOH TCB 6" to Surface |  | 7 | 40.5 | 0.29167 | 1.6875 | 1112 | Reposisi dan ukur 60 jts 2-7/8" tubing (bekas) di sisiran. | 6b | 1 | 61 | 2372 | 0 | 0.041667 | 2.5417 | 2023-01-20 08:00 | -20.5 | 0.85417 | 2023-01-21 | - | 0% | HIDE | 1.6875 | 1112 | 2.5417 | 2372 | 0 | 2 | 3 |  |  |  | 12.3542 | WORKOVER SECTION | 6 | 21 | 5 | #VALUE!
[6 empty] | 40.5 | 0 | 1.6875 | 1112 | Cabut ROE dari 2372 m sampai permukaan. - Fill up annulus berkala. - L/D 20 jts 2-3/8" DP. | 6g | 13 | 74 | 2372 | 0 | 0.54167 | 3.0833 | 2023-01-20 21:00 | -33.5 | 1899-12-31 09:30 | 2023-01-21 | - | 0% | HIDE | 1.6875 | 1112 | 3.0833 | 2372 | 0 | 2 | 3 |  |  |  | 14.0417 | WORKOVER SECTION | 6 | 21 | 5 | #VALUE!
[6 empty] | 40.5 | 0 | 1.6875 | 1112 | Ganti pipe ram dari 3-1/2" ke 2-7/8". | 12a | 1 | 75 | 2372 | 0 | 0.041667 | 3.125 | 2023-01-20 22:00 | -34.5 | 1899-12-31 10:30 | 2023-01-21 | - | 0% | HIDE | 1.6875 | 1112 | 3.125 | 2372 | 0 | 2 | 3 |  |  |  | 15.7292 | WORKOVER SECTION | 6 | 21 | 5 | #VALUE!
|  | 13 | RIH OE Tbg 2-7/8" for Squeeze Lapisan Eksisting |  | 6 | 46.5 | 0.25 | 1.9375 | 1112 | Masuk ROE (2-3/8" mole shoe + 15 jts 2-3/8" tubing (bekas) + X/O + 35 jts 2-7/8" tubing (bekas)) sampai 468.6 m. - Masuk joint per joint 2-3/8" tubing (bekas). | 6g | 2 | 77 | 2372 | 0 | 0.083333 | 3.2083 | 2023-01-21 | -30.5 | 1899-12-31 06:30 | 2023-01-21 | - | 0% | HIDE | 1.9375 | 1112 | 3.2083 | 2372 | 0 | 2 | 3 |  |  |  | 17.6667 | WORKOVER SECTION | 6 | 21 | 5 | #VALUE!
[6 empty] | 46.5 | 0 | 1.9375 | 1112 | Lanjut masuk ROE (2-3/8" mole shoe + 15 jts 2-3/8" tubing (bekas) + X/O + 60 jts 2-7/8" tubing (bekas) + X/O + X/O + 160 jts 2-7/8" DP) dari 468.6 m sampai 2248.5 m. - Rangkaian duduk 1 klbs di 2248.5 m (TOL 4-1/2"). | 6g | 9 | 86 | 2372 | 0 | 0.375 | 3.5833 | 2023-01-21 09:00 | -39.5 | 1899-12-31 15:30 | 2023-01-22 | - | 0% | HIDE | 1.9375 | 1112 | 3.5833 | 2372 | 0 | 2 | 3 |  |  |  | 19.6042 | WORKOVER SECTION | 6 | 21 | 5 | #VALUE!
[6 empty] | 46.5 | 0 | 1.9375 | 1112 | Usaha masuk ROE lebih dalam dengan WOP sambil putar rangkaian, belum berhasil. Pasang circulating head. Wash down dari 2247.6 m sampai 2249.6 m, rangkaian berhasil masuk TOL 4-1/2". - WOB/GPM/SPP : 0.5-1 klbs/80/0 psi. | 3a | 3 | 89 | 2372 | 0 | 0.125 | 3.7083 | 2023-01-21 12:00 | -42.5 | 1899-12-31 18:30 | 2023-01-22 | - | 0% | HIDE | 1.9375 | 1112 | 3.7083 | 2372 | 0 | 2 | 3 |  |  |  | 21.5417 | WORKOVER SECTION | 6 | 21 | 5 | #VALUE!
[6 empty] | 46.5 | 0 | 1.9375 | 1112 | Lanjut masuk ROE (2-3/8" mole shoe + 15 jts 2-3/8" tubing (bekas) + X/O + 60 jts 2-7/8" tubing (bekas) + X/O + X/O + 170 jts 2-7/8" DP) dari 2249.6 m sampai 2346.4 m. | 6g | 1 | 90 | 2372 | 0 | 0.041667 | 3.75 | 2023-01-21 13:00 | -43.5 | 1899-12-31 19:30 | 2023-01-22 | - | 0% | HIDE | 1.9375 | 1112 | 3.75 | 2372 | 0 | 2 | 3 |  |  |  | 23.4792 | WORKOVER SECTION | 6 | 21 | 5 | #VALUE!
|  | 14 | Semen Squeeze Lapisan Eksisting |  | 6 | 52.5 | 0.25 | 2.1875 | 1112 | Persiapan squeeze lapisan eksisting BRF interval 2337-2344 m. - Sirkulasi dengan GPM/SPP : 100/0 psi, tidak ada return. - Total loss : 70 bbl AA, Kumm loss : 900 bbl AA. - Ambil 248 bbl AA dengan vakum truck di SPA-019 (injection well). | 18a | 2 | 92 | 2372 | 0 | 0.083333 | 3.8333 | 2023-01-21 15:00 | -39.5 | 1899-12-31 15:30 | 2023-01-22 | - | 0% | HIDE | 2.1875 | 1112 | 3.8333 | 2372 | 0 | 2 | 3 |  |  |  | 25.6667 | WORKOVER SECTION | 6 | 21 | 5 | #VALUE!
[6 empty] | 52.5 | 0 | 2.1875 | 1112 | Rig up cementing unit. - PJSM. - Function test cementing unit, baik. - M/U cementing line dan plug valve cementing. | 18a | 1 | 93 | 2372 | 0 | 0.041667 | 3.875 | 2023-01-21 16:00 | -40.5 | 1899-12-31 16:30 | 2023-01-22 | - | 0% | HIDE | 2.1875 | 1112 | 3.875 | 2372 | 0 | 2 | 3 |  |  |  | 27.8542 | WORKOVER SECTION | 6 | 21 | 5 | #VALUE!
[6 empty] | 52.5 | 0 | 2.1875 | 1112 | Squeeze lapisan eksisting BRF interval 2337-2344 m. - Pressure test cementing line 2000 psi/5 mnt, baik. - Mixing additive semen. - Pompakan 17 bbl water ahead 8.33 ppg dengan rate 3 bpm, pressure 35 psi. - Aduk dan pompakan 5 bbl semen 13 ppg dengan rate 2 bpm, pressure 70 psi. - Pompakan 3 bbl water behind 8.33 ppg dengan rate 2 bpm, pressure 60 psi. - Displace 34 bbls AA 8.41 ppg dengan rate 2 bpm, pressure 45 psi. - Lepas cementing line dan plug valve cementing. - Cabut ROE dari 2346.4 m sampai 2076.4 m. Tutup annular dan pipe ram BOP. - Hesitasi dengan rate 1.3 bpm, volume 1 bbl, pressure 30 psi. Stop pompa, pressure langsung turun sampai 0 psi. | 18a | 3 | 96 | 2372 | 0 | 0.125 | 4 | 2023-01-21 19:00 | -43.5 | 1899-12-31 19:30 | 2023-01-22 | - | 0% | HIDE | 2.1875 | 1112 | 4 | 2372 | 0 | 2 | 3 |  |  |  | 30.0417 | WORKOVER SECTION | 6 | 21 | 5 | #VALUE!
|  | 15 | WOC |  | 8 | 60.5 | 0.33333 | 2.5208 | 1112 | TSK vakum. - Sample semen di water batch belum keras. | 13a | 5 | 101 | 2372 | 0 | 0.20833 | 4.2083 | 2023-01-22 | -40.5 | 1899-12-31 16:30 | 2023-01-22 | - | 0% | HIDE | 2.5208 | 1112 | 4.2083 | 2372 | 0 | 2 | 3 |  |  |  | 32.5625 | WORKOVER SECTION | 6 | 21 | 5 | #VALUE!
[6 empty] | 60.5 | 0 | 2.5208 | 1112 | Lanjut TSK vakum. - Sample semen di water batch sudah keras. - Buka annular dan pipe ram BOP. | 13a | 11 | 112 | 2372 | 0 | 0.45833 | 4.6667 | 2023-01-22 11:00 | -51.5 | 1900-01-01 03:30 | 2023-01-23 | - | 0% | HIDE | 2.5208 | 1112 | 4.6667 | 2372 | 0 | 2 | 3 |  |  |  | 35.0833 | WORKOVER SECTION | 6 | 21 | 5 | #VALUE!
[6 empty] | 60.5 | 0 | 2.5208 | 1112 | Masuk ROE (2-3/8" mole shoe + 15 jts 2-3/8" tubing (bekas) + X/O + 60 jts 2-7/8" tubing (bekas) + X/O + X/O + 171 jts 2-7/8" DP) dari 2076.4 m sampai 2356 m. - Masuk perlahan dari 2230.3 m sampai 2356 m, rangkaian duduk 2 klbs (TOC). | 6g | 2 | 114 | 2372 | 0 | 0.083333 | 4.75 | 2023-01-22 13:00 | -53.5 | 1900-01-01 05:30 | 2023-01-23 | - | 0% | HIDE | 2.5208 | 1112 | 4.75 | 2372 | 0 | 2 | 3 |  |  |  | 37.6042 | WORKOVER SECTION | 6 | 21 | 5 | #VALUE!
[6 empty] | 60.5 | 0 | 2.5208 | 1112 | Fill up sumur dengan 264 bbl AA, tidak ada return. | 5a | 2 | 116 | 2372 | 0 | 0.083333 | 4.8333 | 2023-01-22 15:00 | -55.5 | 1900-01-01 07:30 | 2023-01-23 | - | 0% | HIDE | 2.5208 | 1112 | 4.8333 | 2372 | 0 | 2 | 3 |  |  |  | 40.125 | WORKOVER SECTION | 6 | 21 | 5 | #VALUE!
[6 empty] | 60.5 | 0 | 2.5208 | 1112 | Persiapan squeeze ke-2 lapisan eksisting BRF interval 2337-2344 m. - Cabut ROE dari 2356 m sampai 2346.4 m. - Ambil 385 bbl AA dengan vakum truck di SPA-019 (injection well). - Fill up sumur dengan 200 bbl AA, tidak ada return. | 18a | 2 | 118 | 2372 | 0 | 0.083333 | 4.9167 | 2023-01-22 17:00 | -57.5 | 1900-01-01 09:30 | 2023-01-23 | - | 0% | HIDE | 2.5208 | 1112 | 4.9167 | 2372 | 0 | 2 | 3 |  |  |  | 42.6458 | WORKOVER SECTION | 6 | 21 | 5 | #VALUE!
[6 empty] | 60.5 | 0 | 2.5208 | 1112 | Squeeze ke-2 lapisan eksisting BRF interval 2337-2344 m. - PJSM. - M/U cementing line dan plug valve cementing. - Pressure test cementing line 2200 psi/5 mnt, baik. - Mixing additive semen. - Pompakan 16.8 bbl water ahead 8.33 ppg dengan rate 2 bpm, pressure 5 psi. - Aduk dan pompakan 8 bbl semen 15.8 ppg dengan rate 2 bpm, pressure 50-60 psi. - Pompakan 3.2 bbl water behind 8.33 ppg dengan rate 2 bpm, pressure 50-60 psi. - Displace 34.3 bbls AA 8.41 ppg dengan rate 1 bpm, pressure 5-10 psi. - Lepas cementing line dan plug valve cementing. Note : Selama pekerjaan squeeze tidak ada return. | 18a | 4.5 | 122.5 | 2372 | 0 | 0.1875 | 5.1042 | 2023-01-22 21:30 | -62 | 1900-01-01 14:00 | 2023-01-23 | - | 0% | HIDE | 2.5208 | 1112 | 5.1042 | 2372 | 0 | 2 | 3 |  |  |  | 45.1667 | WORKOVER SECTION | 6 | 21 | 5 | PreSPUD
[6 empty] | 60.5 | 0 | 2.5208 | 1112 | Cabut ROE dari 2346.4 m sampai 2057 m. | 6g | 1 | 123.5 | 2372 | 0 | 0.041667 | 5.1458 | 2023-01-22 22:30 | -63 | 1900-01-01 15:00 | 2023-01-23 | - | 0% | HIDE | 2.5208 | 1112 | 5.1458 | 2372 | 0 | 2 | 3 |  |  |  | 47.6875 | WORKOVER SECTION | 6 | 21 | 5 | WORKOVER #1
[6 empty] | 60.5 | 0 | 2.5208 | 1112 | Hesitasi dengan rate 1 bpm, volume 1 bbl, pressure 10 psi. Stop pompa, pressure langsung turun sampai 0 psi. - M/U cementing line dan plug valve cementing. - Tutup annular dan pipe ram BOP. | 18a | 0.5 | 124 | 2372 | 0 | 0.020833 | 5.1667 | 2023-01-22 23:00 | -63.5 | 1900-01-01 15:30 | 2023-01-23 | - | 0% | HIDE | 2.5208 | 1112 | 5.1667 | 2372 | 0 | 2 | 3 |  |  |  | 50.2083 | WORKOVER SECTION | 6 | 21 | 5 | WORKOVER #2
[6 empty] | 60.5 | 0 | 2.5208 | 1112 | TSK vakum. - Sample semen di water batch belum keras. | 13a | 1 | 125 | 2372 | 0 | 0.041667 | 5.2083 | 2023-01-23 | -64.5 | 1900-01-01 16:30 | 2023-01-23 | - | 0% | HIDE | 2.5208 | 1112 | 5.2083 | 2372 | 0 | 2 | 3 |  |  |  | 52.7292 | WORKOVER SECTION | 6 | 21 | 5 | WORKOVER #3
[6 empty] | 60.5 | 0 | 2.5208 | 1112 | Lanjut TSK vakum. - Sample semen di water batch sudah keras. - Buka annular dan pipe ram BOP. | 13a | 14 | 139 | 2372 | 0 | 0.58333 | 5.7917 | 2023-01-23 14:00 | -78.5 | 1900-01-02 06:30 | 2023-01-24 | - | 0% | HIDE | 2.5208 | 1112 | 5.7917 | 2372 | 0 | 2 | 3 |  |  |  | 55.25 | WORKOVER SECTION | 6 | 21 | 5 | WORKOVER #4
[6 empty] | 60.5 | 0 | 2.5208 | 1112 | Masuk ROE (2-3/8" mole shoe + 15 jts 2-3/8" tubing (bekas) + X/O + 60 jts 2-7/8" tubing (bekas) + X/O + X/O + 146 jts 2-7/8" DP) dari 2057 m sampai 2114.2 m. - Rangkaian duduk 2-4 klbs (TOC). | 6g | 0.5 | 139.5 | 2372 | 0 | 0.020833 | 5.8125 | 2023-01-23 14:30 | -79 | 1900-01-02 07:00 | 2023-01-24 | - | 0% | HIDE | 2.5208 | 1112 | 5.8125 | 2372 | 0 | 2 | 3 |  |  |  | 57.7708 | WORKOVER SECTION | 6 | 21 | 5 | #VALUE!
[6 empty] | 60.5 | 0 | 2.5208 | 1112 | Fill up sumur dengan 217 bbl AA (GPM/SPP : 126/0 psi), keluar aliran. - Ambil 310 bbl AA dengan vakum truck di SPA-019 (injection well). | 5a | 3 | 142.5 | 2372 | 0 | 0.125 | 5.9375 | 2023-01-23 17:30 | -82 | 1900-01-02 10:00 | 2023-01-24 | - | 0% | HIDE | 2.5208 | 1112 | 5.9375 | 2372 | 0 | 2 | 3 |  |  |  | 60.2917 | WORKOVER SECTION | 6 | 21 | 5 | #VALUE!
[6 empty] | 60.5 | 0 | 2.5208 | 1112 | Flowcheck statik loss, tidak ada penurunan. Pressure test casing dengan 500 psi/10 menit, baik. | 2f | 0.5 | 143 | 2372 | 0 | 0.020833 | 5.9583 | 2023-01-23 18:00 | -82.5 | 1900-01-02 10:30 | 2023-01-24 | - | 0% | HIDE | 2.5208 | 1112 | 5.9583 | 2372 | 0 | 2 | 3 |  |  |  | 62.8125 | WORKOVER SECTION | 6 | 21 | 5 | #VALUE!
[6 empty] | 60.5 | 0 | 2.5208 | 1112 | Hujan deras disertai angin (unsafe condition). | 23a | 2 | 145 | 2372 | 0 | 0.083333 | 6.0417 | 2023-01-23 20:00 | -84.5 | 1900-01-02 12:30 | 2023-01-24 | - | 0% | HIDE | 2.5208 | 1112 | 6.0417 | 2372 | 0 | 2 | 3 |  |  |  | 65.3333 | WORKOVER SECTION | 6 | 21 | 5 | #VALUE!
|  | 16 | POOH OE Tbg Cementing to Surface |  | 6 | 66.5 | 0.25 | 2.7708 | 1112 | Cabut ROE dari 2114.2 m sampai 1179 m. - Fill up annulus setiap 20 jts. | 6g | 4 | 149 | 2372 | 0 | 0.16667 | 6.2083 | 2023-01-24 | -82.5 | 1900-01-02 10:30 | 2023-01-24 | - | 0% | HIDE | 2.7708 | 1112 | 6.2083 | 2372 | 0 | 2 | 3 |  |  |  | 68.1042 | WORKOVER SECTION | 6 | 21 | 5 | #VALUE!
[6 empty] | 66.5 | 0 | 2.7708 | 1112 | Lanjut cabut ROE dari 1179 m sampai permukaan. - Fill up annulus setiap 20 jts. - (02:00) L/D 60 jts 2-7/8" tubing (bekas) + 15 jts 2-3/8" tubing (bekas) | 6g | 8 | 157 | 2372 | 0 | 0.33333 | 6.5417 | 2023-01-24 08:00 | -90.5 | 1900-01-02 18:30 | 2023-01-25 | - | 0% | HIDE | 2.7708 | 1112 | 6.5417 | 2372 | 0 | 2 | 3 |  |  |  | 70.875 | WORKOVER SECTION | 6 | 21 | 5 | #VALUE!
|  | 17 | RIH TCB 6" |  | 7 | 73.5 | 0.29167 | 3.0625 | 1112 | Persiapan masuk rangkaian 6-1/8" TCB + BHA Rotary. - Reposisi 15 jts 2-3/8" tubing (bekas) + 60 jts 2-7/8" tubing (bekas) dari pipe rack rig set ke pipe rack spear. - Loading unloading 10 jts 3-1/2" DP dari pipe box ke pipe rack rig set. | 6d | 2 | 159 | 2372 | 0 | 0.083333 | 6.625 | 2023-01-24 10:00 | -85.5 | 1900-01-02 13:30 | 2023-01-25 | - | 0% | HIDE | 3.0625 | 1112 | 6.625 | 2372 | 0 | 2 | 3 |  |  |  | 73.9375 | WORKOVER SECTION | 6 | 21 | 5 | #VALUE!
[6 empty] | 73.5 | 0 | 3.0625 | 1112 | Ambil 4 jts 4-3/4" DC dari lokasi BNG-045. (NPT Rig GJE #11 (Tubular problem) : 8 jam) - Armada belum bisa masuk ke lokasi SPA-034, dikarenakan perbaikan jembatan sungai Semangus Sopa. - Ambil 225 bbl air tawar dengan vakum truck di SPA-A sebelah SP Sopa. - Ambil 225 bbl AA dengan vakum truck di SPA-019 (injection well). | 8f | 8 | 167 | 2372 | NPT | 0.33333 | 6.9583 | 2023-01-24 18:00 | -93.5 | 1900-01-02 21:30 | 2023-01-25 | 44.44% | 4.79% | HIDE | 3.0625 | 1112 | 6.9583 | 2372 | 0 | 2 | 3 |  |  |  | 77 | WORKOVER SECTION | 6 | 21 | 5 | #VALUE!
[6 empty] | 73.5 | 0 | 3.0625 | 1112 | M/U dan masuk rangkaian 6-1/8" TCB (RR, IADC : 217, Nozz : 3x24/open nozzle) + BHA Rotary (B/S + 4 jts 4-3/4" DC + X/O) sampai 847 m. - Masuk joint per joint 4 jts 4-3/4" DC. | 6d | 6 | 173 | 2372 | 0 | 0.25 | 7.2083 | 2023-01-25 | -99.5 | 1900-01-03 03:30 | 2023-01-25 | 33.33% | 4.624% | HIDE | 3.0625 | 1112 | 7.2083 | 2372 | 0 | 2 | 3 |  |  |  | 80.0625 | WORKOVER SECTION | 6 | 21 | 5 | #VALUE!
[6 empty] | 73.5 | 0 | 3.0625 | 1112 | Lanjut masuk rangkaian 6-1/8" TCB + BHA Rotary dari 847 m sampai 2114.2 m. | 6d | 10 | 183 | 2372 | 0 | 0.41667 | 7.625 | 2023-01-25 10:00 | -109.5 | 1900-01-03 13:30 | 2023-01-26 | - | 4.372% | HIDE | 3.0625 | 1112 | 7.625 | 2372 | 0 | 2 | 3 |  |  |  | 83.125 | WORKOVER SECTION | 6 | 21 | 5 | #VALUE!
[6 empty] | 73.5 | 0 | 3.0625 | 1112 | M/U kelly dan 4" rotary hose. | 6d | 1 | 184 | 2372 | 0 | 0.041667 | 7.6667 | 2023-01-25 11:00 | -110.5 | 1900-01-03 14:30 | 2023-01-26 | - | 4.348% | HIDE | 3.0625 | 1112 | 7.6667 | 2372 | 0 | 2 | 3 |  |  |  | 86.1875 | WORKOVER SECTION | 6 | 21 | 5 | #VALUE!
|  | 18 | Drill Cement From 875 to 1041 m (blong). Rate 250 m/day |  | 8 | 81.5 | 0.33333 | 3.3958 | 1112 | Bor semen dengan 6-1/8" TCB dari 2114.2 m sampai 2210.4 m. - WOB/GPM/SPP/RPM/TQ/ROPavg : 2-3/168-210/500-700 psi/60/600-800 ft-lbs/7.57 mpm. - Semen blong di 2140.8-2149.8 m. | 2c | 13 | 197 | 2372 | 0 | 0.54167 | 8.2083 | 2023-01-26 | -115.5 | 1900-01-03 19:30 | 2023-01-26 | - | 4.061% | HIDE | 3.3958 | 1112 | 8.2083 | 2372 | 0 | 2 | 3 |  |  |  | 89.5833 | WORKOVER SECTION | 6 | 21 | 5 | #VALUE!
[6 empty] | 81.5 | 0 | 3.3958 | 1112 | Lanjut bor semen dengan 6-1/8" TCB dari 2210.4 m sampai 2243.2 m. - WOB/GPM/SPP/RPM/TQ/ROPavg : 2-3/168-210/500-700 psi/60/600-800 ft-lbs/18.29 mpm. | 2c | 11.5 | 208.5 | 2372 | 0 | 0.47917 | 8.6875 | 2023-01-26 11:30 | -127 | 1900-01-04 07:00 | 2023-01-27 | - | 3.837% | HIDE | 3.3958 | 1112 | 8.6875 | 2372 | 0 | 2 | 3 |  |  |  | 92.9792 | WORKOVER SECTION | 6 | 21 | 5 | #VALUE!
|  | 19 | Sirkulasi |  | 2 | 83.5 | 0.083333 | 3.4792 | 1112 | Sirkulasi 1x BU dengan GPM/SPP : 210/700 psi. - Flowcheck statik loss, baik. | 5a | 1.5 | 210 | 2372 | 0 | 0.0625 | 8.75 | 2023-01-26 13:00 | -126.5 | 1900-01-04 06:30 | 2023-01-27 | - | 3.81% | HIDE | 3.4792 | 1112 | 8.75 | 2372 | 0 | 2 | 3 |  |  |  | 96.4583 | WORKOVER SECTION | 6 | 21 | 5 | #VALUE!
[6 empty] | 83.5 | 0 | 3.4792 | 1112 | N/D kelly dan 4" rotary hose. | 6d | 1 | 211 | 2372 | 0 | 0.041667 | 8.7917 | 2023-01-26 14:00 | -127.5 | 1900-01-04 07:30 | 2023-01-27 | - | 3.791% | HIDE | 3.4792 | 1112 | 8.7917 | 2372 | 0 | 2 | 3 |  |  |  | 99.9375 | WORKOVER SECTION | 6 | 21 | 5 | #VALUE!
|  | 20 | POOH TCB 6" to Surface |  | 7 | 90.5 | 0.29167 | 3.7708 | 1112 | Cabut rangkaian 6-1/8" TCB (RR) + BHA Rotary dari 2243.2 m sampai permukaan. - Fill up annulus setiap 20 jts. - L/D 4 jts 4-3/4" DC. | 6d | 10 | 221 | 2372 | 0 | 0.41667 | 9.2083 | 2023-01-27 | -130.5 | 1900-01-04 10:30 | 2023-01-27 | - | 3.62% | HIDE | 3.7708 | 1112 | 9.2083 | 2372 | 0 | 2 | 3 |  |  |  | 103.7083 | WORKOVER SECTION | 6 | 21 | 5 | #VALUE!
[6 empty] | 90.5 | 0 | 3.7708 | 1112 | M/U dan masuk rangkaian 3-3/4" TCB (NB, IADC : 221, Nozz : CJ) + BHA Rotary (B/S + 4 jts 3-1/8" DC) sampai 2283.8 m (TOC). - Masuk joint per joint 4 jts 3-1/8" DC + 16 jts 2-3/8" DP. - Break sirkulasi setiap 20 jts. - Rangkaian duduk 2-4 klbs di 2283.8 m. | 6d | 15 | 236 | 2372 | 0 | 0.625 | 9.8333 | 2023-01-27 15:00 | -145.5 | 1900-01-05 01:30 | 2023-01-28 | - | 3.39% | HIDE | 3.7708 | 1112 | 9.8333 | 2372 | 0 | 2 | 3 |  |  |  | 107.4792 | WORKOVER SECTION | 6 | 21 | 5 | #VALUE!
[6 empty] | 90.5 | 0 | 3.7708 | 1112 | Flowcheck statik loss, tidak ada penurunan. Pressure test casing dengan 500 psi/10 menit, baik. | 2f | 0.5 | 236.5 | 2372 | 0 | 0.020833 | 9.8542 | 2023-01-27 15:30 | -146 | 1900-01-05 02:00 | 2023-01-28 | - | 3.383% | HIDE | 3.7708 | 1112 | 9.8542 | 2372 | 0 | 2 | 3 |  |  |  | 111.25 | WORKOVER SECTION | 6 | 21 | 5 | #VALUE!
[6 empty] | 90.5 | 0 | 3.7708 | 1112 | Gelar dan ukur 10 jts 3-1/2" DP. | 6b | 0.5 | 237 | 2372 | 0 | 0.020833 | 9.875 | 2023-01-27 16:00 | -146.5 | 1900-01-05 02:30 | 2023-01-28 | - | 3.376% | HIDE | 3.7708 | 1112 | 9.875 | 2372 | 0 | 2 | 3 |  |  |  | 115.0208 | WORKOVER SECTION | 6 | 21 | 5 | #VALUE!
[6 empty] | 90.5 | 0 | 3.7708 | 1112 | M/U kelly dan 4" rotary hose. - Lanjut ukur 10 jts 3-1/2" DP. | 6d | 1 | 238 | 2372 | 0 | 0.041667 | 9.9167 | 2023-01-27 17:00 | -147.5 | 1900-01-05 03:30 | 2023-01-28 | - | 3.361% | HIDE | 3.7708 | 1112 | 9.9167 | 2372 | 0 | 2 | 3 |  |  |  | 118.7917 | WORKOVER SECTION | 6 | 21 | 5 | #VALUE!
[6 empty] | 90.5 | 0 | 3.7708 | 1112 | Bor semen dengan 3-3/4" TCB dari 2283.8 m sampai 2306.8 m. - WOB/GPM/SPP/RPM/TQ/ROPavg : 1-2 klbs/210/1000 psi/60/800-900 ft-lbs/1.42 mpm. - Setelah kelly down lakukan sirkulasi dengan GPM/SPP : 252/1200 psi. - Keluar cutting bubur semen. | 2c | 2 | 240 | 2372 | 0 | 0.083333 | 10 | 2023-01-27 19:00 | -149.5 | 1900-01-05 05:30 | 2023-01-28 | - | 3.333% | HIDE | 3.7708 | 1112 | 10 | 2372 | 0 | 2 | 3 |  |  |  | 122.5625 | WORKOVER SECTION | 6 | 21 | 5 | #VALUE!
[6 empty] | 90.5 | 0 | 3.7708 | 1112 | Hujan deras disertai angin (unsafe condition). | 23a | 1 | 241 | 2372 | 0 | 0.041667 | 10.0417 | 2023-01-27 20:00 | -150.5 | 1900-01-05 06:30 | 2023-01-28 | - | 3.32% | HIDE | 3.7708 | 1112 | 10.0417 | 2372 | 0 | 2 | 3 |  |  |  | 126.3333 | WORKOVER SECTION | 6 | 21 | 5 | #VALUE!
[6 empty] | 90.5 | 0 | 3.7708 | 1112 | Lanjut bor dengan 3-3/4" TCB dari 2306.8 m sampai 2330 m. - WOB/GPM/SPP/RPM/TQ/ROPavg : 1-2 klbs/210/1000 psi/60/800-900 ft-lbs/1.29 mpm. - Setelah kelly down lakukan sirkulasi dengan GPM/SPP : 252/1200 psi. - Keluar cutting bubur semen. | 2c | 2 | 243 | 2372 | 0 | 0.083333 | 10.125 | 2023-01-27 22:00 | -152.5 | 1900-01-05 08:30 | 2023-01-28 | - | 3.292% | HIDE | 3.7708 | 1112 | 10.125 | 2372 | 0 | 2 | 3 |  |  |  | 130.1042 | WORKOVER SECTION | 6 | 21 | 5 | #VALUE!
[6 empty] | 90.5 | 0 | 3.7708 | 1112 | Pressure test casing dengan 500 psi/10 menit, baik. | 2f | 0.5 | 243.5 | 2372 | 0 | 0.020833 | 10.1458 | 2023-01-27 22:30 | -153 | 1900-01-05 09:00 | 2023-01-28 | - | 3.285% | HIDE | 3.7708 | 1112 | 10.1458 | 2372 | 0 | 2 | 3 |  |  |  | 133.875 | WORKOVER SECTION | 6 | 21 | 5 | #VALUE!
[6 empty] | 90.5 | 0 | 3.7708 | 1112 | Lanjut bor dengan 3-3/4" TCB dari 2330 m sampai 2340 m. - WOB/GPM/SPP/RPM/TQ/ROPavg : 1-2 klbs/126-210/500-1000 psi/60/800-900 ft-lbs/1.90 mpm. - Keluar cutting bubur semen. - Terdapat loss di 2335 m, tidak ada aliran. - Pin rantai rotary table putus. | 2c | 1.5 | 245 | 2372 | 0 | 0.0625 | 10.2083 | 2023-01-28 | -154.5 | 1900-01-05 10:30 | 2023-01-28 | - | 3.265% | HIDE | 3.7708 | 1112 | 10.2083 | 2372 | 0 | 2 | 3 |  |  |  | 137.6458 | WORKOVER SECTION | 6 | 21 | 5 | #VALUE!
[6 empty] | 90.5 | 0 | 3.7708 | 1112 | Usaha perbaikan pin rantai rotary table. (NPT Rig GJE #11 (Repair rotating system) : 2 jam, Kumm NPT Rig GJE #11 : 10 jam) - Sambil sirkulasi dengan GPM/SPP : 84/100 psi, tidak ada aliran. - Usaha masuk lebih dalam dengan wash down (GPM/SPP : 252/450 psi), terdapat dudukan sampai 5 klbs. | 8d | 2 | 247 | 2372 | NPT | 0.083333 | 10.2917 | 2023-01-28 02:00 | -156.5 | 1900-01-05 12:30 | 2023-01-29 | 100% | 4.049% | HIDE | 3.7708 | 1112 | 10.2917 | 2372 | 0 | 2 | 3 |  |  |  | 141.4167 | WORKOVER SECTION | 6 | 21 | 5 | #VALUE!
[6 empty] | 90.5 | 0 | 3.7708 | 1112 | Lanjut bor dengan 3-3/4" TCB dari 2340 m sampai 2344 m. - WOB/GPM/SPP/RPM/TQ/ROPavg : 1-2 klbs/126-210/500-1000 psi/60/800-900 ft-lbs/1.75 mpm. - Pin rantai rotary table putus kembali. | 2c | 0.5 | 247.5 | 2372 | 0 | 0.020833 | 10.3125 | 2023-01-28 02:30 | -157 | 1900-01-05 13:00 | 2023-01-29 | 80% | 4.04% | HIDE | 3.7708 | 1112 | 10.3125 | 2372 | 0 | 2 | 3 |  |  |  | 145.1875 | WORKOVER SECTION | 6 | 21 | 5 | #VALUE!
[6 empty] | 90.5 | 0 | 3.7708 | 1112 | Usaha perbaikan pin rantai rotary table. (NPT Rig GJE #11 (Repair rotating system) : 1.5 jam, Kumm NPT Rig GJE #11 : 11.5 jam) - Sambil sirkulasi dengan GPM/SPP : 84/100 psi, tidak ada aliran. - Usaha masuk lebih dalam dengan wash down (GPM/SPP : 252/450 psi), terdapat dudukan sampai 5 klbs. | 8d | 1.5 | 249 | 2372 | NPT | 0.0625 | 10.375 | 2023-01-28 04:00 | -158.5 | 1900-01-05 14:30 | 2023-01-29 | 87.5% | 4.618% | HIDE | 3.7708 | 1112 | 10.375 | 2372 | 0 | 2 | 3 |  |  |  | 148.9583 | WORKOVER SECTION | 6 | 21 | 5 | #VALUE!
[6 empty] | 90.5 | 0 | 3.7708 | 1112 | Lanjut bor dengan 3-3/4" TCB dari 2344 m sampai 2349.8 m. - WOB/GPM/SPP/RPM/TQ/ROPavg : 1-2 klbs/210/800 psi/60/800-900 ft-lbs/2.17 mpm. | 2c | 0.5 | 249.5 | 2372 | 0 | 0.020833 | 10.3958 | 2023-01-28 04:30 | -159 | 1900-01-05 15:00 | 2023-01-29 | 77.78% | 4.609% | HIDE | 3.7708 | 1112 | 10.3958 | 2372 | 0 | 2 | 3 |  |  |  | 152.7292 | WORKOVER SECTION | 6 | 21 | 5 | #VALUE!
[6 empty] | 90.5 | 0 | 3.7708 | 1112 | Sirkulasi 1x BU dengan GPM/SPP : 210/800 psi, tidak ada return. | 5a | 1.5 | 251 | 2372 | 0 | 0.0625 | 10.4583 | 2023-01-28 06:00 | -160.5 | 1900-01-05 16:30 | 2023-01-29 | 58.33% | 4.582% | HIDE | 3.7708 | 1112 | 10.4583 | 2372 | 0 | 2 | 3 |  |  |  | 156.5 | WORKOVER SECTION | 6 | 21 | 5 | #VALUE!
[6 empty] | 90.5 | 0 | 3.7708 | 1112 | N/D kelly dan 4" rotary hose. | 6d | 1 | 252 | 2372 | 0 | 0.041667 | 10.5 | 2023-01-28 07:00 | -161.5 | 1900-01-05 17:30 | 2023-01-29 | 50% | 4.563% | HIDE | 3.7708 | 1112 | 10.5 | 2372 | 0 | 2 | 3 |  |  |  | 160.2708 | WORKOVER SECTION | 6 | 21 | 5 | #VALUE!
[6 empty] | 90.5 | 0 | 3.7708 | 1112 | Cabut rangkaian 3-3/4" TCB + BHA Rotary dari 2349.8 m sampai permukaan. - L/D 43 jts 3-1/2" DP. - Fill up annulus setiap 20 jts. | 6d | 11 | 263 | 2372 | 0 | 0.45833 | 10.9583 | 2023-01-28 18:00 | -172.5 | 1900-01-06 04:30 | 2023-01-29 | 19.44% | 4.373% | HIDE | 3.7708 | 1112 | 10.9583 | 2372 | 0 | 2 | 3 |  |  |  | 164.0417 | WORKOVER SECTION | 6 | 21 | 5 | #VALUE!
[6 empty] | 90.5 | 0 | 3.7708 | 1112 | Masuk ROE (2-3/8" saw tooth + 15 jts 2-3/8" tubing (bekas) + X/O + 45 jts 2-7/8" tubing (bekas)) sampai 564 m. - Masuk joint per joint 15 jts 2-3/8" tubing (bekas) + 45 jts 2-7/8" tubing (bekas). | 6g | 6 | 269 | 2372 | 0 | 0.25 | 11.2083 | 2023-01-29 | -178.5 | 1900-01-06 10:30 | 2023-01-29 | 14.58% | 4.275% | HIDE | 3.7708 | 1112 | 11.2083 | 2372 | 0 | 2 | 3 |  |  |  | 167.8125 | WORKOVER SECTION | 6 | 21 | 5 | #VALUE!
[6 empty] | 90.5 | 0 | 3.7708 | 1112 | Lanjut masuk ROE (2-3/8" saw tooth + 15 jts 2-3/8" tubing (bekas) + X/O + 58 jts 2-7/8" tubing (bekas) + 2-7/8" pup joint 6 ft (bekas) + 2 jts 2-7/8" tubing (bekas) + X/O + X/O + 170 jts 2-7/8" DP) dari 564 m sampai 2346.6 m. - Masuk joint per joint 15 jts 2-7/8" tubing (bekas). | 6g | 7 | 276 | 2372 | 0 | 0.29167 | 11.5 | 2023-01-29 07:00 | -185.5 | 1900-01-06 17:30 | 2023-01-30 | - | 4.167% | HIDE | 3.7708 | 1112 | 11.5 | 2372 | 0 | 2 | 3 |  |  |  | 171.5833 | WORKOVER SECTION | 6 | 21 | 5 | #VALUE!
[6 empty] | 90.5 | 0 | 3.7708 | 1112 | Sirkulasi 1x cycle (450 bbl) dengan GPM/SPP : 210/0 psi, tidak ada return. | 5a | 1.5 | 277.5 | 2372 | 0 | 0.0625 | 11.5625 | 2023-01-29 08:30 | -187 | 1900-01-06 19:00 | 2023-01-30 | - | 4.144% | HIDE | 3.7708 | 1112 | 11.5625 | 2372 | 0 | 2 | 3 |  |  |  | 175.3542 | WORKOVER SECTION | 6 | 21 | 5 | #VALUE!
[6 empty] | 90.5 | 0 | 3.7708 | 1112 | Persiapan squeeze ke-3 lapisan eksisting BRF interval 2337-2344 m. - Ambil 370 bbl AA dengan vakum truck di SPA-019 (injection well). - PJSM. - M/U cementing line dan plug valve cementing. - Mixing additive semen. | 18a | 2 | 279.5 | 2372 | 0 | 0.083333 | 11.6458 | 2023-01-29 10:30 | -189 | 1900-01-06 21:00 | 2023-01-30 | - | 4.114% | HIDE | 3.7708 | 1112 | 11.6458 | 2372 | 0 | 2 | 3 |  |  |  | 179.125 | WORKOVER SECTION | 6 | 21 | 5 | #VALUE!
[6 empty] | 90.5 | 0 | 3.7708 | 1112 | Squeeze ke-3 lapisan eksisting BRF interval 2337-2344 m. - Pressure test cementing line 2000 psi/5 mnt, baik. - Pompakan 16.8 bbl water ahead 8.33 ppg dengan rate 2 bpm, pressure 0-10 psi. - Aduk dan pompakan 8 bbl semen 15.8 ppg dengan rate 2 bpm, pressure 40-60 psi. - Pompakan 3.2 bbl water behind 8.33 ppg dengan rate 2 bpm, pressure 30-40 psi. - Displace 34.3 bbls AA 8.41 ppg dengan rate 1 bpm, pressure 10 psi. - Lepas cementing line dan plug valve cementing. Note : Selama pekerjaan squeeze tidak ada return. | 18a | 2.5 | 282 | 2372 | 0 | 0.10417 | 11.75 | 2023-01-29 13:00 | -191.5 | 1900-01-06 23:30 | 2023-01-30 | - | 4.078% | HIDE | 3.7708 | 1112 | 11.75 | 2372 | 0 | 2 | 3 |  |  |  | 182.8958 | WORKOVER SECTION | 6 | 21 | 5 | #VALUE!
[6 empty] | 90.5 | 0 | 3.7708 | 1112 | Cabut ROE dari 2346.6 m sampai 2065.3 m. | 6g | 1 | 283 | 2372 | 0 | 0.041667 | 11.7917 | 2023-01-29 14:00 | -192.5 | 1900-01-07 00:30 | 2023-01-30 | - | 4.064% | HIDE | 3.7708 | 1112 | 11.7917 | 2372 | 0 | 2 | 3 |  |  |  | 186.6667 | WORKOVER SECTION | 6 | 21 | 5 | #VALUE!
[6 empty] | 90.5 | 0 | 3.7708 | 1112 | Hesitasi dengan rate 1 bpm, volume 3 bbl, pressure 10 psi. Stop pompa, pressure langsung turun sampai 0 psi. - M/U cementing line dan plug valve cementing. - Tutup annular dan pipe ram BOP. | 18a | 0.5 | 283.5 | 2372 | 0 | 0.020833 | 11.8125 | 2023-01-29 14:30 | -193 | 1900-01-07 01:00 | 2023-01-30 | - | 4.056% | HIDE | 3.7708 | 1112 | 11.8125 | 2372 | 0 | 2 | 3 |  |  |  | 190.4375 | WORKOVER SECTION | 6 | 21 | 5 | #VALUE!
[6 empty] | 90.5 | 0 | 3.7708 | 1112 | TSK vakum. - Sample semen di water batch belum keras. | 13a | 9.5 | 293 | 2372 | 0 | 0.39583 | 12.2083 | 2023-01-30 | -202.5 | 1900-01-07 10:30 | 2023-01-30 | - | 3.925% | HIDE | 3.7708 | 1112 | 12.2083 | 2372 | 0 | 2 | 3 |  |  |  | 194.2083 | WORKOVER SECTION | 6 | 21 | 5 | #VALUE!
[6 empty] | 90.5 | 0 | 3.7708 | 1112 | Lanjut TSK vakum. - Sample semen di water batch sudah keras. - Buka annular dan pipe ram BOP. | 13a | 12 | 305 | 2372 | 0 | 0.5 | 12.7083 | 2023-01-30 12:00 | -214.5 | 1900-01-07 22:30 | 2023-01-31 | - | 3.77% | HIDE | 3.7708 | 1112 | 12.7083 | 2372 | 0 | 2 | 3 |  |  |  | 197.9792 | WORKOVER SECTION | 6 | 21 | 5 | #VALUE!
[6 empty] | 90.5 | 0 | 3.7708 | 1112 | Masuk ROE (2-3/8" saw tooth + 15 jts 2-3/8" tubing (bekas) + X/O + 58 jts 2-7/8" tubing (bekas) + 2-7/8" pup joint 6 ft (bekas) + 2 jts 2-7/8" tubing (bekas) + X/O + X/O + 163 jts 2-7/8" DP) dari 2065.3 m sampai 2276.4 m. - Rangkaian duduk 4 klbs di 2276.4 m (TOC). | 6g | 1 | 306 | 2372 | 0 | 0.041667 | 12.75 | 2023-01-30 13:00 | -215.5 | 1900-01-07 23:30 | 2023-01-31 | - | 3.758% | HIDE | 3.7708 | 1112 | 12.75 | 2372 | 0 | 2 | 3 |  |  |  | 201.75 | WORKOVER SECTION | 6 | 21 | 5 | #VALUE!
[6 empty] | 90.5 | 0 | 3.7708 | 1112 | Fill up sumur dengan 125 bbl AA 1.01 SG, keluar return. | 5a | 1 | 307 | 2372 | 0 | 0.041667 | 12.7917 | 2023-01-30 14:00 | -216.5 | 1900-01-08 00:30 | 2023-01-31 | - | 3.746% | HIDE | 3.7708 | 1112 | 12.7917 | 2372 | 0 | 2 | 3 |  |  |  | 205.5208 | WORKOVER SECTION | 6 | 21 | 5 | #VALUE!
[6 empty] | 90.5 | 0 | 3.7708 | 1112 | Flowcheck statik loss, tidak ada penurunan. Pressure test casing dengan 500 psi/10 menit, baik. | 2f | 0.5 | 307.5 | 2372 | 0 | 0.020833 | 12.8125 | 2023-01-30 14:30 | -217 | 1900-01-08 01:00 | 2023-01-31 | - | 3.74% | HIDE | 3.7708 | 1112 | 12.8125 | 2372 | 0 | 2 | 3 |  |  |  | 209.2917 | WORKOVER SECTION | 6 | 21 | 5 | #VALUE!
[6 empty] | 90.5 | 0 | 3.7708 | 1112 | Cabut ROE dari 2276.4 m sampai 279.1 m. - Fill up annulus setiap 20 jts. - L/D 45 jts 2-7/8" tubing (bekas). | 6g | 9.5 | 317 | 2372 | 0 | 0.39583 | 13.2083 | 2023-01-31 | -226.5 | 1900-01-08 10:30 | 2023-01-31 | - | 3.628% | HIDE | 3.7708 | 1112 | 13.2083 | 2372 | 0 | 2 | 3 |  |  |  | 213.0625 | WORKOVER SECTION | 6 | 21 | 5 | #VALUE!
[6 empty] | 90.5 | 0 | 3.7708 | 1112 | Lanjut cabut ROE dari 279.1 m sampai permukaan. - Fill up annulus setiap 20 jts. - L/D 15 jts 2-7/8" tubing (bekas) + 15 jts 2-3/8" tubing (bekas). | 6g | 2 | 319 | 2372 | 0 | 0.083333 | 13.2917 | 2023-01-31 02:00 | -228.5 | 1900-01-08 12:30 | 2023-02-01 | - | 3.605% | HIDE | 3.7708 | 1112 | 13.2917 | 2372 | 0 | 2 | 3 |  |  |  | 216.8333 | WORKOVER SECTION | 6 | 21 | 5 | #VALUE!
[6 empty] | 90.5 | 0 | 3.7708 | 1112 | M/U dan masuk rangkaian 3-3/4" TCB (RR, IADC : 221, Nozz : CJ) + BHA Rotary (B/S + 4 jts 3-1/8" DC) sampai 2276.4 m. - Masuk joint per joint 16 jts 2-3/8" DP. | 6d | 12.5 | 331.5 | 2372 | 0 | 0.52083 | 13.8125 | 2023-01-31 14:30 | -241 | 1900-01-09 01:00 | 2023-02-01 | - | 3.469% | HIDE | 3.7708 | 1112 | 13.8125 | 2372 | 0 | 2 | 3 |  |  |  | 220.6042 | WORKOVER SECTION | 6 | 21 | 5 | #VALUE!
[6 empty] | 90.5 | 0 | 3.7708 | 1112 | M/U kelly dan 4" rotary hose. | 6d | 1 | 332.5 | 2372 | 0 | 0.041667 | 13.8542 | 2023-01-31 15:30 | -242 | 1900-01-09 02:00 | 2023-02-01 | - | 3.459% | HIDE | 3.7708 | 1112 | 13.8542 | 2372 | 0 | 2 | 3 |  |  |  | 224.375 | WORKOVER SECTION | 6 | 21 | 5 | #VALUE!
[6 empty] | 90.5 | 0 | 3.7708 | 1112 | Bor semen dengan 3-3/4" TCB dari 2276.4 m sampai 2321 m. - WOB/GPM/SPP/RPM/TQ/ROPavg : 1-2 klbs/210/1000 psi/60/800-900 ft-lbs/3.59 mpm. - Cutting semen. - Tidak ada loss. - Sirkulasi 1.5x BU sambil WOP setelah kelly down dengan GPM/SPP : 252/1200 psi. | 2c | 8.5 | 341 | 2372 | 0 | 0.35417 | 14.2083 | 2023-02-01 | -250.5 | 1900-01-09 10:30 | 2023-02-01 | - | 3.372% | HIDE | 3.7708 | 1112 | 14.2083 | 2372 | 0 | 2 | 3 |  |  |  | 228.1458 | WORKOVER SECTION | 6 | 21 | 5 | #VALUE!
[6 empty] | 90.5 | 0 | 3.7708 | 1112 | Lanjut bor semen dengan 3-3/4" TCB dari 2321 m sampai 2330 m. - WOB/GPM/SPP/RPM/TQ/ROPavg : 1-2 klbs/210/1000 psi/60/800-900 ft-lbs/5.55 mpm. - Cutting semen. - Tidak ada loss. - Sirkulasi 1.5x BU sambil WOP setelah kelly down dengan GPM/SPP : 252/1200 psi. | 2c | 2 | 343 | 2372 | 0 | 0.083333 | 14.2917 | 2023-02-01 02:00 | -252.5 | 1900-01-09 12:30 | 2023-02-02 | - | 3.353% | HIDE | 3.7708 | 1112 | 14.2917 | 2372 | 0 | 2 | 3 |  |  |  | 231.9167 | WORKOVER SECTION | 6 | 21 | 5 | #VALUE!
[6 empty] | 90.5 | 0 | 3.7708 | 1112 | Pressure test casing dengan 500 psi/10 menit, baik. | 2f | 1 | 344 | 2372 | 0 | 0.041667 | 14.3333 | 2023-02-01 03:00 | -253.5 | 1900-01-09 13:30 | 2023-02-02 | - | 3.343% | HIDE | 3.7708 | 1112 | 14.3333 | 2372 | 0 | 2 | 3 |  |  |  | 235.6875 | WORKOVER SECTION | 6 | 21 | 5 | #VALUE!
[6 empty] | 90.5 | 0 | 3.7708 | 1112 | Lanjut bor semen dengan 3-3/4" TCB dari 2330 m sampai 2347 m. - WOB/GPM/SPP/RPM/TQ/ROPavg : 1-2 klbs/210/1000 psi/60/800-900 ft-lbs/4.94 mpm. - Cutting semen. - Tidak ada loss. - Sirkulasi 1.5x BU sambil WOP setelah kelly down dengan GPM/SPP : 252/1200 psi. | 2c | 2 | 346 | 2372 | 0 | 0.083333 | 14.4167 | 2023-02-01 05:00 | -255.5 | 1900-01-09 15:30 | 2023-02-02 | - | 3.324% | HIDE | 3.7708 | 1112 | 14.4167 | 2372 | 0 | 2 | 3 |  |  |  | 239.4583 | WORKOVER SECTION | 6 | 21 | 5 | #VALUE!
[6 empty] | 90.5 | 0 | 3.7708 | 1112 | Pressure test casing dengan 500 psi/10 menit, baik. | 2f | 1 | 347 | 2372 | 0 | 0.041667 | 14.4583 | 2023-02-01 06:00 | -256.5 | 1900-01-09 16:30 | 2023-02-02 | - | 3.314% | HIDE | 3.7708 | 1112 | 14.4583 | 2372 | 0 | 2 | 3 |  |  |  | 243.2292 | WORKOVER SECTION | 6 | 21 | 5 | #VALUE!
[6 empty] | 90.5 | 0 | 3.7708 | 1112 | Lanjut bor semen dengan 3-3/4" TCB dari 2347 m sampai 2374.8 m. - WOB/GPM/SPP/RPM/TQ/ROPavg : 1-2 klbs/210/1000 psi/60/800-900 ft-lbs/6.47 mpm. - Cutting semen. - Tidak ada loss. - Sirkulasi 1.5x BU sambil WOP setelah kelly down dengan GPM/SPP : 252/1200 psi. | 2c | 6.5 | 353.5 | 2374.8 | 0 | 0.27083 | 14.7292 | 2023-02-01 12:30 | -263 | 1900-01-09 23:00 | 2023-02-02 | - | 3.253% | HIDE | 3.7708 | 1112 | 14.7292 | 2374.8 | 0 | 2 | 3 |  |  |  | 247 | WORKOVER SECTION | 6 | 21 | 5 | #VALUE!
[6 empty] | 90.5 | 0 | 3.7708 | 1112 | Sirkulasi bersih dengan GPM/SPP : 252/1200 psi. | 5a | 2 | 355.5 | 2374.8 | 0 | 0.083333 | 14.8125 | 2023-02-01 14:30 | -265 | 1900-01-10 01:00 | 2023-02-02 | - | 3.235% | HIDE | 3.7708 | 1112 | 14.8125 | 2374.8 | 0 | 2 | 3 |  |  |  | 250.7708 | WORKOVER SECTION | 6 | 21 | 5 | #VALUE!
|  |  |  | ` |  | 90.5 | 0 | 3.7708 | 1112 | N/D kelly dan 4" rotary hose. | 6d | 1 | 356.5 | 2374.8 | 0 | 0.041667 | 14.8542 | 2023-02-01 15:30 | -266 | 1900-01-10 02:00 | 2023-02-02 | - | 3.226% | HIDE | 3.7708 | 1112 | 14.8542 | 2374.8 | 0 | 2 | 3 |  |  |  | 254.5417 | WORKOVER SECTION | 6 | 21 | 5 | #VALUE!
[6 empty] | 90.5 | 0 | 3.7708 | 1112 | Cabut rangkaian 3-3/4" TCB + BHA Rotary dari 2374.8 m sampai permukaan. - Fill up annulus setiap 50 joint. | 6d | 8.5 | 365 | 2374.8 | 0 | 0.35417 | 15.2083 | 2023-02-02 | -274.5 | 1900-01-10 10:30 | 2023-02-02 | - | 3.151% | HIDE | 3.7708 | 1112 | 15.2083 | 2374.8 | 0 | 2 | 3 |  |  |  | 258.3125 | WORKOVER SECTION | 6 | 21 | 5 | #VALUE!
|  | 21 | RIH Scraper 7" to 1175 m |  | 7 | 97.5 | 0.29167 | 4.0625 | 1112 | M/U dan masuk rangkaian 3-3/4" TCB (RR, IADC : 221, Nozz : CJ) + Scraper 4-1/2" tandem Scraper 7" sampai 2371.5 m. - Break sirkulasi setiap 20 joint. - Rangkaian duduk 4 klbs di 2371.5 m, pasang circulating head. | 26a | 12 | 377 | 2374.8 | 0 | 0.5 | 15.7083 | 2023-02-02 12:00 | -279.5 | 1900-01-10 15:30 | 2023-02-03 | - | 3.05% | HIDE | 4.0625 | 1112 | 15.7083 | 2374.8 | 0 | 2 | 3 |  |  |  | 262.375 | WORKOVER SECTION | 6 | 21 | 5 | #VALUE!
[6 empty] | 97.5 | 0 | 4.0625 | 1112 | Usaha masuk rangkaian lebih dalam dengan wash down dari 2371.5 m sampai 2374.8 m. - WOB/GPM/SPP : 1 klbs/250/1200 psi. | 3a | 2 | 379 | 2374.8 | 0 | 0.083333 | 15.7917 | 2023-02-02 14:00 | -281.5 | 1900-01-10 17:30 | 2023-02-03 | - | 3.034% | HIDE | 4.0625 | 1112 | 15.7917 | 2374.8 | 0 | 2 | 3 |  |  |  | 266.4375 | WORKOVER SECTION | 6 | 21 | 5 | #VALUE!
|  | 22 | Sirkulasi |  | 2 | 99.5 | 0.083333 | 4.1458 | 1112 | Sirkulasi bersih sambil WOP dengan GPM/SPP : 250/1200 psi. - Keluar cutting semen halus. | 5a | 2 | 381 | 2374.8 | 0 | 0.083333 | 15.875 | 2023-02-02 16:00 | -281.5 | 1900-01-10 17:30 | 2023-02-03 | - | 3.018% | HIDE | 4.1458 | 1112 | 15.875 | 2374.8 | 0 | 2 | 3 |  |  |  | 270.5833 | WORKOVER SECTION | 6 | 21 | 5 | #VALUE!
|  | 23 | POOH Scraper 7" to Surface |  | 7 | 106.5 | 0.29167 | 4.4375 | 1112 | Cabut rangkaian 3-3/4" TCB + Scraper 4-1/2" tandem Scraper 7" dari 2374.8 m sampai 863 m. - Fill up annulus setiap 50 joint. | 26a | 8 | 389 | 2374.8 | 0 | 0.33333 | 16.2083 | 2023-02-03 | -282.5 | 1900-01-10 18:30 | 2023-02-03 | - | 2.956% | HIDE | 4.4375 | 1112 | 16.2083 | 2374.8 | 0 | 2 | 3 |  |  |  | 275.0208 | WORKOVER SECTION | 6 | 21 | 5 | #VALUE!
[6 empty] | 106.5 | 0 | 4.4375 | 1112 | Lanjut cabut rangkaian 3-3/4" TCB + Scraper 4-1/2" tandem Scraper 7" dari 863 m sampai permukaan. - Fill up annulus setiap 50 joint. | 26a | 4 | 393 | 2374.8 | 0 | 0.16667 | 16.375 | 2023-02-03 04:00 | -286.5 | 1900-01-10 22:30 | 2023-02-04 | - | 2.926% | HIDE | 4.4375 | 1112 | 16.375 | 2374.8 | 0 | 2 | 3 |  |  |  | 279.4583 | WORKOVER SECTION | 6 | 21 | 5 | #VALUE!
[6 empty] | 106.5 | 0 | 4.4375 | 1112 | N/D bell nipple. | 14c | 1 | 394 | 2374.8 | 0 | 0.041667 | 16.4167 | 2023-02-03 05:00 | -287.5 | 1900-01-10 23:30 | 2023-02-04 | - | 2.919% | HIDE | 4.4375 | 1112 | 16.4167 | 2374.8 | 0 | 2 | 3 |  |  |  | 283.8958 | WORKOVER SECTION | 6 | 21 | 5 | #VALUE!
|  | 24 | Rig Up Wireline |  | 2 | 108.5 | 0.083333 | 4.5208 | 1112 | R/U wireline unit Elnusa. - N/U upper dan lower sheave wheels. | 11a | 4 | 398 | 2374.8 | 0 | 0.16667 | 16.5833 | 2023-02-03 09:00 | -289.5 | 1900-01-11 01:30 | 2023-02-04 | - | 2.889% | HIDE | 4.5208 | 1112 | 16.5833 | 2374.8 | 0 | 2 | 3 |  |  |  | 288.4167 | WORKOVER SECTION | 6 | 21 | 5 | #VALUE!
|  | 25 | Run GR-CBL-CNL |  | 8 | 116.5 | 0.33333 | 4.8542 | 1112 | Run logging CBL-GR sampai 2371.5 m. | 11a | 3 | 401 | 2374.8 | 0 | 0.125 | 16.7083 | 2023-02-03 12:00 | -284.5 | 1900-01-10 20:30 | 2023-02-04 | - | 2.868% | HIDE | 4.8542 | 1112 | 16.7083 | 2374.8 | 0 | 2 | 3 |  |  |  | 293.2708 | WORKOVER SECTION | 6 | 21 | 5 | #VALUE!
[6 empty] | 116.5 | 0 | 4.8542 | 1112 | Analisa hasil CBL, diputuskan lanjut perforasi produksi. | 11b | 1 | 402 | 2374.8 | 0 | 0.041667 | 16.75 | 2023-02-03 13:00 | -285.5 | 1900-01-10 21:30 | 2023-02-04 | - | 2.861% | HIDE | 4.8542 | 1112 | 16.75 | 2374.8 | 0 | 2 | 3 |  |  |  | 298.125 | WORKOVER SECTION | 6 | 21 | 5 | #VALUE!
[6 empty] | 116.5 | 0 | 4.8542 | 1112 | R/D wireline unit Elnusa. - N/D upper dan lower sheave wheels. | 11a | 1 | 403 | 2374.8 | 0 | 0.041667 | 16.7917 | 2023-02-03 14:00 | -286.5 | 1900-01-10 22:30 | 2023-02-04 | - | 2.854% | HIDE | 4.8542 | 1112 | 16.7917 | 2374.8 | 0 | 2 | 3 |  |  |  | 302.9792 | WORKOVER SECTION | 6 | 21 | 5 | #VALUE!
[6 empty] | 116.5 | 0 | 4.8542 | 1112 | N/U bell nipple. | 14b | 1 | 404 | 2374.8 | 0 | 0.041667 | 16.8333 | 2023-02-03 15:00 | -287.5 | 1900-01-10 23:30 | 2023-02-04 | - | 2.847% | HIDE | 4.8542 | 1112 | 16.8333 | 2374.8 | 0 | 2 | 3 |  |  |  | 307.8333 | WORKOVER SECTION | 6 | 21 | 5 | #VALUE!
[6 empty] | 116.5 | 0 | 4.8542 | 1112 | Masuk rangkaian flexing 2-3/8" plug + 4 jts 3-1/8" DC + X/O + 14 jts 2-3/8" DP + X/O + 116 jts 2-7/8" DP sampai 1253 m. - Pressure test 1800 psi/5 menit setiap 20 jts, baik. | 26c | 9 | 413 | 2374.8 | 0 | 0.375 | 17.2083 | 2023-02-04 | -296.5 | 1900-01-11 08:30 | 2023-02-04 | - | 2.785% | HIDE | 4.8542 | 1112 | 17.2083 | 2374.8 | 0 | 2 | 3 |  |  |  | 312.6875 | WORKOVER SECTION | 6 | 21 | 5 | #VALUE!
[6 empty] | 116.5 | 0 | 4.8542 | 1112 | Lanjut masuk rangkaian flexing 2-3/8" plug + 4 jts 3-1/8" DC + X/O + 14 jts 2-3/8" DP + X/O + 170 jts 2-7/8" DP dari 1253 m sampai 1813 m. - Pressure test 1800 psi/5 menit setiap 20 jts, baik. | 26c | 4 | 417 | 2374.8 | 0 | 0.16667 | 17.375 | 2023-02-04 04:00 | -300.5 | 1900-01-11 12:30 | 2023-02-05 | - | 2.758% | HIDE | 4.8542 | 1112 | 17.375 | 2374.8 | 0 | 2 | 3 |  |  |  | 317.5417 | WORKOVER SECTION | 6 | 21 | 5 | #VALUE!
[6 empty] | 116.5 | 0 | 4.8542 | 1112 | Cabut rangkaian flexing 2-3/8" plug + 4 jts 3-1/8" DC + X/O + 14 jts 2-3/8" DP + X/O + 170 jts 2-7/8" DP dari 1813 m sampai permukaan. - (08:00) Mobilisasi handak dari gudang Field Pendopo ke lokasi SPA-034. | 26c | 7 | 424 | 2374.8 | 0 | 0.29167 | 17.6667 | 2023-02-04 11:00 | -307.5 | 1900-01-11 19:30 | 2023-02-05 | - | 2.712% | HIDE | 4.8542 | 1112 | 17.6667 | 2374.8 | 0 | 2 | 3 |  |  |  | 322.3958 | WORKOVER SECTION | 6 | 21 | 5 | #VALUE!
WORKOVER #1 | [5 empty] | 116.5 | 0 | 4.8542 | 1112 | N/D bell nipple. | 14c | 1 | 425 | 2374.8 | 0 | 0.041667 | 17.7083 | 2023-02-04 12:00 | -308.5 | 1900-01-11 20:30 | 2023-02-05 | - | 2.706% | HIDE | 4.8542 | 1112 | 17.7083 | 2374.8 | 0 | 2 | 3 | 3 | WORKOVER SECTION | WORKOVER #1 | 327.25 | WORKOVER SECTION | 6 | 21 | 5 | #VALUE! | WORKOVER SECTION-WORKOVER #1
|  | 26 | Run RST |  | 48 | 164.5 | 2 | 6.8542 | 1112 |  |  |  | 425 | 2374.8 | 0 | 0 | 17.7083 | 2023-02-04 12:00 | -260.5 | 1900-01-09 20:30 | 2023-02-05 | - | - | HIDE | 6.8542 | 1112 | 17.7083 | 2374.8 | 0 | 2 | 4 |  |  |  | 6.8542 | WORKOVER SECTION | 6 | 21 | 5 | #VALUE!
|  | 27 | Perforasi Zona Remedial |  | 6 | 170.5 | 0.25 | 7.1042 | 1112 |  |  |  | 425 | 2374.8 | 0 | 0 | 17.7083 | 2023-02-04 12:00 | -254.5 | 1900-01-09 14:30 | 2023-02-05 | - | - | HIDE | 7.1042 | 1112 | 17.7083 | 2374.8 | 0 | 2 | 4 |  |  |  | 13.9583 | WORKOVER SECTION | 6 | 21 | 5 | #VALUE!
|  | 28 | RIH OE Tbg 2-7/8" for Remedial Cementing |  | 6.5 | 177 | 0.27083 | 7.375 | 1112 |  |  |  | 425 | 2374.8 | 0 | 0 | 17.7083 | 2023-02-04 12:00 | -248 | 1900-01-09 08:00 | 2023-02-05 | - | - | HIDE | 7.375 | 1112 | 17.7083 | 2374.8 | 0 | 2 | 4 |  |  |  | 21.3333 | WORKOVER SECTION | 6 | 21 | 5 | #VALUE!
|  | 29 | Cementing Perbaikan Bonding |  | 6 | 183 | 0.25 | 7.625 | 1112 |  |  |  | 425 | 2374.8 | 0 | 0 | 17.7083 | 2023-02-04 12:00 | -242 | 1900-01-09 02:00 | 2023-02-05 | - | - | HIDE | 7.625 | 1112 | 17.7083 | 2374.8 | 0 | 2 | 4 |  |  |  | 28.9583 | WORKOVER SECTION | 6 | 21 | 5 | #VALUE!
|  | 30 | WOC |  | 8 | 191 | 0.33333 | 7.9583 | 1112 |  |  |  | 425 | 2374.8 | 0 | 0 | 17.7083 | 2023-02-04 12:00 | -234 | 1900-01-08 18:00 | 2023-02-05 | - | - | HIDE | 7.9583 | 1112 | 17.7083 | 2374.8 | 0 | 2 | 4 |  |  |  | 36.9167 | WORKOVER SECTION | 6 | 21 | 5 | #VALUE!
|  | 31 | POOH OE Tbg Cementing to Surface |  | 6 | 197 | 0.25 | 8.2083 | 1112 |  |  |  | 425 | 2374.8 | 0 | 0 | 17.7083 | 2023-02-04 12:00 | -228 | 1900-01-08 12:00 | 2023-02-05 | - | - | HIDE | 8.2083 | 1112 | 17.7083 | 2374.8 | 0 | 2 | 4 |  |  |  | 45.125 | WORKOVER SECTION | 6 | 21 | 5 | #VALUE!
|  | 32 | M/U & RIH DP + TCB 6" to Tag TOC at 890 m |  | 6 | 203 | 0.25 | 8.4583 | 1112 |  |  |  | 425 | 2374.8 | 0 | 0 | 17.7083 | 2023-02-04 12:00 | -222 | 1900-01-08 06:00 | 2023-02-05 | - | - | HIDE | 8.4583 | 1112 | 17.7083 | 2374.8 | 0 | 2 | 4 |  |  |  | 53.5833 | WORKOVER SECTION | 6 | 21 | 5 | #VALUE!
|  | 33 | Drill Cement From 860 to 1041 m (blong). Rate 250 m/day |  | 10 | 213 | 0.41667 | 8.875 | 1112 |  |  |  | 425 | 2374.8 | 0 | 0 | 17.7083 | 2023-02-04 12:00 | -212 | 1900-01-07 20:00 | 2023-02-05 | - | - | HIDE | 8.875 | 1112 | 17.7083 | 2374.8 | 0 | 2 | 4 |  |  |  | 62.4583 | WORKOVER SECTION | 6 | 21 | 5 | #VALUE!
|  | 34 | Circulate Hole Clean |  | 2 | 215 | 0.083333 | 8.9583 | 1112 |  |  |  | 425 | 2374.8 | 0 | 0 | 17.7083 | 2023-02-04 12:00 | -210 | 1900-01-07 18:00 | 2023-02-05 | - | - | HIDE | 8.9583 | 1112 | 17.7083 | 2374.8 | 0 | 2 | 4 |  |  |  | 71.4167 | WORKOVER SECTION | 6 | 21 | 5 | #VALUE!
|  | 35 | Pressure Test |  | 1 | 216 | 0.041667 | 9 | 1112 |  |  |  | 425 | 2374.8 | 0 | 0 | 17.7083 | 2023-02-04 12:00 | -209 | 1900-01-07 17:00 | 2023-02-05 | - | - | HIDE | 9 | 1112 | 17.7083 | 2374.8 | 0 | 2 | 4 |  |  |  | 80.4167 | WORKOVER SECTION | 6 | 21 | 5 | #VALUE!
|  | 36 | POOH TCB 6" to Surface |  | 7 | 223 | 0.29167 | 9.2917 | 1112 |  |  |  | 425 | 2374.8 | 0 | 0 | 17.7083 | 2023-02-04 12:00 | -202 | 1900-01-07 10:00 | 2023-02-05 | - | - | HIDE | 9.2917 | 1112 | 17.7083 | 2374.8 | 0 | 2 | 4 |  |  |  | 89.7083 | WORKOVER SECTION | 6 | 21 | 5 | #VALUE!
|  | 37 | RIH Scraper 7" to 1041 m |  | 7 | 230 | 0.29167 | 9.5833 | 1112 |  |  |  | 425 | 2374.8 | 0 | 0 | 17.7083 | 2023-02-04 12:00 | -195 | 1900-01-07 03:00 | 2023-02-05 | - | - | HIDE | 9.5833 | 1112 | 17.7083 | 2374.8 | 0 | 2 | 4 |  |  |  | 99.2917 | WORKOVER SECTION | 6 | 21 | 5 | #VALUE!
|  | 38 | Sirkulasi |  | 2 | 232 | 0.083333 | 9.6667 | 1112 |  |  |  | 425 | 2374.8 | 0 | 0 | 17.7083 | 2023-02-04 12:00 | -193 | 1900-01-07 01:00 | 2023-02-05 | - | - | HIDE | 9.6667 | 1112 | 17.7083 | 2374.8 | 0 | 2 | 4 |  |  |  | 108.9583 | WORKOVER SECTION | 6 | 21 | 5 | #VALUE!
|  | 39 | POOH Scraper 7" to Surface |  | 7 | 239 | 0.29167 | 9.9583 | 1112 |  |  |  | 425 | 2374.8 | 0 | 0 | 17.7083 | 2023-02-04 12:00 | -186 | 1900-01-06 18:00 | 2023-02-05 | - | - | HIDE | 9.9583 | 1112 | 17.7083 | 2374.8 | 0 | 2 | 4 |  |  |  | 118.9167 | WORKOVER SECTION | 6 | 21 | 5 | #VALUE!
|  | 40 | Rig Up Wireline |  | 2 | 241 | 0.083333 | 10.0417 | 1112 | R/U wireline unit Elnusa. - N/U upper dan lower sheave wheels. - N/U PCE wireline. Pressure test 300 psi/10 menit, baik. - (13:30) Handak dari gudang Field Pendopo tiba di lokasi SPA-034. | 11a | 1.5 | 426.5 | 2374.8 | 0 | 0.0625 | 17.7708 | 2023-02-04 13:30 | -185.5 | 1900-01-06 17:30 | 2023-02-05 | - | 2.696% | HIDE | 10.0417 | 1112 | 17.7708 | 2374.8 | 0 | 2 | 4 |  |  |  | 128.9583 | WORKOVER SECTION | 6 | 21 | 5 | #VALUE!
WORKOVER #2 |  | 41 | Run GR-CBL |  | 6 | 247 | 0.25 | 10.2917 | 1112 |  |  |  | 426.5 | 2374.8 | 0 | 0 | 17.7708 | 2023-02-04 13:30 | -179.5 | 1900-01-06 11:30 | 2023-02-05 | - | - | HIDE | 10.2917 | 1112 | 17.7708 | 2374.8 | 0 | 2 | 4 | 4 | WORKOVER SECTION | WORKOVER #2 | 139.25 | WORKOVER SECTION | 6 | 21 | 5 | #VALUE! | WORKOVER SECTION-WORKOVER #2
|  | 42 | Perforasi Lapisan Produksi |  | 6 | 253 | 0.25 | 10.5417 | 1112 | PJSM. Pekerjaan perforasi lapisan BRF interval 2363-2366 m dengan 3-3/8" HSD 6 SPF. - Loading handak. - Arming casing gun 3-3/8" HSD 6 SPF. - RIH casing gun 3-3/8" HSD 6 SPF. - Korelasi kedalaman interval perforasi, fire. - Cabut casing gun sampai permukaan, all fired (60 ea). | 11a | 2.5 | 429 | 2374.8 | 0 | 0.10417 | 17.875 | 2023-02-04 16:00 | -176 | 1900-01-06 08:00 | 2023-02-05 | - | 2.681% | HIDE | 10.5417 | 1112 | 17.875 | 2374.8 | 0 | 2 | 5 |  |  |  | 10.5417 | WORKOVER SECTION | 6 | 21 | 5 | #VALUE!
[6 empty] | 253 | 0 | 10.5417 | 1112 | Pekerjaan perforasi lapisan BRF interval 2333-2338 m dengan 3-3/8" HSD 6 SPF. - Loading handak. - Arming casing gun 3-3/8" HSD 6 SPF. - RIH casing gun 3-3/8" HSD 6 SPF. - Korelasi kedalaman interval perforasi, fire. - Cabut casing gun sampai permukaan, all fired (99 ea). | 11a | 2 | 431 | 2374.8 | 0 | 0.083333 | 17.9583 | 2023-02-04 18:00 | -178 | 1900-01-06 10:00 | 2023-02-05 | - | 2.668% | HIDE | 10.5417 | 1112 | 17.9583 | 2374.8 | 0 | 2 | 5 |  |  |  | 21.0833 | WORKOVER SECTION | 6 | 21 | 5 | #VALUE!
[6 empty] | 253 | 0 | 10.5417 | 1112 | R/D wireline unit Elnusa. - N/D upper dan lower sheave wheels. - N/D PCE wireline. | 11a | 0.5 | 431.5 | 2374.8 | 0 | 0.020833 | 17.9792 | 2023-02-04 18:30 | -178.5 | 1900-01-06 10:30 | 2023-02-05 | - | 2.665% | HIDE | 10.5417 | 1112 | 17.9792 | 2374.8 | 0 | 2 | 5 |  |  |  | 31.625 | WORKOVER SECTION | 6 | 21 | 5 | #VALUE!
[6 empty] | 253 | 0 | 10.5417 | 1112 | N/U bell nipple. | 14b | 0.5 | 432 | 2374.8 | 0 | 0.020833 | 18 | 2023-02-04 19:00 | -179 | 1900-01-06 11:00 | 2023-02-05 | - | 2.662% | HIDE | 10.5417 | 1112 | 18 | 2374.8 | 0 | 2 | 5 |  |  |  | 42.1667 | WORKOVER SECTION | 6 | 21 | 5 | #VALUE!
[6 empty] | 253 | 0 | 10.5417 | 1112 | Fill up lubang sampai penuh dengan 98 bbl AA 1.01 SG. Flowcheck selama 10 menit, statik loss 1.1 BPM. | 2d | 0.5 | 432.5 | 2374.8 | 0 | 0.020833 | 18.0208 | 2023-02-04 19:30 | -179.5 | 1900-01-06 11:30 | 2023-02-05 | - | 2.659% | HIDE | 10.5417 | 1112 | 18.0208 | 2374.8 | 0 | 2 | 5 |  |  |  | 52.7083 | WORKOVER SECTION | 6 | 21 | 5 | #VALUE!
|  | 43 | RIH RPP Tbg 2-7/8 + Packer 7" to 1142 m |  | 6 | 259 | 0.25 | 10.7917 | 1112 |  |  |  | 432.5 | 2374.8 | 0 | 0 | 18.0208 | 2023-02-04 19:30 | -173.5 | 1900-01-06 05:30 | 2023-02-05 | - | - | HIDE | 10.7917 | 1112 | 18.0208 | 2374.8 | 0 | 2 | 5 |  |  |  | 63.5 | WORKOVER SECTION | 6 | 21 | 5 | #VALUE!
|  | 44 | N/D BOP 7-1/16" x 3000 psi |  | 6 | 265 | 0.25 | 11.0417 | 1112 |  |  |  | 432.5 | 2374.8 | 0 | 0 | 18.0208 | 2023-02-04 19:30 | -167.5 | 1900-01-05 23:30 | 2023-02-05 | - | - | HIDE | 11.0417 | 1112 | 18.0208 | 2374.8 | 0 | 2 | 5 |  |  |  | 74.5417 | WORKOVER SECTION | 6 | 21 | 5 | #VALUE!
|  | 45 | N/U X Mass Tree & Pressure Test |  | 4 | 269 | 0.16667 | 11.2083 | 1112 |  |  |  | 432.5 | 2374.8 | 0 | 0 | 18.0208 | 2023-02-04 19:30 | -163.5 | 1900-01-05 19:30 | 2023-02-05 | - | - | HIDE | 11.2083 | 1112 | 18.0208 | 2374.8 | 0 | 2 | 5 |  |  |  | 85.75 | WORKOVER SECTION | 6 | 21 | 5 | #VALUE!
|  | 46 | Swab dan Test Produksi Lapisan Target |  | 48 | 317 | 2 | 13.2083 | 1112 |  |  |  | 432.5 | 2374.8 | 0 | 0 | 18.0208 | 2023-02-04 19:30 | -115.5 | 1900-01-03 19:30 | 2023-02-05 | - | - | HIDE | 13.2083 | 1112 | 18.0208 | 2374.8 | 0 | 2 | 5 |  |  |  | 98.9583 | WORKOVER SECTION | 6 | 21 | 5 | #VALUE!
|  | 47 | Preparation and Killing well |  | 4 | 321 | 0.16667 | 13.375 | 1112 |  |  |  | 432.5 | 2374.8 | 0 | 0 | 18.0208 | 2023-02-04 19:30 | -111.5 | 1900-01-03 15:30 | 2023-02-05 | - | - | HIDE | 13.375 | 1112 | 18.0208 | 2374.8 | 0 | 2 | 5 |  |  |  | 112.3333 | WORKOVER SECTION | 6 | 21 | 5 | #VALUE!
|  | 48 | Observasi Well |  | 1 | 322 | 0.041667 | 13.4167 | 1112 |  |  |  | 432.5 | 2374.8 | 0 | 0 | 18.0208 | 2023-02-04 19:30 | -110.5 | 1900-01-03 14:30 | 2023-02-05 | - | - | HIDE | 13.4167 | 1112 | 18.0208 | 2374.8 | 0 | 2 | 5 |  |  |  | 125.75 | WORKOVER SECTION | 6 | 21 | 5 | #VALUE!
|  | 49 | N/D X Mass Tree |  | 4 | 326 | 0.16667 | 13.5833 | 1112 |  |  |  | 432.5 | 2374.8 | 0 | 0 | 18.0208 | 2023-02-04 19:30 | -106.5 | 1900-01-03 10:30 | 2023-02-05 | - | - | HIDE | 13.5833 | 1112 | 18.0208 | 2374.8 | 0 | 2 | 5 |  |  |  | 139.3333 | WORKOVER SECTION | 6 | 21 | 5 | #VALUE!
|  | 50 | N/U BOP 7-1/16" x 3000 psi & BOP Test |  | 6 | 332 | 0.25 | 13.8333 | 1112 |  |  |  | 432.5 | 2374.8 | 0 | 0 | 18.0208 | 2023-02-04 19:30 | -100.5 | 1900-01-03 04:30 | 2023-02-05 | - | - | HIDE | 13.8333 | 1112 | 18.0208 | 2374.8 | 0 | 2 | 5 |  |  |  | 153.1667 | WORKOVER SECTION | 6 | 21 | 5 | #VALUE!
|  | 51 | Unset Packer |  | 1 | 333 | 0.041667 | 13.875 | 1112 |  |  |  | 432.5 | 2374.8 | 0 | 0 | 18.0208 | 2023-02-04 19:30 | -99.5 | 1900-01-03 03:30 | 2023-02-05 | - | - | HIDE | 13.875 | 1112 | 18.0208 | 2374.8 | 0 | 2 | 5 |  |  |  | 167.0417 | WORKOVER SECTION | 6 | 21 | 5 | #VALUE!
|  | 52 | Circulation Condition Mud |  | 2 | 335 | 0.083333 | 13.9583 | 1112 |  |  |  | 432.5 | 2374.8 | 0 | 0 | 18.0208 | 2023-02-04 19:30 | -97.5 | 1900-01-03 01:30 | 2023-02-05 | - | - | HIDE | 13.9583 | 1112 | 18.0208 | 2374.8 | 0 | 2 | 5 |  |  |  | 181 | WORKOVER SECTION | 6 | 21 | 5 | #VALUE!
|  | 53 | POOH Production String + Packer 7" to Surface |  | 6 | 341 | 0.25 | 14.2083 | 1112 |  |  |  | 432.5 | 2374.8 | 0 | 0 | 18.0208 | 2023-02-04 19:30 | -91.5 | 1900-01-02 19:30 | 2023-02-05 | - | - | HIDE | 14.2083 | 1112 | 18.0208 | 2374.8 | 0 | 2 | 5 |  |  |  | 195.2083 | WORKOVER SECTION | 6 | 21 | 5 | #VALUE!
|  | 54 | RIH RPP Stimulation |  | 6 | 347 | 0.25 | 14.4583 | 1112 | M/U dan masuk rangkaian stimulasi acidizing (2-3/8" mole shoe + 2 jts 2-3/8" tubing (bekas)) sampai 20.4 m. | 6g | 0.5 | 433 | 2374.8 | 0 | 0.020833 | 18.0417 | 2023-02-04 20:00 | -86 | 1900-01-02 14:00 | 2023-02-05 | - | 2.656% | HIDE | 14.4583 | 1112 | 18.0417 | 2374.8 | 0 | 2 | 5 |  |  |  | 209.6667 | WORKOVER SECTION | 6 | 21 | 5 | #VALUE!
[6 empty] | 347 | 0 | 14.4583 | 1112 | Hujan deras disertai angin (unsafe condition). | 23a | 1 | 434 | 2374.8 | 0 | 0.041667 | 18.0833 | 2023-02-04 21:00 | -87 | 1900-01-02 15:00 | 2023-02-05 | - | 2.65% | HIDE | 14.4583 | 1112 | 18.0833 | 2374.8 | 0 | 2 | 5 |  |  |  | 224.125 | WORKOVER SECTION | 6 | 21 | 5 | #VALUE!
[6 empty] | 347 | 0 | 14.4583 | 1112 | Lanjut masuk rangkaian stimulasi acidizing (2-3/8" mole shoe + 2 jts 2-3/8" tubing (bekas) + 4-1/2" packer SG + 2 ea X/O + 4 jts 3-1/8" DC + X/O + 9 jts 2-3/8" DP + X/O + 31 jts 2-7/8" DP) dari 20.4 m sampai 447.2 m. - Function test packer di permukaan, baik. - Fill up annulus setiap 50 jts. | 6g | 3 | 437 | 2374.8 | 0 | 0.125 | 18.2083 | 2023-02-05 | -90 | 1900-01-02 18:00 | 2023-02-05 | - | 2.632% | HIDE | 14.4583 | 1112 | 18.2083 | 2374.8 | 0 | 2 | 5 |  |  |  | 238.5833 | WORKOVER SECTION | 6 | 21 | 5 | #VALUE!
[6 empty] | 347 | 0 | 14.4583 | 1112 | Lanjut masuk rangkaian stimulasi acidizing (2-3/8" mole shoe + 2 jts 2-3/8" tubing (bekas) + 4-1/2" packer SG + 2 ea X/O + 4 jts 3-1/8" DC + X/O + 9 jts 2-3/8" DP + X/O + 170 jts 2-7/8" DP + 2 ea 2-7/8" pup joint + X/O + 58 jts 3-1/2" DP) dari 447.2 m sampai 2349.9 m. - Fill up annulus setiap 50 jts. | 6g | 6 | 443 | 2374.8 | 0 | 0.25 | 18.4583 | 2023-02-05 06:00 | -96 | 1900-01-03 | 2023-02-06 | - | 2.596% | HIDE | 14.4583 | 1112 | 18.4583 | 2374.8 | 0 | 2 | 5 |  |  |  | 253.0417 | WORKOVER SECTION | 6 | 21 | 5 | #VALUE!
|  | 55 | Stimulation Job (Acid Solvent) |  | 24 | 371 | 1 | 15.4583 | 1112 | Mixing 97 bbl brine water dan 5 bbl 15% HCl pickle. | 27a | 5.5 | 448.5 | 2374.8 | 0 | 0.22917 | 18.6875 | 2023-02-05 11:30 | -77.5 | 1900-01-02 05:30 | 2023-02-06 | - | 2.564% | HIDE | 15.4583 | 1112 | 18.6875 | 2374.8 | 0 | 2 | 5 |  |  |  | 268.5 | WORKOVER SECTION | 6 | 21 | 5 | #VALUE!
[6 empty] | 371 | 0 | 15.4583 | 1112 | R/U cementing line dan plug valve cementing. - Pressure test cementing line 2000 psi/5 menit, baik. | 27a | 0.5 | 449 | 2374.8 | 0 | 0.020833 | 18.7083 | 2023-02-05 12:00 | -78 | 1900-01-02 06:00 | 2023-02-06 | - | 2.561% | HIDE | 15.4583 | 1112 | 18.7083 | 2374.8 | 0 | 2 | 5 |  |  |  | 283.9583 | WORKOVER SECTION | 6 | 21 | 5 | #VALUE!
[6 empty] | 371 | 0 | 15.4583 | 1112 | PJSM. Pekerjaan pickle string. - Pompakan 5 bbls 15% HCL. - Displace string dengan 37 bbl AA 1.01 SG, rate 1-2 BPM/10-20 psi. - Tutup annular dan pipe ram BOP. - Reverse out dengan 390 bbl AA 1.01 SG, rate 6 BPM, tidak ada return. - Buka annular dan pipe ram BOP. - Displace string dengan 10 bbl AA 1.01 SG, rate 2 BPM/20-60 psi. - R/D cementing line. | 27a | 2 | 451 | 2374.8 | 0 | 0.083333 | 18.7917 | 2023-02-05 14:00 | -80 | 1900-01-02 08:00 | 2023-02-06 | - | 2.55% | HIDE | 15.4583 | 1112 | 18.7917 | 2374.8 | 0 | 2 | 5 |  |  |  | 299.4167 | WORKOVER SECTION | 6 | 21 | 5 | #VALUE!
[6 empty] | 371 | 0 | 15.4583 | 1112 | Set 4-1/2" packer SG di 2327.9 m, UR di 2349.9 m. - Angkat rangkaian 20 cm, putar kiri 4x, dudukan rangkaian 12 klbs. | 6g | 0.5 | 451.5 | 2374.8 | 0 | 0.020833 | 18.8125 | 2023-02-05 14:30 | -80.5 | 1900-01-02 08:30 | 2023-02-06 | - | 2.547% | HIDE | 15.4583 | 1112 | 18.8125 | 2374.8 | 0 | 2 | 5 |  |  |  | 314.875 | WORKOVER SECTION | 6 | 21 | 5 | #VALUE!
[6 empty] | 371 | 0 | 15.4583 | 1112 | IRT dengan AA 1.01 SG. - Fill up string dengan 35 bbl AA 1.01 SG dengan rate 3 BPM, pressure 30-500 psi. Pressure sempat naik sampai 500 psi saat pemompaan 18 bbl, cek tekanan annulus tidak ada kenaikan pressure, indikasi pressure set sempurna. Turunkan rate menjadi 2 BPM, pressure langsung turun menjadi 30 psi. - Tutup annular dan pipe ram BOP. - IRT dengan 12 bbls AA 1.01 SG, naikan rate bertahap 0.25-1 BPM, pressure 0-45 psi. - Stop pompa, tekanan langsung turun menjadi 0 psi. - Ablas tekanan, tidak ada aliran balik. | 27a | 0.5 | 452 | 2374.8 | 0 | 0.020833 | 18.8333 | 2023-02-05 15:00 | -81 | 1900-01-02 09:00 | 2023-02-06 | - | 2.544% | HIDE | 15.4583 | 1112 | 18.8333 | 2374.8 | 0 | 2 | 5 |  |  |  | 330.3333 | WORKOVER SECTION | 6 | 21 | 5 | #VALUE!
[6 empty] | 371 | 0 | 15.4583 | 1112 | Mixing 78 bbl 15% HCl acid. | 27a | 1 | 453 | 2374.8 | 0 | 0.041667 | 18.875 | 2023-02-05 16:00 | -82 | 1900-01-02 10:00 | 2023-02-06 | - | 2.539% | HIDE | 15.4583 | 1112 | 18.875 | 2374.8 | 0 | 2 | 5 |  |  |  | 345.7917 | WORKOVER SECTION | 6 | 21 | 5 | #VALUE!
[6 empty] | 371 | 0 | 15.4583 | 1112 | Pekerjaan stimulasi acidizing. - Pompakan 78 bbl 15% HCl acid dengan rate 2-3 BPM, pressure 0-310 psi. - Over flush 21 bbl brine water dengan rate 2-2.5 BPM, pressure 0-20 psi. - Displace 45 bbl brine water dengan rate 2.5-3 BPM, pressure 0-350 psi. - Tutup plug valve cementing. | 27a | 1 | 454 | 2374.8 | 0 | 0.041667 | 18.9167 | 2023-02-05 17:00 | -83 | 1900-01-02 11:00 | 2023-02-06 | - | 2.533% | HIDE | 15.4583 | 1112 | 18.9167 | 2374.8 | 0 | 2 | 5 |  |  |  | 361.25 | WORKOVER SECTION | 6 | 21 | 5 | #VALUE!
[6 empty] | 371 | 0 | 15.4583 | 1112 | Rendam 78 bbl 15% HCl acid di formasi. | 27a | 1 | 455 | 2374.8 | 0 | 0.041667 | 18.9583 | 2023-02-05 18:00 | -84 | 1900-01-02 12:00 | 2023-02-06 | - | 2.527% | HIDE | 15.4583 | 1112 | 18.9583 | 2374.8 | 0 | 2 | 5 |  |  |  | 376.7083 | WORKOVER SECTION | 6 | 21 | 5 | #VALUE!
|  | 56 | Preparation and Killing Well |  | 4 | 375 | 0.16667 | 15.625 | 1112 |  |  |  | 455 | 2374.8 | 0 | 0 | 18.9583 | 2023-02-05 18:00 | -80 | 1900-01-02 08:00 | 2023-02-06 | - | - | HIDE | 15.625 | 1112 | 18.9583 | 2374.8 | 0 | 2 | 5 |  |  |  | 392.3333 | WORKOVER SECTION | 6 | 21 | 5 | #VALUE!
|  | 57 | Observasi Well |  | 1 | 376 | 0.041667 | 15.6667 | 1112 |  |  |  | 455 | 2374.8 | 0 | 0 | 18.9583 | 2023-02-05 18:00 | -79 | 1900-01-02 07:00 | 2023-02-06 | - | - | HIDE | 15.6667 | 1112 | 18.9583 | 2374.8 | 0 | 2 | 5 |  |  |  | 408 | WORKOVER SECTION | 6 | 21 | 5 | #VALUE!
|  | 58 | N/D X Mass Tree |  | 4 | 380 | 0.16667 | 15.8333 | 1112 |  |  |  | 455 | 2374.8 | 0 | 0 | 18.9583 | 2023-02-05 18:00 | -75 | 1900-01-02 03:00 | 2023-02-06 | - | - | HIDE | 15.8333 | 1112 | 18.9583 | 2374.8 | 0 | 2 | 5 |  |  |  | 423.8333 | WORKOVER SECTION | 6 | 21 | 5 | #VALUE!
|  | 59 | N/U BOP 7-1/16" x 3000 psi & BOP Test |  | 6 | 386 | 0.25 | 16.0833 | 1112 |  |  |  | 455 | 2374.8 | 0 | 0 | 18.9583 | 2023-02-05 18:00 | -69 | 1900-01-01 21:00 | 2023-02-06 | - | - | HIDE | 16.0833 | 1112 | 18.9583 | 2374.8 | 0 | 2 | 5 |  |  |  | 439.9167 | WORKOVER SECTION | 6 | 21 | 5 | #VALUE!
|  | 60 | Unset Packer |  | 1 | 387 | 0.041667 | 16.125 | 1112 | Unset 4-1/2" packer SG. - Buka plug valve cementing. Buka annular dan pipe ram BOP. - Angkat rangkaian 2 m (P/U : 81 klbs), turunkan rangkaian 3 m (S/O : 76 klbs), packer unset. | 6g | 1 | 456 | 2374.8 | 0 | 0.041667 | 19 | 2023-02-05 19:00 | -69 | 1900-01-01 21:00 | 2023-02-06 | - | 2.522% | HIDE | 16.125 | 1112 | 19 | 2374.8 | 0 | 2 | 5 |  |  |  | 456.0417 | WORKOVER SECTION | 6 | 21 | 5 | #VALUE!
|  | 61 | Circulation Condition Mud |  | 2 | 389 | 0.083333 | 16.2083 | 1112 | Fill up 1x volume string, tidak ada return. | 5a | 0.5 | 456.5 | 2374.8 | 0 | 0.020833 | 19.0208 | 2023-02-05 19:30 | -67.5 | 1900-01-01 19:30 | 2023-02-06 | - | 2.519% | HIDE | 16.2083 | 1112 | 19.0208 | 2374.8 | 0 | 2 | 5 |  |  |  | 472.25 | WORKOVER SECTION | 6 | 21 | 5 | #VALUE!
|  | 62 | POOH Production String + Packer 7" to Surface |  | 6 | 395 | 0.25 | 16.4583 | 1112 | Cabut L/D rangkaian stimulasi acidizing dari 2349.9 m sampai 1682.52 m. - Fill up annulus dengan 10 bbl AA 1.01 SG setiap 1.5 jam, tidak ada return. - L/D 58 jts 3-1/2" DP, 2 ea 2-7/8" pup joint dan 11 jts 2-7/8" DP. | 6g | 4.5 | 461 | 2374.8 | 0 | 0.1875 | 19.2083 | 2023-02-06 | -66 | 1900-01-01 18:00 | 2023-02-06 | - | 2.495% | HIDE | 16.4583 | 1112 | 19.2083 | 2374.8 | 0 | 2 | 5 |  |  |  | 488.7083 | WORKOVER SECTION | 6 | 21 | 5 | #VALUE!
[6 empty] | 395 | 0 | 16.4583 | 1112 | Lanjut cabut L/D rangkaian stimulasi acidizing dari 1682.52 m sampai permukaan. - Fill up annulus dengan 10 bbl AA 1.01 SG setiap 1.5 jam, tidak ada return. - L/D 159 jts 2-7/8" DP, kumm 170 jts 2-7/8" DP. - L/D 9 jts 2-3/8" DP - L/D 4 jts 3-1/8" DC - L/D 2-3/8" mole shoe + 2 jts 2-3/8" tubing (bekas) + 4-1/2" packer SG | 6g | 13 | 474 | 2374.8 | 0 | 0.54167 | 19.75 | 2023-02-06 13:00 | -79 | 1900-01-02 07:00 | 2023-02-07 | - | 2.426% | HIDE | 16.4583 | 1112 | 19.75 | 2374.8 | 0 | 2 | 5 |  |  |  | 505.1667 | WORKOVER SECTION | 6 | 21 | 5 | #VALUE!
[6 empty] | 395 | 0 | 16.4583 | 1112 | Persiapan masuk RPP ESP WESPI. - Loading unloading 91 jts 2-7/8" Drill pipe + 9 jts 2-3/8" DP +4 jts DC 3-1/8" + 2 jts 2-3/8" tubing dari pipe rack set Rig, ke pipe box. - Loading unloading 70 jts 2-7/8" Tubing (Dari storage pipe rack ke Pipe rack Rig set) menggunakan crane. - Ganti pipe ram 3-1/2" ke 2-7/8". - Ganti link elevator. - Susun, tally dan bersihkan drat pin/box tubing 2-7/8". - PJSM bersama membahas program kerja, keselamatan kerja & mitigasi resiko bahaya pekerjaan masuk RPP ESP. - Set roller kabel ke kabel spooler. - Pasang clamp motor, pump, gas separator dan protector. - Tally dan catat serial number ESP. - Megger motor ~ P.P : 0.5 Ohm. ~ P.G : 2000 M.Ohm (balance) - Megger Cable PG : 2000 M.Ohm - Naikan peralatan kerja ESP WESPI ke meja floor. | 26b | 3 | 477 | 2374.8 | 0 | 0.125 | 19.875 | 2023-02-06 16:00 | -82 | 1900-01-02 10:00 | 2023-02-07 | - | 2.411% | HIDE | 16.4583 | 1112 | 19.875 | 2374.8 | 0 | 2 | 5 |  |  |  | 521.625 | WORKOVER SECTION | 6 | 21 | 5 | #VALUE!
[6 empty] | 395 | 0 | 16.4583 | 1112 | M/U dan Install rangkaian ESP WESPI. Dengan rincian: - Centralizer - Motor 80 HP. 1160 V. 45 A UT 540 S S/N : 1 CW 04 U Y 1B12D2202 - Flushing oli ke motor sampai penuh. - Lower protector 66 L 540 S S/N : 3 CW 1 ZN. Y 2B14B 7611 - Upper protector PFDB 540 S S/N : 3 C 01 V - 3110076 - Gas separator KGS 400 S S/N : 4 BW 11 T 21100 45 - PUMP LT. TD 750. 133 STG 400 S. S/N : 2 BW 125 Y 5 D 12 D 0377 - Pump UT . TD 750. 212 STG 400 S. S/N : 2 BW 09 U. 10005 + pump head /BOH | 26b | 5 | 482 | 2374.8 | 0 | 0.20833 | 20.0833 | 2023-02-06 21:00 | -87 | 1900-01-02 15:00 | 2023-02-07 | - | 2.386% | HIDE | 16.4583 | 1112 | 20.0833 | 2374.8 | 0 | 2 | 5 |  |  |  | 538.0833 | WORKOVER SECTION | 6 | 21 | 5 | #VALUE!
WORKOVER #3 | [5 empty] | 395 | 0 | 16.4583 | 1112 | Splicing Cable ke motor , check reading cable motor d ground. * PP : 0.5 Ohm * PG : 2000 M.ohm (balance). - Megger cable setelah di install ke motor * PP : 3.3 Ohm. * PG : 2000 M.ohm (balance). - Flushing oli dari motor sampai pump UT, ok. | 26b | 3 | 485 | 2374.8 | 0 | 0.125 | 20.2083 | 2023-02-07 | -90 | 1900-01-02 18:00 | 2023-02-07 | - | 2.371% | HIDE | 16.4583 | 1112 | 20.2083 | 2374.8 | 0 | 2 | 5 | 5 | WORKOVER SECTION | WORKOVER #3 | 554.5417 | WORKOVER SECTION | 6 | 21 | 5 | #VALUE! | WORKOVER SECTION-WORKOVER #3
|  | 63 | RIH RPP Tbg 2-7/8 + Packer 7" to 1700 m |  | 6 | 401 | 0.25 | 16.7083 | 1112 | Masuk joint per joint RPP + ESP WESPI sampai kedalaman 1189 m. Dengan rincian: - Centralizer + Motor 80 HP + Lower protector 66 L + Upper protector PFDB + Gas Separator + Lower pump + Upper pump + Pump head / BOH + 3 jts 2-7/8" tubing + Check valve + 1 jts 2-7/8" tubing + Bleeder valve + 1 jts 2-7/8" tubing. - P/T 1 jts di atas bleeder valve 500 psi/5 menit. baik. - Pasang Capilary tube 3 meter di atas bleeder valve. - Rabbit semua 2-7/8" tubing yang masuk. - P/T 2-7/8" tubing 500 psi setiap penambahan 20 jts tubing. - F/U AA ke tubing pakai filter agar kotoran tidak masuk. - Pasang 1 ea cable protector dan 1 ea cable band setiap joint. - Masuk perlahan hindari jepitan pada kabel. - Total tubing 2-7/8" yang masuk 104 jts. - Megger test cable per 20 jts: Depht P-P P-G (mMD) (Ohm) (MOhm) 246.05 3.3 1700 434.46 3.4 1500 623.31 3.4 1200 1000.9 3.5 600 1189 3.6 400 Aksesoris ESP WESPI - Cable guard : 7 ea - Cable band : 122 ea - Cable protector :100 ea | 26b | 17 | 502 | 2374.8 | 0 | 0.70833 | 20.9167 | 2023-02-07 17:00 | -101 | 1900-01-03 05:00 | 2023-02-08 | - | 2.291% | HIDE | 16.7083 | 1112 | 20.9167 | 2374.8 | 0 | 2 | 6 |  |  |  | 16.7083 | WORKOVER SECTION | 6 | 21 | 5 | #VALUE!
[6 empty] | 401 | 0 | 16.7083 | 1112 | Hujan deras di sertai angin kencang (unsafe condition). | 23a | 1 | 503 | 2374.8 | 0 | 0.041667 | 20.9583 | 2023-02-07 18:00 | -102 | 1900-01-03 06:00 | 2023-02-08 | - | 2.286% | HIDE | 16.7083 | 1112 | 20.9583 | 2374.8 | 0 | 2 | 6 |  |  |  | 33.4167 | WORKOVER SECTION | 6 | 21 | 5 | #VALUE!
[6 empty] | 401 | 0 | 16.7083 | 1112 | Lanjut Masuk joint per joint RPP + ESP WESPI dari 1189 m sampai kedalaman 1564.38 m. - Rabbit semua 2-7/8" tubing yang masuk. - P/T 2-7/8" tubing 500 psi setiap penambahan 20 jts tubing. - F/U AA ke tubing pakai filter agar kotoran tidak masuk. - Pasang 1 ea cable protector dan 1 ea cable band setiap joint. - Masuk perlahan hindari jepitan pada kabel. - Total tubing 2-7/8" yang masuk 164 jts. - Megger test cable per 20 jts: Depht P-P P-G (mMD) (Ohm) (MOhm) 1375.96 3.7 200 1564.38 3.8 50 | 26b | 6 | 509 | 2374.8 | 0 | 0.25 | 21.2083 | 2023-02-08 | -108 | 1900-01-03 12:00 | 2023-02-08 | - | 2.259% | HIDE | 16.7083 | 1112 | 21.2083 | 2374.8 | 0 | 2 | 6 |  |  |  | 50.125 | WORKOVER SECTION | 6 | 21 | 5 | #VALUE!
[6 empty] | 401 | 0 | 16.7083 | 1112 | Lanjut Masuk joint per joint RPP + ESP WESPI dari 1564.38 m sampai kedalaman 1804.59 m, Set KI di kedalaman 1796 m. - Rabbit semua 2-7/8" tubing yang masuk. - P/T 2-7/8" tubing 500 psi setiap penambahan 20 jts tubing. - F/U AA ke tubing pakai filter agar kotoran tidak masuk. - Pasang 1 ea cable protector dan 1 ea cable band setiap joint. - Masuk perlahan hindari jepitan pada kabel. - Total tubing 2-7/8" yang masuk 188 jts + 1 jt Tbg 3-1/2". - Set Capilary tube di 1745.71 m dan sambung 2 titik capilary tube yang bocor. - Megger test cable per 20 jts: Depht P-P P-G (mMD) (Ohm) (MOhm) 1788.46 4.1 20 Aksesoris ESP WESPI - Cable guard : 7 ea - Cable band : 259 ea - Cable protector : 167 ea - Cable sambungan: 4 | 26b | 2 | 511 | 2374.8 | 0 | 0.083333 | 21.2917 | 2023-02-08 02:00 | -110 | 1900-01-03 14:00 | 2023-02-09 | - | 2.25% | HIDE | 16.7083 | 1112 | 21.2917 | 2374.8 | 0 | 2 | 6 |  |  |  | 66.8333 | WORKOVER SECTION | 6 | 21 | 5 | #VALUE!
|  | 64 | N/D BOP 7-1/16" x 3000 psi |  | 6 | 407 | 0.25 | 16.9583 | 1112 | N/D BOP Group 7-1/16" x 5000 psi + DSAF 7-1/16" x 3000 psi. - N/U 7" hanger temporary dan landing joint. - N/D bell nipple + flow line. | 14c | 2 | 513 | 2374.8 | 0 | 0.083333 | 21.375 | 2023-02-08 04:00 | -106 | 1900-01-03 10:00 | 2023-02-09 | - | 2.242% | HIDE | 16.9583 | 1112 | 21.375 | 2374.8 | 0 | 2 | 6 |  |  |  | 83.7917 | WORKOVER SECTION | 6 | 21 | 5 | #VALUE!
|  | 65 | Masuk RBI |  | 8 | 415 | 0.33333 | 17.2917 | 1112 |  |  |  | 513 | 2374.8 | 0 | 0 | 21.375 | 2023-02-08 04:00 | -98 | 1900-01-03 02:00 | 2023-02-09 | - | - | HIDE | 17.2917 | 1112 | 21.375 | 2374.8 | 0 | 2 | 6 |  |  |  | 101.0833 | WORKOVER SECTION | 6 | 21 | 5 | #VALUE!
|  | 66 | N/U SRP Wellhead & Production Line |  | 10 | 425 | 0.41667 | 17.7083 | 1112 | N/U ESP wellhead hercules 7-1/16" x 3000 psi + master valve 3-1/8" x 3000 psi. - N/D landing joint.2-7/8" tbg. | 14a | 3 | 516 | 2374.8 | 0 | 0.125 | 21.5 | 2023-02-08 07:00 | -91 | 1900-01-02 19:00 | 2023-02-09 | - | 2.229% | HIDE | 17.7083 | 1112 | 21.5 | 2374.8 | 0 | 2 | 6 |  |  |  | 118.7917 | WORKOVER SECTION | 6 | 21 | 5 | #VALUE!
[6 empty] | 425 | 0 | 17.7083 | 1112 | Persiapan Geser substructure. - Turunkan peralatan kerja dan masukan ke dalam tool box. - Loading unloding 75 jts 2-7/8" tubing. - Loading unloding unit BAKER. | 29a | 6 | 522 | 2374.8 | 0 | 0.25 | 21.75 | 2023-02-08 13:00 | -97 | 1900-01-03 01:00 | 2023-02-09 | - | 2.203% | HIDE | 17.7083 | 1112 | 21.75 | 2374.8 | 0 | 2 | 6 |  |  |  | 136.5 | WORKOVER SECTION | 6 | 21 | 5 | #VALUE!
[6 empty] | 425 | 0 | 17.7083 | 1112 | Geser substructure 1 dan 2. - Geser Accumulator unit. - Geser Compressor portabel. - Turukan 3 ea tangga substructure + V-door. | 29a | 3 | 525 | 2374.8 | 0 | 0.125 | 21.875 | 2023-02-08 16:00 | -100 | 1900-01-03 04:00 | 2023-02-09 | - | 2.19% | HIDE | 17.7083 | 1112 | 21.875 | 2374.8 | 0 | 2 | 6 |  |  |  | 154.2083 | WORKOVER SECTION | 6 | 21 | 5 | #VALUE!
[6 empty] | 425 | 0 | 17.7083 | 1112 | N/U surface line 4" dan 2" casing line. - Install ESP cable ke junction box. | 29a | 1 | 526 | 2374.8 | 0 | 0.041667 | 21.9167 | 2023-02-08 17:00 | -101 | 1900-01-03 05:00 | 2023-02-09 | - | 2.186% | HIDE | 17.7083 | 1112 | 21.9167 | 2374.8 | 0 | 2 | 6 |  |  |  | 171.9167 | WORKOVER SECTION | 6 | 21 | 5 | #VALUE!
|  | 67 | Production Test and Put Well On Production |  | 24 | 449 | 1 | 18.7083 | 1112 | Uji produksi lapisan BRF 2333-2338 m dan 2363-2366 m, alirkan ke SP-SOPA. - Sonolog Static SFL : 545.91m - Start up ESP pukul 17.10 wib - Parameter ESP Freq : 38 HZ MC : 75 A MV : 405 V ADH : 22.22.21 TP : 80 psi - Pukul 17.30 wib cairan keluar sampai di SP- SOPA. - Uji produksi Waktu/Gross/Nett/WC/TP/Rate 17.30- 20.30/ 360 BFPD/ - BOPD/100%/80 psi/15 bbl per jam. - Cairan terproduksi. | 29a | 7 | 533 | 2374.8 | 0 | 0.29167 | 22.2083 | 2023-02-09 | -84 | 1900-01-02 12:00 | 2023-02-09 | - | 2.158% | HIDE | 18.7083 | 1112 | 22.2083 | 2374.8 | 0 | 2 | 6 |  |  |  | 190.625 | WORKOVER SECTION | 6 | 21 | 5 | #VALUE!
[6 empty] | 449 | 0 | 18.7083 | 1112 | Lanjut Uji produksi lapisan BRF 2333-2338 m dan 2363-2366 m, alirkan ke SP- SOPA. - Hasil test produksi sumur SPA - 034 Pukul 00.00 - 03.00 WIB ( 86 Bbl / 3 Jam) : - Rate : 28.66 bbl /3 jam - Gross : 688 bbl. - Net : 0 - WC : 100 %. - TP : 90 psi . - Frek : 38 Hz . - Dynamic Sonolog, Pukul 08.40 WIB : - DFL : 859.55 m. Hasil test produksi sumur SPA - 034 Pukul 10.00 - 14.00 WIB ( 80 Bbl / 4 Jam) : - Rate : 20 bbl/1 jam - Gross : 480 bbl. - Net : 0 - WC : 100 %. - TP : 90 psi . - Frek : 38 Hz. Rig GJE-11 dinyatakan release dari pekerjaan sumur SPA-034 TMT 09 Februari 2023 pukul 18:00 WIB, selanjutnya sumur SPA-034 dinyatakan sebagai sumur pengamatan produksi dari lapisan BRF interval 2363-2366 m dan 2333-2338 m. | 29a | 18 | 551 | 2374.8 | 0 | 0.75 | 22.9583 | 2023-02-09 18:00 | -102 | 1900-01-03 06:00 | 2023-02-10 | - | 2.087% | HIDE | 18.7083 | 1112 | 22.9583 | 2374.8 | 0 | 2 | 6 |  |  |  | 209.3333 | WORKOVER SECTION | 6 | 21 | 5 | #VALUE!
WORKOVER #4 | 2 | WORKOVER SECTION |  |  | 449 | 449 | 18.7083 | 18.7083 | 1112 |  |  | 551 | 551 | 2374.8 |  | 22.9583 | 22.9583 | 2023-02-09 18:00 | -102 | 1900-01-03 06:00 | 2023-02-10 | ---------------------- | ---------------------- | HIDE | 18.7083 | 1112 | 22.9583 | 2374.8 | 0 | 2 | 6 | 6 | WORKOVER SECTION | WORKOVER #4 | 228.0417 | WORKOVER SECTION | 6 | 21 | 5 | #VALUE! | WORKOVER SECTION-WORKOVER #4
|  | 68 | Rig Release |  | 0 | 0 | 0 | 18.7083 | 1112 |  |  |  | 0 |  | 0 | 0 | 22.9583 | 2023-02-09 18:00 |  |  | 2023-02-10 | - | - | HIDE | 18.7083 | 1112 | 22.9583 | 2374.8 |  | 3 | 7 |  |  |  | 18.7083 | RELEASE | 13 | 31 | 1 | Rig Release
Rig Release | 3 | RELEASE |  |  | 0 | 0 | 0 | 18.7083 | 1112 |  |  | 0 | 0 | 2374.8 |  | 0 | 22.9583 | 2023-02-09 18:00 |  |  | 2023-02-10 | ---------------------- | ---------------------- | HIDE | 18.7083 | 1112 | 22.9583 | 2374.8 |  | 3 | 7 | 7 | RELEASE | Rig Release | 37.4167 | RELEASE | 13 | 31 | 1 | Rig Release | RELEASE-Rig Release
|  | 68 |  |  | 449 | 449 | 18.7083 | 18.7083 | 1112
122.7171
[11 empty] | 22.9583 | 4.25
Formulas:
DATE & DAY = IF([NO. SECTION]=1,MAX(INDIRECT(ADDRESS(9,COLUMN(U8),,,)):INDIRECT(ADDRESS(ROW()-1,COLUMN(U8),,,))),MAX(INDIRECT(ADDRESS(MATCH([NO. SECTION]-1,B1:[NO. SECTION, row above],0)+1,COLUMN(U8),,,)):INDIRECT(ADDRESS(ROW()-1,COLUMN(U8),,,))))
DATE & DAY = [CUM DAYS]+'1_INPUT'!$E18
DAILY NPT (%) = IF([NO. SECTION]=1,MAX(INDIRECT(ADDRESS(9,COLUMN(X8),,,)):INDIRECT(ADDRESS(ROW()-1,COLUMN(X8),,,))),MAX(INDIRECT(ADDRESS(MATCH([NO. SECTION]-1,B1:[NO. SECTION, row above],0),COLUMN(X8),,,)):INDIRECT(ADDRESS(ROW()-1,COLUMN(X8),,,))))
DAILY NPT (%) = IF([DATE & DAY]=0,"-",ROUNDUP(VALUE([DATE & DAY]),0))
DD:HH:MM = IFERROR(IF([GAIN / LOSS]>0,TIME([GAIN / LOSS],([GAIN / LOSS]-ROUNDDOWN([GAIN / LOSS],0))*60,0)+DAY((ROUNDDOWN([GAIN / LOSS],0)/24)),TIME((-[GAIN / LOSS]),((-[GAIN / LOSS])-ROUNDDOWN((-[GAIN / LOSS]),0))*60,0)+DAY((ROUNDDOWN((-[GAIN / LOSS]),0)/24))),"")

## 4_CHART
HIDE
WORKOVER TIME CHART WELL SPA-034
| ROW of INT | PLAN |  | ACTUAL
|  | SHOE | TOL | SHOE | TOL | CASING DESIGN | [15 empty] | FORMATION
[7 empty] | 0 | 0 | 4.5 | 7 | 9.625 | 13.375 | 20 | 0 | 0 | 4.5 | 7 | 9.625 | 13.375 | 20
| 68.5 | - | - | 20 | - |  | #N/A | #N/A | 0 | 0 | 0 | 0 | 0 | #N/A | #N/A | 0 | 0 | 1 | 1 | 2 | 20'' at 99 m |  | PASTE (AND SNAP TO GRID) YOUR LITHOLOGY SCHEME HERE
| 137 | - | - | - | - |  | #N/A | #N/A | 0 | 0 | 0 | 0 | 0 | #N/A | #N/A | 0 | 0 | 1 | 1 | 0
| 205.5 | - | - | - | - |  | #N/A | #N/A | 0 | 0 | 0 | 0 | 0 | #N/A | #N/A | 0 | 0 | 1 | 1 | 0
| 274 | - | - | - | - |  | #N/A | #N/A | 0 | 0 | 0 | 0 | 0 | #N/A | #N/A | 0 | 0 | 1 | 1 | 0
| 342.5 | - | - | - | - |  | #N/A | #N/A | 0 | 0 | 0 | 0 | 0 | #N/A | #N/A | 0 | 0 | 1 | 1 | 0
| 411 | - | - | - | - |  | #N/A | #N/A | 0 | 0 | 0 | 0 | 0 | #N/A | #N/A | 0 | 0 | 1 | 1 | 0
| 479.5 | - | - | - | - |  | #N/A | #N/A | 0 | 0 | 0 | 0 | 0 | #N/A | #N/A | 0 | 0 | 1 | 1 | 0
| 548 | - | - | - | - |  | #N/A | #N/A | 0 | 0 | 0 | 0 | 0 | #N/A | #N/A | 0 | 0 | 1 | 1 | 0
| 616.5 | - | - | - | - |  | #N/A | #N/A | 0 | 0 | 0 | 0 | 0 | #N/A | #N/A | 0 | 0 | 1 | 1 | 0
| 685 | - | - | 13.375 | - |  | #N/A | #N/A | 0 | 0 | 0 | 0 | 0 | #N/A | #N/A | 0 | 0 | 1 | 2 | 0 | 13 3/8'' at 699 m
| 753.5 | - | - | - | - |  | #N/A | #N/A | 0 | 0 | 0 | 0 | 0 | #N/A | #N/A | 0 | 0 | 1 | 0 | 0
| 822 | - | - | - | - |  | #N/A | #N/A | 0 | 0 | 0 | 0 | 0 | #N/A | #N/A | 0 | 0 | 1 | 0 | 0
| 890.5 | - | - | - | - |  | #N/A | #N/A | 0 | 0 | 0 | 0 | 0 | #N/A | #N/A | 0 | 0 | 1 | 0 | 0
| 959 | - | - | - | - |  | #N/A | #N/A | 0 | 0 | 0 | 0 | 0 | #N/A | #N/A | 0 | 0 | 1 | 0 | 0
| 1027.5 | - | - | - | - |  | #N/A | #N/A | 0 | 0 | 0 | 0 | 0 | #N/A | #N/A | 0 | 0 | 1 | 0 | 0
| 1096 | - | - | - | - |  | #N/A | #N/A | 0 | 0 | 0 | 0 | 0 | #N/A | #N/A | 0 | 0 | 1 | 0 | 0
| 1164.5 | - | - | - | - |  | #N/A | #N/A | 0 | 0 | 0 | 0 | 0 | #N/A | #N/A | 0 | 0 | 1 | 0 | 0
| 1233 | - | - | - | - |  | #N/A | #N/A | 0 | 0 | 0 | 0 | 0 | #N/A | #N/A | 0 | 0 | 1 | 0 | 0
| 1301.5 | - | - | - | - |  | #N/A | #N/A | 0 | 0 | 0 | 0 | 0 | #N/A | #N/A | 0 | 0 | 1 | 0 | 0
| 1370 | - | - | - | - |  | #N/A | #N/A | 0 | 0 | 0 | 0 | 0 | #N/A | #N/A | 0 | 0 | 1 | 0 | 0
| 1438.5 | - | - | - | 7 |  | #N/A | #N/A | 0 | 0 | 0 | 0 | 0 | #N/A | #N/A | 0 | 3 | 1 | 0 | 0 | TOL 7'' at 1433 m
| 1507 | - | - | 9.625 | - |  | #N/A | #N/A | 0 | 0 | 0 | 0 | 0 | #N/A | #N/A | 0 | 1 | 2 | 0 | 0 | 9 5/8'' at 1495 m
| 1575.5 | - | - | - | - |  | #N/A | #N/A | 0 | 0 | 0 | 0 | 0 | #N/A | #N/A | 0 | 1 | 0 | 0 | 0
| 1644 | - | - | - | - |  | #N/A | #N/A | 0 | 0 | 0 | 0 | 0 | #N/A | #N/A | 0 | 1 | 0 | 0 | 0
| 1712.5 | - | - | - | - |  | #N/A | #N/A | 0 | 0 | 0 | 0 | 0 | #N/A | #N/A | 0 | 1 | 0 | 0 | 0
| 1781 | - | - | - | - |  | #N/A | #N/A | 0 | 0 | 0 | 0 | 0 | #N/A | #N/A | 0 | 1 | 0 | 0 | 0
| 1849.5 | - | - | - | - |  | #N/A | #N/A | 0 | 0 | 0 | 0 | 0 | #N/A | #N/A | 0 | 1 | 0 | 0 | 0
| 1918 | - | - | - | - |  | #N/A | #N/A | 0 | 0 | 0 | 0 | 0 | #N/A | #N/A | 0 | 1 | 0 | 0 | 0
| 1986.5 | - | - | - | - |  | #N/A | #N/A | 0 | 0 | 0 | 0 | 0 | #N/A | #N/A | 0 | 1 | 0 | 0 | 0
| 2055 | - | - | - | - |  | #N/A | #N/A | 0 | 0 | 0 | 0 | 0 | #N/A | #N/A | 0 | 1 | 0 | 0 | 0
| 2123.5 | - | - | - | - |  | #N/A | #N/A | 0 | 0 | 0 | 0 | 0 | #N/A | #N/A | 0 | 1 | 0 | 0 | 0
| 2192 | - | - | - | - |  | #N/A | #N/A | 0 | 0 | 0 | 0 | 0 | #N/A | #N/A | 0 | 1 | 0 | 0 | 0
| 2260.5 | - | - | - | 4.5 |  | #N/A | #N/A | 0 | 0 | 0 | 0 | 0 | #N/A | #N/A | 3 | 1 | 0 | 0 | 0 | TOL 4 1/2'' at 2249 m
| 2329 | - | - | 7 | - |  | #N/A | #N/A | 0 | 0 | 0 | 0 | 0 | #N/A | #N/A | 1 | 2 | 0 | 0 | 0 | 7'' at 2305 m
| 2397.5 | - | - | 4.5 | - |  | #N/A | #N/A | 0 | 0 | 0 | 0 | 0 | #N/A | #N/A | 2 | 0 | 0 | 0 | 0 | 4 1/2'' at 2399 m
TD at 2400 mMD
G E N E R A L D A T A
[7 empty] | No. AFE | [11 empty] | 23-190-221-OO
[7 empty] | Well Name | [11 empty] | SPA-034 |  |  |  |  | INTERVAL |  |  | DESCRIPTION | PLAN |  | ACTUAL
[7 empty] | Location | [11 empty] | SOPA | [8 empty] | DAYS | CUM | DAYS | CUM
[7 empty] | Field Structure | [11 empty] | PENDOPO | [7 empty] | PRE-OPERATION JOB
[7 empty] | Surface Coord. (X) | [11 empty] | 330343.4411 |  |  |  |  | A | - | B | Rig Move & Rig Up | 0 | 0 | 0 | 0
[7 empty] | Surface Coord. (Y) | [11 empty] | 9639877.6688 | [7 empty] | WORKOVER
[7 empty] | Sub Surface Coord. (X) | [11 empty] | - |  |  |  |  | B | - | C | Preparation (Kill well & POOH existing string) | 1.0208 | 1.0208 | 1.1667 | 1.1667
[7 empty] | Sub Surface Coord. (Y) | [11 empty] | - |  |  |  |  | C | - | D | Squeeze lapisan Eksisting. Run Scraper. Run GR-CBL-CNL | 3.8333 | 4.8542 | 16.5417 | 17.7083
[7 empty] | Elevation | [11 empty] | 1.43 |  |  |  |  | D | - | E | Perbaikan bonding. DOC. Run Scraper. Re run GR-CBL-VDL | 5.4375 | 10.2917 | 0.0625 | 17.7708
[7 empty] | Well Type | [11 empty] | DIRECTIONAL |  |  |  |  | E | - | F | Perforasi Produksi. Stimulation Job. RIH RPP. Swab Job. POOH RPP | 6.1667 | 16.4583 | 2.4375 | 20.2083
[7 empty] | Project Type | [11 empty] | WORKOVER |  |  |  |  | F | - | G | RIH RPP. Put well on production | 2.25 | 18.7083 | 2.75 | 22.9583
[7 empty] | Planned Total Depth | [11 empty] | 1112 | [7 empty] | RELEASE
[7 empty] | Rig Name / Owner | [11 empty] | GJE #11 (450 HP) |  |  |  |  | G | - | H | Rig Release | 0 | 18.7083 | 0 | 22.9583
[7 empty] | Tinggi Rig Floor | [11 empty] | 5.5
[7 empty] | Spud Date | [11 empty] | 2023-01-17 19:00
Release
[7 empty] | AFE BUDGET | [11 empty] | 470258.4928
[7 empty] | ENG. ESTIMATE ACTUAL | [11 empty] | 315917.8721
[7 empty] | PERCENTAGE | [11 empty] | 67.18%
Doc No. : EP3700/Form/DSpv/05. Form Vers: 4.1/2016
[43 empty] | DEPTH | LINK MTR | TOP FM | NO |  | Section | Interval |  |  |  | SUB SECTION | Duration | Drill'g Days | Rig Days |  |  |  |  | KOLOM BANTU | Interval |  |  | DESC | Duration | Drill'g Days | Rig Days
[43 empty] | 0 | 0 | 0 | --------------- | --------------- | --------------- | --------------- | --------------- | --------------- | --------------- | --------------- | --------------- | --------------- | --------------- | [9 empty] | Kum | Hari | Kum
[43 empty] | 0 | 0 | 0 | 1 | Pre Spud | Pre Spud | A | - | B | : | PreSPUD | 0 | 0 | 12 | DRILLING | 200 | 4 | 100 | PRE SPUD |  |  |  | PRE SPUD
[43 empty] | 0 | 0 | 0 | 2 | Pre Spud | Pre Spud | B | - | C | : | PreSPUD | 0 | 0 | 14 | COMPLETION | 300 | 11 | 101 | 1 | A | - | B | Rig Move, Rig Up, including Stand-up 5" DP and 8" DC. | 0 | 0 | 12
[43 empty] | 0 | 0 | 0 | 3 | 26 | DRILLING | C | - | D | : | DRILLING | 1.4375 | 1.4375 | 15.4375 | WORKOVER |  |  | 102 | 2 | B | - | C | Rig Up Top Drive M/U BHA dan Bit 26". | 0 | 0 | 14
[43 empty] | 0 | 0 | 0 | 4 | 26 | DRILLING | D | - | E | : | NON DRILLING | 2.4792 | 3.9167 | 17.9167 | PRE SPUD | 100 | 1 | 200 | DRILLING |  |  |  | DRILLING
[43 empty] | 0 | 0 | 0 | 5 | 17.5 | DRILLING | E | - | F | : | DRILLING | 3.8958 | 7.8125 | 21.8125 |  |  |  | 203 | 3 | C | - | D | Drilling 26" OH to casing point, Circulation, Trip, POOH & L/D BHA | 1.4375 | 1.4375 | 15.4375
[43 empty] | 0 | 0 | 0 | 6 | 17.5 | DRILLING | F | - | G | : | NON DRILLING | 3.3333 | 11.1458 | 25.1458 |  |  |  | 204 | 4 | D | - | E | RIH & 20" Casing Cementing job, WOC, N/U Bottom Flange, N/U BOP Diverter & Pressure Test | 2.4792 | 3.9167 | 17.9167
[43 empty] | 0 | 0 | 0 | 7 | 12.25 | DRILLING | G | - | H | : | DRILLING | 6.1458 | 17.2917 | 31.2917 |  | 101 | 2 | 205 | 5 | E | - | F | Drilling 17,5" OH to Csg Point, Circulation, Trip, POOH & L/D BHA | 3.8958 | 7.8125 | 21.8125
[46 empty] | 8 | 12.25 | DRILLING | H | - | I | : | NON DRILLING | 4.9167 | 22.2083 | 36.2083 |  | 102 | 3 | 206 | 6 | F | - | G | RIH & 13.3/8" Casing Cementing job, WOC, N/U WellHead, N/U BOP & Pressure Test | 3.3333 | 11.1458 | 25.1458
[46 empty] | 9 | Completion | Completion | I | - | J | : | COMPLETION #1 | 4.4792 | 26.6875 | 40.6875 |  | 203 | 5 | 207 | 7 | G | - | H | Drilling 17,5" OH to Csg Point, Circulation, Trip, POOH & L/D BHA | 6.1458 | 17.2917 | 31.2917
[46 empty] | 10 | Completion | Completion | J | - | K | : | COMPLETION #2 | 7.875 | 34.5625 | 48.5625 |  | 204 | 6 | 208 | 8 | H | - | I | RIH & 13.3/8" Casing Cementing job, WOC, N/U WellHead, N/U BOP & Pressure Test | 4.9167 | 22.2083 | 36.2083
[46 empty] | 11 | Completion | Completion | K | - | L | : | COMPLETION #3 | 15.8333 | 50.3958 | 64.3958 |  | 205 | 7 | 300 | COMPLETION |  |  |  | COMPLETION
[46 empty] | 12 |  |  | L | - | M | : |  |  | 50.3958 |  |  | 206 | 8 | 309 | 9 | I | - | J | RIH Scrapper to Liner depth interval, RIH and perform production casing cementing job | 4.4792 | 26.6875 | 40.6875
[46 empty] | 13 |  |  | M | - | N | : |  |  | 50.3958 |  |  | 207 | 9 | 310 | 10 | J | - | K | Completion Job | 7.875 | 34.5625 | 48.5625
[46 empty] | 14 |  |  | N | - | O | : |  |  | 50.3958 |  |  | 208 | 10 | 311 | 11 | K | - | L | Production Test | 15.8333 | 50.3958 | 64.3958
[46 empty] | 15 |  |  | O | - | P | : |  |  | 50.3958 |  |  | 309 | 12
[33 empty] | PLAN |  |  |  | ACTUAL | [8 empty] | 16 |  |  | P | - | Q | : |  |  | 50.3958 |  |  | 310 | 13
[33 empty] | LINK MTR | CSG | DEPTH | CASING TYPE : LINK | LINK MTR | CSG | DEPTH | CASING TYPE : LINK | KOMBINASI DATA UNTUK WELL PROFILE |  |  |  |  | 17 |  |  | Q | - | R | : |  |  | 50.3958 |  |  | 311 | 14
[33 empty] | 0 | 20 | 0 | 20'' at 0 m | 68.5 | 20 | 98.69 | 20'' at 99 m | Total Depth | 2399 | mMD |  |  | 18 |  |  | R | - | S | : |  |  | 50.3958
[33 empty] | 0 | 13.375 | 0 | 13 3/8'' at 0 m | 685 | 13.375 | 698.86 | 13 3/8'' at 699 m | Jumlah Row | 35 | -- |  |  | 19 |  |  | S | - | T | : |  |  | 50.3958
[33 empty] | 0 | 9.625 | 0 | 9 5/8'' at 0 m | 1507 | 9.625 | 1495.27 | 9 5/8'' at 1495 m | Pjg Line | 68.5 | -- |  |  | 20 |  |  | T | - | U | : |  |  | 50.3958
[33 empty] | 0 | 7 | 0 | 7'' at 0 m | 2329 | 7 | 2305 | 7'' at 2305 m | [5 empty] | 21 |  |  | U | - | V | : |  |  | 50.3958
[33 empty] | 0 | 4.5 | 0 | 4 1/2'' at 0 m | 2397.5 | 4.5 | 2399 | 4 1/2'' at 2399 m
[33 empty] | 0 |  | 0 | 0'' at 0 m | 0 |  | 0 | 0'' at 0 m
[33 empty] | 0 |  | 0 | 0'' at 0 m | 0 |  | 0 | 0'' at 0 m
[37 empty] | 0 |  | 0 | '' at 0 m
[33 empty] | 0 | 7 | 0 | TOL 7'' at 0 m | 1438.5 | 7 | 1433.34 | TOL 7'' at 1433 m
[33 empty] | 0 | 4.5 | 0 | TOL 4 1/2'' at 0 m | 2260.5 | 4.5 | 2249 | TOL 4 1/2'' at 2249 m
[34 empty] | 0 |  | TOL 0'' at m |  | 0 |  | TOL 0'' at m
[34 empty] | KOP #1 |  | KOP #1'' at m |  | KOP #1 |  | KOP #1'' at m
[34 empty] | KOP #2 |  | KOP #2'' at m |  | KOP #2 |  | KOP #2'' at m
Keterangan Marker (Call Out) dibuat secara manual, pakai contoh ini
NPT Rig GJE #11
(Tubular problem) : 8 jam
NPT Rig GJE #11
(Repair rotating system) : 3,5 jam

## 3_TIME SUM
WORKOVER TIME SUMMARY
Doc No. : EP3700/Form/DSpv/05 Form Vers. : 4.0/2016
WELL |  | : SPA-034
LOCATION |  | : SOPA
IADC Code |  | Description | Sub code | Sub Description | Code | NPT | Hours | REMARK |  |  | NICK NAME
DRILLING TIME | 1 | Rig Up and Tear Down | a | R/U | 1a |  | 0 |  |  |  | RU & Tear Down - JRA/ Safety Meeting / Time Out
|  |  | b | R/D | 1b |  | 0 |  |  |  | R/U
|  |  | c | Prepare Rig Mob/Demob | 1c |  | 0 |  |  |  | R/D
|  |  | d | Under Tow / Mobilization | 1d |  | 0 |  |  |  | Prepare Rig Mob/Demob
|  |  | e | Anchoring Operations | 1e |  | 0 |  |  |  | Under Tow / Mobilization
|  |  | f | Jack Up / Jack Down | 1f |  | 0 |  |  |  | Anchoring Operations
|  |  | g | Preload | 1g |  | 0 |  |  |  | Jack Up / Jack Down
|  |  | h | Skid Out / Skid In | 1h |  | 0 |  |  |  | Preload
|  |  | i | Pull Leg | 1i |  | 0 |  |  |  | Skid Out / Skid In
|  |  | j | Others | 1j |  | 0 | Untuk Services Non Rig (MPD, UBD, CTU, Wireline etc) selama menambah operation days |  |  | Pull Leg
Others
| 2 | Drilling Actual | a | Drilling - Rotating | 2a |  | 0 |  |  |  | Drilling Actual - JRA/ Safety Meeting / Drills / Time Out
|  |  | b | Drilling - Sliding | 2b |  | 0 |  |  |  | Drilling - Rotating
|  |  | c | Coiled Tubing - Drilling | 2c |  | 50 | Drill Out Cement, Bottom & Top Plug, Float Shoe, DSCC. Include milling yang direncanakan | Drill Out Cement, Bottom & Top Plug, Float Shoe, DSCC. Include milling yang direncanakan | Drill Out Cement, Bottom & Top Plug, Float Shoe, DSCC. Include milling yang direncanakan | Drilling - Sliding
|  |  | d | Flow Check / Monitor Well While Drilling | 2d |  | 0.5 | Monitoring well while drilling | Monitoring well while drilling | Monitoring well while drilling | Coiled Tubing - Drilling
|  |  | e | Other Drilling Activities | 2e |  | 2 |  |  |  | Flow Check / Monitor Well while Drilling
|  |  | f | Test casing / Leak Off Test / Formation Integrity Test | 2f |  | 4 |  |  |  | Clean Rig Floor
|  |  | g | Well Control Operations / Situation (NPT) | 2g |  | 0 |  |  |  | Other drilling Activities
|  |  | h | Lossing Circ / Pumping LCM / Monitor Unplanned (NPT) | 2h |  | 0 |  |  |  | Other drilling Activities
|  |  | i | Lossing Circ / Pumping LCM / Monitor planned | 2i |  | 0 |  |  |  | Other drilling Activities
|  |  | j | Stuck Pipe Include Handling operations (NPT) | 2j |  | 0 |  |  |  | Other drilling Activities
| 3 | Reaming | a | Wash / Reaming / Backreaming | 3a |  | 11 |  |  |  | Reaming - JRA/ Safety Meeting / Time Out
|  |  | b | Wash / Reaming / Backreaming Unplanned (NPT) | 3b | NPT | 0 |  |  |  | Reaming / Backreaming
|  |  | c | Enlarge Hole (Under Reaming) | 3c |  | 0 |  |  |  | Coiled Tubing - Reaming / Backreaming
| 4 | Coring | a | Pick up / Lay down Core barrel | 4a |  | 0 |  |  |  | Coring - JRA/ Safety Meeting / Time Out
|  |  | b | Trip in / Out for Core | 4b |  | 0 |  |  |  | Pick Up / Lay Down Core Barrel
|  |  | c | Coring | 4c |  | 0 |  |  |  | Trip in / Out for Core
|  |  | d | Coiled Tubing - Coring | 4d |  | 0 |  |  |  | Coring
[7 empty] | 0 |  |  |  | Coiled Tubing - Coring
| 5 | Condition Mud & Circulate | a | Circulate / Condition Mud | 5a |  | 18.5 |  |  |  | Condition Mud - JRA/ Safety Meeting / Time Out
|  |  | b | Change Mud System | 5b |  | 0
|  |  | c | Unplanned Circulate / Condition Mud | 5c | NPT | 0 | Sirkulasi yang tidak direncanakan dalam program
| 6 | Trips | a | PU / LD BHA | 6a |  | 0
|  |  | b | Stand Up or L/D Drill Pipe | 6b |  | 1.5
|  |  | c | Load / Unload MWD / LWD when out of hole | 6c |  | 0
|  |  | d | Trip in / out Drilling BHA | 6d |  | 81
|  |  | e | Trip in / out Coiled Tubing | 6e |  | 0
|  |  | f | Pumping Out of Hole / Casing | 6f |  | 0
|  |  | g | Wiper / Conditioner Trip | 6g |  | 120
|  |  | h | Flow Check / Monitor Well | 6h |  | 1
| 7 | Lubricate Rig | a | Service Rig - Normal Lubrication and service of Rig | 7a |  | 0
|  |  | b | Scheduled Planned Maintenance - that shuts operations down without contractual down time | 7b |  | 0
| 8 | Repair Rig | a | Repair Power System (NPT) | 8a | NPT | 0
|  |  | b | Repair Housting System (NPT) | 8b | NPT | 0
|  |  | c | Repair Cirulating System (NPT) | 8c | NPT | 0
|  |  | d | Repair Rotating System (NPT) | 8d | NPT | 3.5
|  |  | e | Repair Blow Out Preventer System (NPT) | 8e | NPT | 0
|  |  | f | Tubular Problem (NPT) | 8f | NPT | 8
|  |  | g | Personal Problem (NPT) | 8g | NPT | 0
| 9 | Cut off Drilling Line | a | Slip and Cut Drill Line | 9a |  | 0
| 10 | Deviation Survey | a | Performing Survey Operations | 10b |  | 0
| 11 | Wireline Logs | a | Wireline Logging / Drill Pipe conveyed | 11a |  | 14.5
|  |  | b | Wireline Work Other | 11b |  | 1
|  |  | c | Slick Line Job | 11c |  | 0
|  |  | d | Wireline/Slick Line Job Unplanned (NPT) | 11d | NPT | 0 | Pekerjaan wireline/slick line yang tidak direncanakan (ganti konfigurasi tools akibat duduk, etc)
| 12 | Run Casing and Cement | a | Change Rams | 12a |  | 1
|  |  | b | Rig Up/Rig Down Casing Running, Running Tools, Hammer for Drive Pipe | 12b |  | 0
|  |  | c | Make Up Floating Equipment | 12c |  | 0
|  |  | d | Run Casing / Liner / Accessories Lainya | 12d |  | 0
|  |  | e | Cement Casing / Liner | 12e |  | 0
|  |  | f | Run Casing / Liner Problem (NPT) | 12f | NPT | 0 | Casing/liner duduk, stuck, cabut casing/liner
| 13 | Wait on Cement | a | Waiting on Cement | 13a |  | 52.5
| 14 | Nipple Up BOP | a | Install / Remove or Change Wellhead and Riser (spool) include final casing cut / dressing stub | 14a |  | 5
|  |  | b | N/U BOP, N/U & Install Diverter, Install Bell Nipple and Flowline or mandrel | 14b |  | 3.5
|  |  | c | N/D BOP, N/D Diverter, N/D Bell Nipple and Flowline or mandrel | 14c |  | 4
|  |  | d | Other BOP Operation | 14d |  | 0
| 15 | Test BOP | a | Function & Pressure Test of BOP's | 15a |  | 1
| 16 | Drill Stem Test / WCT (Well Completion Test di PGE) | a | Drill Stem Test | 16a |  | 0 | Pekerjaan Mulai RIH Down Hole Test, Proses Testing hingga Cabut Down Hole Test spi Permukaan
| 17 | Plug Back | a | Plug back - cement | 17a |  | 0 | For Abandont, Combat Loss
|  |  | b | Coiled Tubing - Plug back | 17b |  | 0 | For Abandont, Combat Loss
|  |  | c | Plugback - other | 17c |  | 0 | For sidetrack
| 18 | Squeeze Cement | a | Squeeze Planned Include Used Coiled Tubing | 18a |  | 18 | Remedial Cementing & Tutup Zona Perforasi
|  |  | b | Squeeze Unplanned (NPT) | 18b |  | 0 | Mengatasi Casing bocor, Top liner bocor, DSCC bocor, Kegagalan Primary Cementing
| 19 | Fishing | a | Fishing Operations (NPT) | 19a | NPT | 0
| 20 | Open Windows | a | Preparation, Run & Set Wipstock | 20a |  | 0
|  |  | b | Mill / Cut Window c/w Mill Bit & Coilled Tubing | 20b |  | 0
0
| 21 | Service Company (NPT) | a | Directional Services | 21a | NPT | 0
|  |  | b | Mud Services | 21b | NPT | 0
|  |  | c | MLU Services | 21c | NPT | 0
|  |  | d | UBD, MPD, Aerated Services | 21d | NPT | 0
|  |  | e | Casing Drilling Services | 21e | NPT | 0
|  |  | f | Cementing Services | 21f | NPT | 0
|  |  | g | Down Hole & Surface Services | 21g | NPT | 0
|  |  | h | Coiled Tubing Services | 21h | NPT | 0
|  |  | i | Wireline Services | 21i | NPT | 0
|  |  | j | Slick Line Services | 21j | NPT | 0
|  |  | k | RTO Services | 21k | NPT | 0
|  |  | l | Tubular Services | 21l | NPT | 0
|  |  | m | Well Head & X-Mastree Services | 21m | NPT | 0
|  |  | n | Solid Control Services (Pihak Ketiga) | 21n | NPT | 0
|  |  | o | Waste Management Services | 21o | NPT | 0
|  |  | p | H2S Services | 21p | NPT | 0
|  |  | q | Stimulation Services | 21q | NPT | 0
|  |  | r | Marine Support Services | 21r | NPT | 0
|  |  | s | Transportation Services | 21s | NPT | 0
|  |  | t | Others Services | 21t | NPT | 0
| 22 | Others NPT | a | Material Problems | 22a | NPT | 0
|  |  | b | Sosial Issue | 22b | NPT | 0
|  |  | c | Evironment Issue | 22c | NPT | 0
|  |  | d | Location Problem | 22d | NPT | 0
|  |  | e | Logistics Problem | 22e | NPT | 0
|  |  | f | Regulatory problems | 22f | NPT | 0
|  |  | g | Other Problem Time | 22g | NPT | 0
| 23 | Uncontrol Situation | a | Waiting on Weather | 23a |  | 5
|  |  | b | Force Majure | 23b |  | 0 | Tidak termasuk PT & NPT
|  |  | c | Tunggu Hari Terang | 23c |  | 0
COMPLETION TIME | 24 | Drills | a | Kick Drill, Medivac drill, Pit drill, H2S Drill, etc | 24a |  | 0 | Semua pelatihan terkait keselamatan kerja
| 25 | Cased Hole Logging & Perforating | a | Cased hole logging | 25a |  | 0
|  |  | b | Perforating | 25b |  | 0
| 26 | Trips | a | Running / pulling Scraper | 26a |  | 24
|  |  | b | Running / pulling Production Tubing (Tubing Trips) | 26b |  | 54 | Termasuk Run TCP untuk sumur Pengembangan
|  |  | c | Test / Presure test production tubing | 26c |  | 20
| 27 | Stimulation | a | Stimulation/Fracturing/Unloading/Production Treatment | 27a |  | 11.5
| 28 | Swabbing | a | Swabbing Well | 28a |  | 0
| 29 | Production Test | a | Well Testing | 29a |  | 35
| 30 | X-Mastree | a | N/U & N/D | 30a |  | 0
|  |  | b | Tree Pressure Testing | 30b | NPT | 0
TOTAL RUN HOURS | [6 empty] | 551
note ALERT : N/A | [6 empty] | 0
NPT starts whenever normal operation cease and there is no drilling progress

## 5_PERFORM (1)_Table
HIDE | HIDE | HIDE | HIDE | HIDE | HIDE | HIDE | HIDE | HIDE | HIDE | HIDE | HIDE | HIDE | HIDE | HIDE | HIDE | HIDE | HIDE | HIDE | HIDE |  |  | CHOOSE ACTIVITY HERE êêêêêêê
|  |  | WORKOVER SECTION | [15 empty] | #VALUE! | #VALUE! |  | WORKOVER SECTION |  |  |  |  | <<< GRAFIKNYA DI SHEET "5_PERFORM (2)_Graph" | FOR GRAPH
ITEM DESC | ROW |  | 5 | 3 |  |  | PT & NPT | HRS | ORDER | [9 empty] | 38 |  |  |  | Doc No. : EP3700/Form/DSpv/05 Form Vers. : 4.0/2016 |  |  |  |  | WORKOVER SECTIONSPA-034
STARTING CELL | 9 |  | R/U | Rig Up and Tear Down | Rig Up and Tear Down : R/U | 1a | PT | 0 |  |  | 1000 |  | DRY HOLE BASE | 1000 | 1 | 1000 | DRY HOLE BASE | 0 | [9 empty] | 1 | 1001 | Drilling Actual : Coiled Tubing - Drilling | 2.0833
WORKOVER SECTION | 192 |  | R/D | Rig Up and Tear Down | Rig Up and Tear Down : R/D | 1b | PT | 0 |  |  | 1000 |  | COMPLETION BASE |  | 0 | 1001 | Drilling Actual : Coiled Tubing - Drilling | 1 |  |  | WELL | : SPA-034 | [5 empty] | 2 | 1002 | Drilling Actual : Flow Check / Monitor Well While Drilling | 0.020833
RELEASE | 194 |  | Prepare Rig Mob/Demob | Rig Up and Tear Down | Rig Up and Tear Down : Prepare Rig Mob/Demob | 1c | PT | 0 |  |  | 1000 |  |  |  | 0 | 1002 | Drilling Actual : Flow Check / Monitor Well While Drilling | 2 |  |  | LOCATION | : SOPA | [5 empty] | 3 | 1003 | Drilling Actual : Other Drilling Activities | 0.083333
| 13 |  | Under Tow / Mobilization | Rig Up and Tear Down | Rig Up and Tear Down : Under Tow / Mobilization | 1d | PT | 0 |  |  | 1000 |  |  |  | 0 | 1003 | Drilling Actual : Other Drilling Activities | 3 | [9 empty] | 4 | 1004 | Drilling Actual : Test casing / Leak Off Test / Formation Integrity Test | 0.16667
| 13 |  | Anchoring Operations | Rig Up and Tear Down | Rig Up and Tear Down : Anchoring Operations | 1e | PT | 0 |  |  | 1000 |  |  |  | 0 | 1004 | Drilling Actual : Test casing / Leak Off Test / Formation Integrity Test | 4 |  |  | AFE PLAN | : 19 days | DRY HOLE BASE |  | : 23 days |  |  | 5 | 1005 | Reaming : Wash / Reaming / Backreaming | 0.45833
| 13 |  | Jack Up / Jack Down | Rig Up and Tear Down | Rig Up and Tear Down : Jack Up / Jack Down | 1f | PT | 0 |  |  | 1000 |  |  |  | 0 | 1005 | Reaming : Wash / Reaming / Backreaming | 5 |  |  | ACTUAL | : 16,864 days | COMPLETION BASE |  | : 0,0 days |  |  | 6 | 1006 | Condition Mud & Circulate : Circulate / Condition Mud | 0.77083
| 13 |  | Preload | Rig Up and Tear Down | Rig Up and Tear Down : Preload | 1g | PT | 0 |  |  | 1000 |  |  |  | 0 | 1006 | Condition Mud & Circulate : Circulate / Condition Mud | 6 | [9 empty] | 7 | 1007 | Trips : Stand Up or L/D Drill Pipe | 0.0625
| 13 |  | Skid Out / Skid In | Rig Up and Tear Down | Rig Up and Tear Down : Skid Out / Skid In | 1h | PT | 0 |  |  | 1000 |  |  |  | 0 | 1007 | Trips : Stand Up or L/D Drill Pipe | 7 | [9 empty] | 8 | 1008 | Trips : Trip in / out Drilling BHA | 3.375
0 |  |  | Pull Leg | Rig Up and Tear Down | Rig Up and Tear Down : Pull Leg | 1i | PT | 0 |  |  | 1000 |  |  |  | 0 | 1008 | Trips : Trip in / out Drilling BHA | 8 |  |  | NO | ACTIVITY | STATUS | CODE | HOURS | DAYS |  | 9 | 1009 | Trips : Wiper / Conditioner Trip | 5
ALL ACTIVITY | 194 |  | Others | Rig Up and Tear Down | Rig Up and Tear Down : Others | 1j | PT | 0 |  |  | 1000 |  |  |  | 0 | 1009 | Trips : Wiper / Conditioner Trip | 9 |  |  |  | DRY HOLE BASE | [5 empty] | 10 | 1010 | Trips : Flow Check / Monitor Well | 0.041667
NON PRODUCTIVE TIME |  |  | 0 | Rig Up and Tear Down | Rig Up and Tear Down : 0 | #N/A | #N/A | 0 | [6 empty] | 0 | 1010 | Trips : Flow Check / Monitor Well | 10 |  |  | 1 | Drilling Actual : Coiled Tubing - Drilling | PT | 2c | 50 | 2.0833 |  | 11 | 1011 | Repair Rig : Repair Rotating System (NPT) | 0.14583
|  |  | Drilling - Rotating | Drilling Actual | Drilling Actual : Drilling - Rotating | 2a | PT | 0 |  |  | 1000 |  |  |  | 0 | 1011 | Repair Rig : Repair Rotating System (NPT) | 11 |  |  | 2 | Drilling Actual : Flow Check / Monitor Well While Drilling | PT | 2d | 0.5 | 0.020833 |  | 12 | 1012 | Repair Rig : Tubular Problem (NPT) | 0.33333
|  |  | Drilling - Sliding | Drilling Actual | Drilling Actual : Drilling - Sliding | 2b | PT | 0 |  |  | 1000 |  |  |  | 0 | 1012 | Repair Rig : Tubular Problem (NPT) | 12 |  |  | 3 | Drilling Actual : Other Drilling Activities | PT | 2e | 2 | 0.083333 |  | 13 | 1013 | Wireline Logs : Wireline Logging / Drill Pipe conveyed | 0.60417
|  |  | Coiled Tubing - Drilling | Drilling Actual | Drilling Actual : Coiled Tubing - Drilling | 2c | PT | 50 | 1 |  | 1000 | 1001 |  |  | 0 | 1013 | Wireline Logs : Wireline Logging / Drill Pipe conveyed | 13 |  |  | 4 | Drilling Actual : Test casing / Leak Off Test / Formation Integrity Test | PT | 2f | 4 | 0.16667 |  | 14 | 1014 | Wireline Logs : Wireline Work Other | 0.041667
|  |  | Flow Check / Monitor Well While Drilling | Drilling Actual | Drilling Actual : Flow Check / Monitor Well While Drilling | 2d | PT | 0.5 | 2 |  | 1000 | 1002 |  |  | 0 | 1014 | Wireline Logs : Wireline Work Other | 14 |  |  | 5 | Reaming : Wash / Reaming / Backreaming | PT | 3a | 11 | 0.45833 |  | 15 | 1015 | Run Casing and Cement : Change Rams | 0.041667
|  |  | Other Drilling Activities | Drilling Actual | Drilling Actual : Other Drilling Activities | 2e | PT | 2 | 3 |  | 1000 | 1003 |  |  | 0 | 1015 | Run Casing and Cement : Change Rams | 15 |  |  | 6 | Condition Mud & Circulate : Circulate / Condition Mud | PT | 5a | 18.5 | 0.77083 |  | 16 | 1016 | Wait on Cement : Waiting on Cement | 2.1875
|  |  | Test casing / Leak Off Test / Formation Integrity Test | Drilling Actual | Drilling Actual : Test casing / Leak Off Test / Formation Integrity Test | 2f | PT | 4 | 4 |  | 1000 | 1004 |  | 1001 | 2 | 1016 | Wait on Cement : Waiting on Cement | 16 |  |  | 7 | Trips : Stand Up or L/D Drill Pipe | PT | 6b | 1.5 | 0.0625 |  | 17 | 1017 | Nipple Up BOP : Install / Remove or Change Wellhead and Riser (spool) include final casing cut / dressing stub | 0.20833
|  |  | Well Control Operations / Situation (NPT) | Drilling Actual | Drilling Actual : Well Control Operations / Situation (NPT) | 2g | PT | 0 |  |  | 1000 |  |  | 1002 | 3 | 1017 | Nipple Up BOP : Install / Remove or Change Wellhead and Riser (spool) include final casing cut / dressing stub | 17 |  |  | 8 | Trips : Trip in / out Drilling BHA | PT | 6d | 81 | 3.375 |  | 18 | 1018 | Nipple Up BOP : N/U BOP, N/U & Install Diverter, Install Bell Nipple and Flowline or mandrel | 0.14583
|  |  | Lossing Circ / Pumping LCM / Monitor Unplanned (NPT) | Drilling Actual | Drilling Actual : Lossing Circ / Pumping LCM / Monitor Unplanned (NPT) | 2h | PT | 0 |  |  | 1000 |  |  | 1003 | 4 | 1018 | Nipple Up BOP : N/U BOP, N/U & Install Diverter, Install Bell Nipple and Flowline or mandrel | 18 |  |  | 9 | Trips : Wiper / Conditioner Trip | PT | 6g | 120 | 5 |  | 19 | 1019 | Nipple Up BOP : N/D BOP, N/D Diverter, N/D Bell Nipple and Flowline or mandrel | 0.16667
|  |  | Lossing Circ / Pumping LCM / Monitor planned | Drilling Actual | Drilling Actual : Lossing Circ / Pumping LCM / Monitor planned | 2i | PT | 0 |  |  | 1000 |  |  | 1004 | 5 | 1019 | Nipple Up BOP : N/D BOP, N/D Diverter, N/D Bell Nipple and Flowline or mandrel | 19 |  |  | 10 | Trips : Flow Check / Monitor Well | PT | 6h | 1 | 0.041667 |  | 20 | 1020 | Test BOP : Function & Pressure Test of BOP's | 0.041667
|  |  | Stuck Pipe Include Handling operations (NPT) | Drilling Actual | Drilling Actual : Stuck Pipe Include Handling operations (NPT) | 2j | PT | 0 |  |  | 1000 |  |  |  | 0 | 1020 | Test BOP : Function & Pressure Test of BOP's | 20 |  |  | 11 | Repair Rig : Repair Rotating System (NPT) | NPT | 8d | 3.5 | 0.14583 |  | 21 | 1021 | Squeeze Cement : Squeeze Planned Include Used Coiled Tubing | 0.75
|  |  | Wash / Reaming / Backreaming | Reaming | Reaming : Wash / Reaming / Backreaming | 3a | PT | 11 | 5 |  | 1000 | 1005 |  |  | 0 | 1021 | Squeeze Cement : Squeeze Planned Include Used Coiled Tubing | 21 |  |  | 12 | Repair Rig : Tubular Problem (NPT) | NPT | 8f | 8 | 0.33333 |  | 22 | 1022 | Uncontrol Situation : Waiting on Weather | 0.20833
|  |  | Wash / Reaming / Backreaming Unplanned (NPT) | Reaming | Reaming : Wash / Reaming / Backreaming Unplanned (NPT) | 3b | NPT | 0 |  |  | 1000 |  |  |  | 0 | 1022 | Uncontrol Situation : Waiting on Weather | 22 |  |  | 13 | Wireline Logs : Wireline Logging / Drill Pipe conveyed | PT | 11a | 14.5 | 0.60417 |  | 23 | 1023 | Trips : Running / pulling Scraper | 1
|  |  | Enlarge Hole (Under Reaming) | Reaming | Reaming : Enlarge Hole (Under Reaming) | 3c | PT | 0 |  |  | 1000 |  |  |  | 0 | 1023 | Trips : Running / pulling Scraper | 23 |  |  | 14 | Wireline Logs : Wireline Work Other | PT | 11b | 1 | 0.041667 |  | 24 | 1024 | Trips : Running / pulling Production Tubing (Tubing Trips) | 2.25
|  |  | Pick up / Lay down Core barrel | Coring | Coring : Pick up / Lay down Core barrel | 4a | PT | 0 |  |  | 1000 |  |  | 1005 | 6 | 1024 | Trips : Running / pulling Production Tubing (Tubing Trips) | 24 |  |  | 15 | Run Casing and Cement : Change Rams | PT | 12a | 1 | 0.041667 |  | 25 | 1025 | Trips : Test / Presure test production tubing | 0.83333
|  |  | Trip in / Out for Core | Coring | Coring : Trip in / Out for Core | 4b | PT | 0 |  |  | 1000 |  |  |  | 0 | 1025 | Trips : Test / Presure test production tubing | 25 |  |  | 16 | Wait on Cement : Waiting on Cement | PT | 13a | 52.5 | 2.1875 |  | 26 | 1026 | Stimulation : Stimulation/Fracturing/Unloading/Production Treatment | 0.47917
|  |  | Coring | Coring | Coring : Coring | 4c | PT | 0 |  |  | 1000 |  |  |  | 0 | 1026 | Stimulation : Stimulation/Fracturing/Unloading/Production Treatment | 26 |  |  | 17 | Nipple Up BOP : Install / Remove or Change Wellhead and Riser (spool) include final casing cut / dressing stub | PT | 14a | 5 | 0.20833 |  | 27 | 1027 | Production Test : Well Testing | 1.4583
|  |  | Coiled Tubing - Coring | Coring | Coring : Coiled Tubing - Coring | 4d | PT | 0 |  |  | 1000 |  |  |  | 0 | 1027 | Production Test : Well Testing | 27 |  |  | 18 | Nipple Up BOP : N/U BOP, N/U & Install Diverter, Install Bell Nipple and Flowline or mandrel | PT | 14b | 3.5 | 0.14583 |  | 28
|  |  | 0 | Coring | Coring : 0 | #N/A | #N/A | 0 | [6 empty] | 0 | - |  |  |  |  | 19 | Nipple Up BOP : N/D BOP, N/D Diverter, N/D Bell Nipple and Flowline or mandrel | PT | 14c | 4 | 0.16667 |  | 29
|  |  | Circulate / Condition Mud | Condition Mud & Circulate | Condition Mud & Circulate : Circulate / Condition Mud | 5a | PT | 18.5 | 6 |  | 1000 | 1006 |  |  | 0 | - |  |  |  |  | 20 | Test BOP : Function & Pressure Test of BOP's | PT | 15a | 1 | 0.041667 |  | 30
|  |  | Change Mud System | Condition Mud & Circulate | Condition Mud & Circulate : Change Mud System | 5b | PT | 0 |  |  | 1000 |  |  |  | 0 | - |  |  |  |  | 21 | Squeeze Cement : Squeeze Planned Include Used Coiled Tubing | PT | 18a | 18 | 0.75 |  | 31
|  |  | Unplanned Circulate / Condition Mud | Condition Mud & Circulate | Condition Mud & Circulate : Unplanned Circulate / Condition Mud | 5c | NPT | 0 |  |  | 1000 |  |  |  | 0 | - |  |  | 1000 |  | 22 | Uncontrol Situation : Waiting on Weather | PT | 23a | 5 | 0.20833 |  | 32
|  |  | PU / LD BHA | Trips | Trips : PU / LD BHA | 6a | PT | 0 |  |  | 1000 |  |  | 1006 | 7 | - |  |  | 1001 |  | 23 | Trips : Running / pulling Scraper | PT | 26a | 24 | 1 |  | 33
|  |  | Stand Up or L/D Drill Pipe | Trips | Trips : Stand Up or L/D Drill Pipe | 6b | PT | 1.5 | 7 |  | 1000 | 1007 |  |  | 0 | - |  |  | 1002 |  | 24 | Trips : Running / pulling Production Tubing (Tubing Trips) | PT | 26b | 54 | 2.25 |  | 34
|  |  | Load / Unload MWD / LWD when out of hole | Trips | Trips : Load / Unload MWD / LWD when out of hole | 6c | PT | 0 |  |  | 1000 |  |  |  | 0 | - |  |  | 1003 |  | 25 | Trips : Test / Presure test production tubing | PT | 26c | 20 | 0.83333 |  | 35
|  |  | Trip in / out Drilling BHA | Trips | Trips : Trip in / out Drilling BHA | 6d | PT | 81 | 8 |  | 1000 | 1008 |  |  | 0 | - |  |  | 1004 |  | 26 | Stimulation : Stimulation/Fracturing/Unloading/Production Treatment | PT | 27a | 11.5 | 0.47917 |  | 36
|  |  | Trip in / out Coiled Tubing | Trips | Trips : Trip in / out Coiled Tubing | 6e | PT | 0 |  |  | 1000 |  |  | 1007 | 8 | - |  |  | 1005 |  | 27 | Production Test : Well Testing | PT | 29a | 35 | 1.4583 |  | 37
|  |  | Pumping Out of Hole / Casing | Trips | Trips : Pumping Out of Hole / Casing | 6f | PT | 0 |  |  | 1000 |  |  |  | 0 | - |  |  | 1006 | [8 empty] | 38
|  |  | Wiper / Conditioner Trip | Trips | Trips : Wiper / Conditioner Trip | 6g | PT | 120 | 9 |  | 1000 | 1009 |  | 1008 | 9 | - |  |  | 1007 | [8 empty] | 39
|  |  | Flow Check / Monitor Well | Trips | Trips : Flow Check / Monitor Well | 6h | PT | 1 | 10 |  | 1000 | 1010 |  |  | 0 | - |  |  | 1008 | [8 empty] | 40
|  |  | Service Rig - Normal Lubrication and service of Rig | Lubricate Rig | Lubricate Rig : Service Rig - Normal Lubrication and service of Rig | 7a | PT | 0 |  |  | 1000 |  |  |  | 0 | - |  |  | 1009 | [8 empty] | 41
|  |  | Scheduled Planned Maintenance - that shuts operations down without contractual down time | Lubricate Rig | Lubricate Rig : Scheduled Planned Maintenance - that shuts operations down without contractual down time | 7b | PT | 0 |  |  | 1000 |  |  | 1009 | 10 | - |  |  | 1010 | [8 empty] | 42
|  |  | Repair Power System (NPT) | Repair Rig | Repair Rig : Repair Power System (NPT) | 8a | NPT | 0 |  |  | 1000 |  |  | 1010 | 11 | - |  |  | 1011 | [8 empty] | 43
|  |  | Repair Housting System (NPT) | Repair Rig | Repair Rig : Repair Housting System (NPT) | 8b | NPT | 0 |  |  | 1000 |  |  |  | 0 | - |  |  | 1012 | [8 empty] | 44
|  |  | Repair Cirulating System (NPT) | Repair Rig | Repair Rig : Repair Cirulating System (NPT) | 8c | NPT | 0 |  |  | 1000 |  |  |  | 0 | - |  |  | 1013 | [8 empty] | 45
|  |  | Repair Rotating System (NPT) | Repair Rig | Repair Rig : Repair Rotating System (NPT) | 8d | NPT | 3.5 | 11 |  | 1000 | 1011 |  |  | 0 | - |  |  | 1014 | [8 empty] | 46
|  |  | Repair Blow Out Preventer System (NPT) | Repair Rig | Repair Rig : Repair Blow Out Preventer System (NPT) | 8e | NPT | 0 |  |  | 1000 |  |  |  | 0 | - |  |  | 1015 | [8 empty] | 47
|  |  | Tubular Problem (NPT) | Repair Rig | Repair Rig : Tubular Problem (NPT) | 8f | NPT | 8 | 12 |  | 1000 | 1012 |  |  | 0 | - |  |  | 1016 | [8 empty] | 48
|  |  | Personal Problem (NPT) | Repair Rig | Repair Rig : Personal Problem (NPT) | 8g | NPT | 0 |  |  | 1000 |  |  | 1011 | 12 | - |  |  | 1017 | [8 empty] | 49
|  |  | Slip and Cut Drill Line | Cut off Drilling Line | Cut off Drilling Line : Slip and Cut Drill Line | 9a | PT | 0 |  |  | 1000 |  |  |  | 0 | - |  |  | 1018 | [8 empty] | 50
|  |  | Performing Survey Operations | Deviation Survey | Deviation Survey : Performing Survey Operations | 10b | PT | 0 |  |  | 1000 |  |  | 1012 | 13 | - |  |  | 1019 | [8 empty] | 51
|  |  | Wireline Logging / Drill Pipe conveyed | Wireline Logs | Wireline Logs : Wireline Logging / Drill Pipe conveyed | 11a | PT | 14.5 | 13 |  | 1000 | 1013 |  |  | 0 | - |  |  | 1020 | [8 empty] | 52
|  |  | Wireline Work Other | Wireline Logs | Wireline Logs : Wireline Work Other | 11b | PT | 1 | 14 |  | 1000 | 1014 |  |  | 0 | - |  |  | 1021 | [8 empty] | 53
|  |  | Slick Line Job | Wireline Logs | Wireline Logs : Slick Line Job | 11c | PT | 0 |  |  | 1000 |  |  |  | 0 | - |  |  | 1022 | [8 empty] | 54
|  |  | Wireline/Slick Line Job Unplanned (NPT) | Wireline Logs | Wireline Logs : Wireline/Slick Line Job Unplanned (NPT) | 11d | NPT | 0 |  |  | 1000 |  |  | 1013 | 14 | - |  |  | 1023 | [8 empty] | 55
|  |  | Change Rams | Run Casing and Cement | Run Casing and Cement : Change Rams | 12a | PT | 1 | 15 |  | 1000 | 1015 |  | 1014 | 15 | - |  |  | 1024 | [8 empty] | 56
|  |  | Rig Up/Rig Down Casing Running, Running Tools, Hammer for Drive Pipe | Run Casing and Cement | Run Casing and Cement : Rig Up/Rig Down Casing Running, Running Tools, Hammer for Drive Pipe | 12b | PT | 0 |  |  | 1000 |  |  |  | 0 | - |  |  | 1025 | [8 empty] | 57
|  |  | Make Up Floating Equipment | Run Casing and Cement | Run Casing and Cement : Make Up Floating Equipment | 12c | PT | 0 |  |  | 1000 |  |  |  | 0 | - |  |  | 1026 | [8 empty] | 58
|  |  | Run Casing / Liner / Accessories Lainya | Run Casing and Cement | Run Casing and Cement : Run Casing / Liner / Accessories Lainya | 12d | PT | 0 |  |  | 1000 |  |  | 1015 | 16 | - |  |  | 1027 | [8 empty] | 59
|  |  | Cement Casing / Liner | Run Casing and Cement | Run Casing and Cement : Cement Casing / Liner | 12e | PT | 0 |  |  | 1000 |  |  |  | 0 | - |  |  | - | [8 empty] | 60
|  |  | Run Casing / Liner Problem (NPT) | Run Casing and Cement | Run Casing and Cement : Run Casing / Liner Problem (NPT) | 12f | NPT | 0 |  |  | 1000 |  |  |  | 0 | - |  |  | - | [8 empty] | 61
|  |  | Waiting on Cement | Wait on Cement | Wait on Cement : Waiting on Cement | 13a | PT | 52.5 | 16 |  | 1000 | 1016 |  |  | 0 | - |  |  | - | [8 empty] | 62
|  |  | Install / Remove or Change Wellhead and Riser (spool) include final casing cut / dressing stub | Nipple Up BOP | Nipple Up BOP : Install / Remove or Change Wellhead and Riser (spool) include final casing cut / dressing stub | 14a | PT | 5 | 17 |  | 1000 | 1017 |  |  | 0 | - |  |  | - | [8 empty] | 63
|  |  | N/U BOP, N/U & Install Diverter, Install Bell Nipple and Flowline or mandrel | Nipple Up BOP | Nipple Up BOP : N/U BOP, N/U & Install Diverter, Install Bell Nipple and Flowline or mandrel | 14b | PT | 3.5 | 18 |  | 1000 | 1018 |  |  | 0 | - |  |  | - | [8 empty] | 64
|  |  | N/D BOP, N/D Diverter, N/D Bell Nipple and Flowline or mandrel | Nipple Up BOP | Nipple Up BOP : N/D BOP, N/D Diverter, N/D Bell Nipple and Flowline or mandrel | 14c | PT | 4 | 19 |  | 1000 | 1019 |  | 1016 | 17 | - |  |  | - | [8 empty] | 65
|  |  | Other BOP Operation | Nipple Up BOP | Nipple Up BOP : Other BOP Operation | 14d | PT | 0 |  |  | 1000 |  |  | 1017 | 18 | - |  |  | - | [8 empty] | 66
|  |  | Function & Pressure Test of BOP's | Test BOP | Test BOP : Function & Pressure Test of BOP's | 15a | PT | 1 | 20 |  | 1000 | 1020 |  | 1018 | 19 | - |  |  | - | [8 empty] | 67
|  |  | Drill Stem Test | Drill Stem Test / WCT (Well Completion Test di PGE) | Drill Stem Test / WCT (Well Completion Test di PGE) : Drill Stem Test | 16a | PT | 0 |  |  | 1000 |  |  | 1019 | 20 | - |  |  | - | [8 empty] | 68
|  |  | Plug back - cement | Plug Back | Plug Back : Plug back - cement | 17a | PT | 0 |  |  | 1000 |  |  |  | 0 | - |  |  | - | [8 empty] | 69
|  |  | Coiled Tubing - Plug back | Plug Back | Plug Back : Coiled Tubing - Plug back | 17b | PT | 0 |  |  | 1000 |  |  | 1020 | 21 | - |  |  | - | [8 empty] | 70
|  |  | Plugback - other | Plug Back | Plug Back : Plugback - other | 17c | PT | 0 |  |  | 1000 |  |  |  | 0 | - |  |  | - | [8 empty] | 71
|  |  | Squeeze Planned Include Used Coiled Tubing | Squeeze Cement | Squeeze Cement : Squeeze Planned Include Used Coiled Tubing | 18a | PT | 18 | 21 |  | 1000 | 1021 |  |  | 0 | - |  |  | - | [8 empty] | 72
|  |  | Squeeze Unplanned (NPT) | Squeeze Cement | Squeeze Cement : Squeeze Unplanned (NPT) | 18b | PT | 0 |  |  | 1000 |  |  |  | 0 | - |  |  | - | [8 empty] | 73
|  |  | Fishing Operations (NPT) | Fishing | Fishing : Fishing Operations (NPT) | 19a | NPT | 0 |  |  | 1000 |  |  |  | 0 | - |  |  | - | [8 empty] | 74
|  |  | Preparation, Run & Set Wipstock | Open Windows | Open Windows : Preparation, Run & Set Wipstock | 20a | PT | 0 |  |  | 1000 |  |  | 1021 | 22 | - |  |  | - | [8 empty] | 75
|  |  | Mill / Cut Window c/w Mill Bit & Coilled Tubing | Open Windows | Open Windows : Mill / Cut Window c/w Mill Bit & Coilled Tubing | 20b | PT | 0 |  |  | 1000 |  |  |  | 0 | - |  |  | - | [8 empty] | 76
|  |  | 0 | Open Windows | Open Windows : 0 | #N/A | #N/A | 0 | [6 empty] | 0 | - |  |  | - | [8 empty] | 77
|  |  | Directional Services | Service Company (NPT) | Service Company (NPT) : Directional Services | 21a | NPT | 0 |  |  | 1000 |  |  |  | 0 | - |  |  | - | [8 empty] | 78
|  |  | Mud Services | Service Company (NPT) | Service Company (NPT) : Mud Services | 21b | NPT | 0 |  |  | 1000 |  |  |  | 0 | - |  |  | - | [8 empty] | 79
|  |  | MLU Services | Service Company (NPT) | Service Company (NPT) : MLU Services | 21c | NPT | 0 |  |  | 1000 |  |  |  | 0 | - |  |  | - | [8 empty] | 80
|  |  | UBD, MPD, Aerated Services | Service Company (NPT) | Service Company (NPT) : UBD, MPD, Aerated Services | 21d | NPT | 0 |  |  | 1000 |  |  |  | 0 | - |  |  | - | [8 empty] | 81
|  |  | Casing Drilling Services | Service Company (NPT) | Service Company (NPT) : Casing Drilling Services | 21e | NPT | 0 |  |  | 1000 |  |  |  | 0 | - |  |  | - | [8 empty] | 82
|  |  | Cementing Services | Service Company (NPT) | Service Company (NPT) : Cementing Services | 21f | NPT | 0 |  |  | 1000 |  |  |  | 0 | - |  |  | - | [8 empty] | 83
|  |  | Down Hole & Surface Services | Service Company (NPT) | Service Company (NPT) : Down Hole & Surface Services | 21g | NPT | 0 |  |  | 1000 |  |  |  | 0 | - |  |  | - | [8 empty] | 84
|  |  | Coiled Tubing Services | Service Company (NPT) | Service Company (NPT) : Coiled Tubing Services | 21h | NPT | 0 |  |  | 1000 |  |  |  | 0 | - |  |  | - | [8 empty] | 85
|  |  | Wireline Services | Service Company (NPT) | Service Company (NPT) : Wireline Services | 21i | NPT | 0 |  |  | 1000 |  |  |  | 0 | - |  |  | - | [8 empty] | 86
|  |  | Slick Line Services | Service Company (NPT) | Service Company (NPT) : Slick Line Services | 21j | NPT | 0 |  |  | 1000 |  |  |  | 0 | - |  |  | - | [8 empty] | 87
|  |  | RTO Services | Service Company (NPT) | Service Company (NPT) : RTO Services | 21k | NPT | 0 |  |  | 1000 |  |  |  | 0 | - |  |  | - | [8 empty] | 88
|  |  | Tubular Services | Service Company (NPT) | Service Company (NPT) : Tubular Services | 21l | NPT | 0 |  |  | 1000 |  |  |  | 0 | - |  |  | - | [8 empty] | 89
|  |  | Well Head & X-Mastree Services | Service Company (NPT) | Service Company (NPT) : Well Head & X-Mastree Services | 21m | NPT | 0 |  |  | 1000 |  |  |  | 0 | - |  |  | - | [8 empty] | 90
|  |  | Solid Control Services (Pihak Ketiga) | Service Company (NPT) | Service Company (NPT) : Solid Control Services (Pihak Ketiga) | 21n | NPT | 0 |  |  | 1000 |  |  |  | 0 | - |  |  | - | [8 empty] | 91
|  |  | Waste Management Services | Service Company (NPT) | Service Company (NPT) : Waste Management Services | 21o | NPT | 0 |  |  | 1000 |  |  |  | 0 | - |  |  | - | [8 empty] | 92
|  |  | H2S Services | Service Company (NPT) | Service Company (NPT) : H2S Services | 21p | NPT | 0 |  |  | 1000 |  |  |  | 0 | - |  |  | - | [8 empty] | 93
|  |  | Stimulation Services | Service Company (NPT) | Service Company (NPT) : Stimulation Services | 21q | NPT | 0 |  |  | 1000 |  |  |  | 0 | - |  |  | - | [8 empty] | 94
|  |  | Marine Support Services | Service Company (NPT) | Service Company (NPT) : Marine Support Services | 21r | NPT | 0 |  |  | 1000 |  |  |  | 0 | - |  |  | - | [8 empty] | 95
|  |  | Transportation Services | Service Company (NPT) | Service Company (NPT) : Transportation Services | 21s | NPT | 0 |  |  | 1000 |  |  |  | 0 | - |  |  | - | [8 empty] | 96
|  |  | Others Services | Service Company (NPT) | Service Company (NPT) : Others Services | 21t | NPT | 0 |  |  | 1000 |  |  |  | 0 | - |  |  | - | [8 empty] | 97
|  |  | Material Problems | Others NPT | Others NPT : Material Problems | 22a | NPT | 0 |  |  | 1000 |  |  |  | 0 | - |  |  | - | [8 empty] | 98
|  |  | Sosial Issue | Others NPT | Others NPT : Sosial Issue | 22b | NPT | 0 |  |  | 1000 |  |  |  | 0 | - |  |  | - | [8 empty] | 99
|  |  | Evironment Issue | Others NPT | Others NPT : Evironment Issue | 22c | NPT | 0 |  |  | 1000 |  |  |  | 0 | - |  |  | - | [8 empty] | 100
|  |  | Location Problem | Others NPT | Others NPT : Location Problem | 22d | NPT | 0 |  |  | 1000 |  |  |  | 0 | - |  |  | - | [8 empty] | 101
|  |  | Logistics Problem | Others NPT | Others NPT : Logistics Problem | 22e | NPT | 0 |  |  | 1000 |  |  |  | 0 | - |  |  | - | [8 empty] | 102
|  |  | Regulatory problems | Others NPT | Others NPT : Regulatory problems | 22f | NPT | 0 |  |  | 1000 |  |  |  | 0 | - |  |  | - | [8 empty] | 103
|  |  | Other Problem Time | Others NPT | Others NPT : Other Problem Time | 22g | NPT | 0 |  |  | 1000 |  |  |  | 0 | - |  |  | -
|  |  | Waiting on Weather | Uncontrol Situation | Uncontrol Situation : Waiting on Weather | 23a | PT | 5 | 22 |  | 1000 | 1022 |  |  | 0 | - |  |  | -
|  |  | Force Majure | Uncontrol Situation | Uncontrol Situation : Force Majure | 23b | PT | 0 |  |  | 1000 |  |  |  | 0 | - |  |  | -
|  |  | Tunggu Hari Terang | Uncontrol Situation | Uncontrol Situation : Tunggu Hari Terang | 23c | PT | 0 |  |  | 1000 |  |  |  | 0 | - |  |  | -
|  |  | Kick Drill, Medivac drill, Pit drill, H2S Drill, etc | Drills | Drills : Kick Drill, Medivac drill, Pit drill, H2S Drill, etc | 24a | PT | 0 |  |  | 1000 |  |  | 1022 | 23 | - |  |  | -
|  |  | Cased hole logging | Cased Hole Logging & Perforating | Cased Hole Logging & Perforating : Cased hole logging | 25a | PT | 0 |  |  | 1000 |  |  |  | 0 | - |  |  | -
|  |  | Perforating | Cased Hole Logging & Perforating | Cased Hole Logging & Perforating : Perforating | 25b | PT | 0 |  |  | 1000 |  |  |  | 0 | - |  |  | -
|  |  | Running / pulling Scraper | Trips | Trips : Running / pulling Scraper | 26a | PT | 24 | 23 |  | 1000 | 1023 |  |  | 0 | - |  |  | -
|  |  | Running / pulling Production Tubing (Tubing Trips) | Trips | Trips : Running / pulling Production Tubing (Tubing Trips) | 26b | PT | 54 | 24 |  | 1000 | 1024 |  |  | 0 | - |  |  | -
|  |  | Test / Presure test production tubing | Trips | Trips : Test / Presure test production tubing | 26c | PT | 20 | 25 |  | 1000 | 1025 |  |  | 0 | - |  |  | -
|  |  | Stimulation/Fracturing/Unloading/Production Treatment | Stimulation | Stimulation : Stimulation/Fracturing/Unloading/Production Treatment | 27a | PT | 11.5 | 26 |  | 1000 | 1026 |  | 1023 | 24 | - |  |  | -
|  |  | Swabbing Well | Swabbing | Swabbing : Swabbing Well | 28a | PT | 0 |  |  | 1000 |  |  | 1024 | 25 | - |  |  | -
|  |  | Well Testing | Production Test | Production Test : Well Testing | 29a | PT | 35 | 27 |  | 1000 | 1027 |  | 1025 | 26 | - |  |  | -
|  |  | N/U & N/D | X-Mastree | X-Mastree : N/U & N/D | 30a | PT | 0 |  |  | 1000 |  |  | 1026 | 27 | - |  |  | -
|  |  | Tree Pressure Testing | X-Mastree | X-Mastree : Tree Pressure Testing | 30b | NPT | 0 |  |  | 1000 |  |  |  | 0 | - |  |  | -
|  |  | 0 | X-Mastree | X-Mastree : 0 | #N/A | #N/A | 0 | [5 empty] | 1027 | 28 | - |  |  | -
|  |  | 0 | X-Mastree | X-Mastree : 0 | #N/A | #N/A | 0 | [6 empty] | 0 | - |  |  | -
|  |  | 0 | X-Mastree | X-Mastree : 0 | #N/A | #N/A | 0 | [6 empty] | 0 | - |  |  | -
|  |  | 0 | X-Mastree | X-Mastree : 0 | #N/A | #N/A | 0 | [6 empty] | 0 | - |  |  | -
|  |  | 0 | X-Mastree | X-Mastree : 0 | #N/A | #N/A | 0 | [6 empty] | 0 | - |  |  | -
|  |  | 0 | X-Mastree | X-Mastree : 0 | #N/A | #N/A | 0 | [6 empty] | 0 | - |  |  | -
|  |  | 0 | X-Mastree | X-Mastree : 0 | #N/A | #N/A | 0 | [6 empty] | 0 | - |  |  | -
|  |  | 0 | X-Mastree | X-Mastree : 0 | #N/A | #N/A | 0 | [6 empty] | 0 | - |  |  | -
|  |  | 0 | X-Mastree | X-Mastree : 0 | #N/A | #N/A | 0 | [6 empty] | 0 | - |  |  | -
|  |  | 0 | X-Mastree | X-Mastree : 0 | #N/A | #N/A | 0 | [6 empty] | 0 | - |  |  | -
|  |  | 0 | X-Mastree | X-Mastree : 0 | #N/A | #N/A | 0 | [6 empty] | 0 | - |  |  | -
|  |  | 0 | X-Mastree | X-Mastree : 0 | #N/A | #N/A | 0 | [6 empty] | 0 | - |  |  | -
|  |  | 0 | X-Mastree | X-Mastree : 0 | #N/A | #N/A | 0 | [6 empty] | 0 | - |  |  | -
|  |  | 0 | X-Mastree | X-Mastree : 0 | #N/A | #N/A | 0 | [6 empty] | 0 | - |  |  | -
|  |  | 0 | X-Mastree | X-Mastree : 0 | #N/A | #N/A | 0 | [6 empty] | 0 | - |  |  | -
|  |  | 0 | X-Mastree | X-Mastree : 0 | #N/A | #N/A | 0 | [6 empty] | 0 | - |  |  | -
|  |  | 0 | X-Mastree | X-Mastree : 0 | #N/A | #N/A | 0 | [6 empty] | 0 | - |  |  | -
|  |  | 0 | X-Mastree | X-Mastree : 0 | #N/A | #N/A | 0 | [6 empty] | 0 | - |  |  | -
|  |  | 0 | X-Mastree | X-Mastree : 0 | #N/A | #N/A | 0 | [6 empty] | 0 | - |  |  | -
|  |  | 0 | X-Mastree | X-Mastree : 0 | #N/A | #N/A | 0 | [6 empty] | 0 | - |  |  | -
|  |  | 0 | X-Mastree | X-Mastree : 0 | #N/A | #N/A | 0 | [6 empty] | 0 | - |  |  | -
|  |  | 0 | X-Mastree | X-Mastree : 0 | #N/A | #N/A | 0 | [6 empty] | 0 | - |  |  | -
|  |  | 0 | X-Mastree | X-Mastree : 0 | #N/A | #N/A | 0 | [6 empty] | 0 | - |  |  | -
|  |  | 0 | X-Mastree | X-Mastree : 0 | #N/A | #N/A | 0 | [6 empty] | 0 | - |  |  | -
|  |  | 0 | X-Mastree | X-Mastree : 0 | #N/A | #N/A | 0 | [6 empty] | 0 | - |  |  | -
|  |  | 0 | X-Mastree | X-Mastree : 0 | #N/A | #N/A | 0 | [6 empty] | 0 | - |  |  | -
|  |  | 0 | X-Mastree | X-Mastree : 0 | #N/A | #N/A | 0 | [6 empty] | 0 | - |  |  | -
|  |  | 0 | X-Mastree | X-Mastree : 0 | #N/A | #N/A | 0 | [6 empty] | 0 | - |  |  | -
|  |  | 0 | X-Mastree | X-Mastree : 0 | #N/A | #N/A | 0 | [6 empty] | 0 | - |  |  | -
|  |  | 0 | X-Mastree | X-Mastree : 0 | #N/A | #N/A | 0 | [6 empty] | 0 | - |  |  | -
|  |  | 0 | X-Mastree | X-Mastree : 0 | #N/A | #N/A | 0 | [6 empty] | 0 | - |  |  | -
|  |  | 0 | X-Mastree | X-Mastree : 0 | #N/A | #N/A | 0 | [6 empty] | 0 | - |  |  | -
|  |  | 0 | X-Mastree | X-Mastree : 0 | #N/A | #N/A | 0 | [6 empty] | 0 | - |  |  | -
|  |  | 0 | X-Mastree | X-Mastree : 0 | #N/A | #N/A | 0 | [6 empty] | 0 | - |  |  | -
|  |  | 0 | X-Mastree | X-Mastree : 0 | #N/A | #N/A | 0 | [6 empty] | 0 | - |  |  | -
|  |  | 0 | X-Mastree | X-Mastree : 0 | #N/A | #N/A | 0 | [6 empty] | 0 | - |  |  | -
|  |  | 0 | X-Mastree | X-Mastree : 0 | #N/A | #N/A | 0 | [6 empty] | 0 | - |  |  | -
|  |  | 0 | X-Mastree | X-Mastree : 0 | #N/A | #N/A | 0 | [6 empty] | 0 | - |  |  | -
|  |  | 0 | X-Mastree | X-Mastree : 0 | #N/A | #N/A | 0 | [6 empty] | 0 | - |  |  | -
|  |  | 0 | X-Mastree | X-Mastree : 0 | #N/A | #N/A | 0 | [6 empty] | 0 | - |  |  | -
|  |  | 0 | X-Mastree | X-Mastree : 0 | #N/A | #N/A | 0 | [6 empty] | 0 | - |  |  | -
|  |  | 0 | X-Mastree | X-Mastree : 0 | #N/A | #N/A | 0 | [6 empty] | 0 | - |  |  | -
|  |  | 0 | X-Mastree | X-Mastree : 0 | #N/A | #N/A | 0 | [6 empty] | 0 | - |  |  | -
|  |  | 0 | X-Mastree | X-Mastree : 0 | #N/A | #N/A | 0 | [6 empty] | 0 | - |  |  | -
|  |  | 0 | X-Mastree | X-Mastree : 0 | #N/A | #N/A | 0 | [6 empty] | 0 | - |  |  | -
|  |  | 0 | X-Mastree | X-Mastree : 0 | #N/A | #N/A | 0 | [6 empty] | 0 | - |  |  | -
|  |  | 0 | X-Mastree | X-Mastree : 0 | #N/A | #N/A | 0 | [6 empty] | 0 | - |  |  | -
|  |  | 0 | X-Mastree | X-Mastree : 0 | #N/A | #N/A | 0 | [6 empty] | 0 | - |  |  | -
|  |  | 0 | X-Mastree | X-Mastree : 0 | #N/A | #N/A | 0 | [6 empty] | 0 | - |  |  | -
|  |  | 0 | X-Mastree | X-Mastree : 0 | #N/A | #N/A | 0 | [6 empty] | 0 | - |  |  | -
|  |  | 0 | X-Mastree | X-Mastree : 0 | #N/A | #N/A | 0 | [6 empty] | 0 | - |  |  | -
|  |  | 0 | X-Mastree | X-Mastree : 0 | #N/A | #N/A | 0 | [6 empty] | 0 | - |  |  | -
|  |  | 0 | X-Mastree | X-Mastree : 0 | #N/A | #N/A | 0 | [6 empty] | 0 | - |  |  | -
|  |  | 0 | X-Mastree | X-Mastree : 0 | #N/A | #N/A | 0 | [6 empty] | 0 | - |  |  | -
|  |  | 0 | X-Mastree | X-Mastree : 0 | #N/A | #N/A | 0 | [6 empty] | 0 | - |  |  | -
|  |  | 0 | X-Mastree | X-Mastree : 0 | #N/A | #N/A | 0 | [6 empty] | 0 | - |  |  | -
|  |  | 0 | X-Mastree | X-Mastree : 0 | #N/A | #N/A | 0 | [6 empty] | 0 | - |  |  | -
|  |  | 0 | X-Mastree | X-Mastree : 0 | #N/A | #N/A | 0 | [6 empty] | 0 | - |  |  | -
|  |  | 0 | X-Mastree | X-Mastree : 0 | #N/A | #N/A | 0 | [6 empty] | 0 | - |  |  | -
|  |  | 0 | X-Mastree | X-Mastree : 0 | #N/A | #N/A | 0 | [6 empty] | 0 | - |  |  | -
|  |  | 0 | X-Mastree | X-Mastree : 0 | #N/A | #N/A | 0 | [6 empty] | 0 | - |  |  | -
|  |  | 0 | X-Mastree | X-Mastree : 0 | #N/A | #N/A | 0 | [6 empty] | 0 | - |  |  | -
|  |  | 0 | X-Mastree | X-Mastree : 0 | #N/A | #N/A | 0 | [6 empty] | 0 | - |  |  | -
|  |  | 0 | X-Mastree | X-Mastree : 0 | #N/A | #N/A | 0 | [6 empty] | 0 | - |  |  | -
|  |  | 0 | X-Mastree | X-Mastree : 0 | #N/A | #N/A | 0 | [6 empty] | 0 | - |  |  | -
|  |  | 0 | X-Mastree | X-Mastree : 0 | #N/A | #N/A | 0 | [6 empty] | 0 | - |  |  | -
|  |  | 0 | X-Mastree | X-Mastree : 0 | #N/A | #N/A | 0 | [6 empty] | 0 | - |  |  | -
|  |  | 0 | X-Mastree | X-Mastree : 0 | #N/A | #N/A | 0 | [6 empty] | 0 | - |  |  | -
|  |  | 0 | X-Mastree | X-Mastree : 0 | #N/A | #N/A | 0 | [6 empty] | 0 | - |  |  | -
|  |  | 0 | X-Mastree | X-Mastree : 0 | #N/A | #N/A | 0 | [6 empty] | 0 | - |  |  | -
|  |  | 0 | X-Mastree | X-Mastree : 0 | #N/A | #N/A | 0 | [6 empty] | 0 | - |  |  | -
|  |  | 0 | X-Mastree | X-Mastree : 0 | #N/A | #N/A | 0 | [6 empty] | 0 | - |  |  | -
|  |  | 0 | X-Mastree | X-Mastree : 0 | #N/A | #N/A | 0 | [6 empty] | 0 | - |  |  | -
|  |  | 0 | X-Mastree | X-Mastree : 0 | #N/A | #N/A | 0 | [6 empty] | 0 | - |  |  | -
|  |  | 0 | X-Mastree | X-Mastree : 0 | #N/A | #N/A | 0 | [6 empty] | 0 | - |  |  | -
|  |  | 0 | X-Mastree | X-Mastree : 0 | #N/A | #N/A | 0 | [6 empty] | 0 | - |  |  | -
|  |  | 0 | X-Mastree | X-Mastree : 0 | #N/A | #N/A | 0 | [6 empty] | 0 | - |  |  | -
|  |  | 0 | X-Mastree | X-Mastree : 0 | #N/A | #N/A | 0 | [6 empty] | 0 | - |  |  | -
|  |  | 0 | X-Mastree | X-Mastree : 0 | #N/A | #N/A | 0 | [6 empty] | 0 | - |  |  | -
|  |  | 0 | X-Mastree | X-Mastree : 0 | #N/A | #N/A | 0 | [6 empty] | 0 | - |  |  | -
|  |  | 0 | X-Mastree | X-Mastree : 0 | #N/A | #N/A | 0 | [6 empty] | 0 | - |  |  | -
|  |  | 0 | X-Mastree | X-Mastree : 0 | #N/A | #N/A | 0 | [6 empty] | 0 | - |  |  | -
|  |  | 0 | X-Mastree | X-Mastree : 0 | #N/A | #N/A | 0 | [6 empty] | 0 | - |  |  | -
|  |  | 0 | X-Mastree | X-Mastree : 0 | #N/A | #N/A | 0 | [6 empty] | 0 | - |  |  | -
|  |  | 0 | X-Mastree | X-Mastree : 0 | #N/A | #N/A | 0 | [6 empty] | 0 | - |  |  | -
|  |  | 0 | X-Mastree | X-Mastree : 0 | #N/A | #N/A | 0 | [6 empty] | 0 | - |  |  | -
|  |  | 0 | X-Mastree | X-Mastree : 0 | #N/A | #N/A | 0 | [6 empty] | 0 | - |  |  | -
|  |  | 0 | X-Mastree | X-Mastree : 0 | #N/A | #N/A | 0 | [6 empty] | 0 | - |  |  | -
|  |  | 0 | X-Mastree | X-Mastree : 0 | #N/A | #N/A | 0 | [6 empty] | 0 | - |  |  | -
|  |  | 0 | X-Mastree | X-Mastree : 0 | #N/A | #N/A | 0 | [6 empty] | 0 | - |  |  | -
|  |  | 0 | X-Mastree | X-Mastree : 0 | #N/A | #N/A | 0 | [6 empty] | 0 | - |  |  | -
|  |  | 0 | X-Mastree | X-Mastree : 0 | #N/A | #N/A | 0 | [6 empty] | 0 | - |  |  | -
|  |  | 0 | X-Mastree | X-Mastree : 0 | #N/A | #N/A | 0 | [6 empty] | 0 | - |  |  | -
|  |  | 0 | X-Mastree | X-Mastree : 0 | #N/A | #N/A | 0 | [6 empty] | 0 | - |  |  | -
|  |  | 0 | X-Mastree | X-Mastree : 0 | #N/A | #N/A | 0 | [6 empty] | 0 | - |  |  | -
|  |  | 0 | X-Mastree | X-Mastree : 0 | #N/A | #N/A | 0 | [6 empty] | 0 | - |  |  | -
|  |  | 0 | X-Mastree | X-Mastree : 0 | #N/A | #N/A | 0 | [6 empty] | 0 | - |  |  | -
|  |  | 0 | X-Mastree | X-Mastree : 0 | #N/A | #N/A | 0 | [6 empty] | 0 | - |  |  | -
|  |  | 0 | X-Mastree | X-Mastree : 0 | #N/A | #N/A | 0 | [6 empty] | 0 | - |  |  | -
|  |  | 0 | X-Mastree | X-Mastree : 0 | #N/A | #N/A | 0 | [6 empty] | 0 | - |  |  | -
|  |  | 0 | X-Mastree | X-Mastree : 0 | #N/A | #N/A | 0 | [6 empty] | 0 | - |  |  | -
|  |  | 0 | X-Mastree | X-Mastree : 0 | #N/A | #N/A | 0 | [6 empty] | 0 | - |  |  | -
|  |  | 0 | X-Mastree | X-Mastree : 0 | #N/A | #N/A | 0 | [6 empty] | 0 | - |  |  | -
|  |  | 0 | X-Mastree | X-Mastree : 0 | #N/A | #N/A | 0 | [6 empty] | 0 | - |  |  | -
|  |  | 0 | X-Mastree | X-Mastree : 0 | #N/A | #N/A | 0 | [6 empty] | 0 | - |  |  | -
-
-
-
-
-
-
-
-
-
[19 empty] | - |  |  | 0
[19 empty] | - |  |  | 0
[19 empty] | - |  |  | 0
[19 empty] | - |  |  | 0
[19 empty] | - |  |  | 0
[19 empty] | - |  |  | 0
[19 empty] | - |  |  | 0
[19 empty] | - |  |  | 0
[19 empty] | - |  |  | 0
[19 empty] | - |  |  | 0
[19 empty] | - |  |  | 0
[19 empty] | - |  |  | 0
[19 empty] | - |  |  | 0
[19 empty] | - |  |  | 0
[19 empty] | - |  |  | 0
[19 empty] | - |  |  | 0
[19 empty] | - |  |  | 0
[19 empty] | - |  |  | 0
[19 empty] | - |  |  | 0
[19 empty] | - |  |  | 0
[19 empty] | - |  |  | 0
[19 empty] | - |  |  | 0
[19 empty] | 0 |  |  | 0
[19 empty] | 0 |  |  | 0
[19 empty] | 0 |  |  | 0
[19 empty] | 0 |  |  | 0
[19 empty] | 0 |  |  | 0
[19 empty] | 0 |  |  | 0
[19 empty] | 0 |  |  | 0
[19 empty] | 0 |  |  | 0
[19 empty] | 0 |  |  | 0
[19 empty] | 0 |  |  | 0
[19 empty] | 0 |  |  | 0
[19 empty] | 0 |  |  | 0
[19 empty] | 0 |  |  | 0
[19 empty] | 0 |  |  | 0
[19 empty] | 0 |  |  | 0
[19 empty] | 0 |  |  | 0
[19 empty] | 0 |  |  | 0
[19 empty] | 0 |  |  | 0
[19 empty] | 0 |  |  | 0
[19 empty] | 0 |  |  | 0
[19 empty] | 0 |  |  | 0
[19 empty] | 0 |  |  | 0
[19 empty] | 0 |  |  | 0
[19 empty] | 0 |  |  | 0
[19 empty] | 0 |  |  | 0
[19 empty] | 0 |  |  | 0
[19 empty] | 0 |  |  | 0
[19 empty] | 0 |  |  | 0
[19 empty] | 0 |  |  | 0
[19 empty] | 0 |  |  | 0
[19 empty] | 0 |  |  | 0
[19 empty] | 0 |  |  | 0
[19 empty] | 0 |  |  | 0
[19 empty] | 0 |  |  | 0
[19 empty] | 0 |  |  | 0
[19 empty] | 0 |  |  | 0
[19 empty] | 0 |  |  | 0
[19 empty] | 0 |  |  | 0
[19 empty] | 0 |  |  | 0
[19 empty] | 0 |  |  | 0
[19 empty] | 0 |  |  | 0
[19 empty] | 0 |  |  | 0
[19 empty] | 0 |  |  | 0
[19 empty] | 0 |  |  | 0
[19 empty] | 0 |  |  | 0
[19 empty] | 0 |  |  | 0
[19 empty] | 0 |  |  | 0
[19 empty] | 0 |  |  | 0
[19 empty] | 0 |  |  | 0
[19 empty] | 0 |  |  | 0
[19 empty] | 0 |  |  | 0
[19 empty] | 0 |  |  | 0
[19 empty] | 0 |  |  | 0
[19 empty] | 0 |  |  | 0
[19 empty] | 0 |  |  | 0
[19 empty] | 0 |  |  | 0
[19 empty] | 0 |  |  | 0
[19 empty] | 0 |  |  | 0
[19 empty] | 0 |  |  | 0
[19 empty] | 0 |  |  | 0
[19 empty] | 0 |  |  | 0
[19 empty] | 0 |  |  | 0
[19 empty] | 0 |  |  | 0
[19 empty] | 0 |  |  | 0
[19 empty] | 0 |  |  | 0
[19 empty] | 0 |  |  | 0
[19 empty] | 0 |  |  | 0
[19 empty] | 0 |  |  | 0
[19 empty] | 0 |  |  | 0
[19 empty] | 0 |  |  | 0
[19 empty] | 0 |  |  | 0
[19 empty] | 0 |  |  | 0
[19 empty] | 0 |  |  | 0
[19 empty] | 0 |  |  | 0
[19 empty] | 0 |  |  | 0
[19 empty] | 0 |  |  | 0
[19 empty] | 0 |  |  | 0
[19 empty] | 0 |  |  | 0
[19 empty] | 0 |  |  | 0
[19 empty] | 0 |  |  | 0
[19 empty] | 0 |  |  | 0
[19 empty] | 0 |  |  | 0
[19 empty] | 0 |  |  | 0
[19 empty] | 0 |  |  | 0
[19 empty] | 0 |  |  | 0
[19 empty] | 0 |  |  | 0
[19 empty] | 0 |  |  | 0
[19 empty] | 0 |  |  | 0
[19 empty] | 0 |  |  | 0
[19 empty] | 0 |  |  | 0
[19 empty] | 0 |  |  | 0
[19 empty] | 0 |  |  | 0
[19 empty] | 0 |  |  | 0
[19 empty] | 0 |  |  | 0
[19 empty] | 0 |  |  | 0
[19 empty] | 0 |  |  | 0
[19 empty] | 0 |  |  | 0
[19 empty] | 0 |  |  | 0
[19 empty] | 0 |  |  | 0
[19 empty] | 0 |  |  | 0
[19 empty] | 0 |  |  | 0
[19 empty] | 0 |  |  | 0
[19 empty] | 0 |  |  | 0
[19 empty] | 0 |  |  | 0
[19 empty] | 0 |  |  | 0
[19 empty] | 0 |  |  | 0
[19 empty] | 0 |  |  | 0
[19 empty] | 0 |  |  | 0
[19 empty] | 0 |  |  | 0
[19 empty] | 0 |  |  | 0
[19 empty] | 0 |  |  | 0
[19 empty] | 0 |  |  | 0
[19 empty] | 0 |  |  | 0
[19 empty] | 0 |  |  | 0
[19 empty] | 0 |  |  | 0
[19 empty] | 0 |  |  | 0
[19 empty] | 0 |  |  | 0
[19 empty] | 0 |  |  | 0
[19 empty] | 0 |  |  | 0
[19 empty] | 0 |  |  | 0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0

## 6_LESSON LEARN
PERFORMANCE EVALUATION BASED ON PERTAMINA CODE
STEP 1). INPUT PROBLEM & LESSON LEARN
| NON PRODUCTIVE TIME (NPT) | IADC | HOURS | PROBLEM SOLVING | LESSON LEARN
| Well Control Operations / Situation (NPT) | 2g | 0 |  |  |  | 0 |  | 1 | 8f
| Lossing Circ / Pumping LCM / Monitor Unplanned (NPT) | 2h | 0 |  |  |  | 0 |  | 2 | 8d
| Stuck Pipe Include Handling operations (NPT) | 2j | 0 |  |  |  | 0 |  | 3
| Wash / Reaming / Backreaming Unplanned (NPT) | 3b | 0 |  |  |  | 0 |  | 4
| Unplanned Circulate / Condition Mud | 5c | 0 |  |  |  | 0 |  | 5
| Repair Power System (NPT) | 8a | 0 |  |  |  | 0 |  | 6
| Repair Housting System (NPT) | 8b | 0 |  |  |  | 0 |  | 7
| Repair Cirulating System (NPT) | 8c | 0 |  |  |  | 0 |  | 8
| Repair Rotating System (NPT) | 8d | 3.5 |  |  | 3.5 | 1 | 2 | 9
| Repair Blow Out Preventer System (NPT) | 8e | 0 |  |  |  | 0 |  | 10
| Tubular Problem (NPT) | 8f | 8 |  |  | 8 | 2 | 1 | 11
| Personal Problem (NPT) | 8g | 0 |  |  |  | 0 |  | 12
| Wireline/Slick Line Job Unplanned (NPT) | 11d | 0 |  |  |  | 0 |  | 13
| Run Casing / Liner Problem (NPT) | 12f | 0 |  |  |  | 0 |  | 14
| Squeeze Unplanned (NPT) | 18b | 0 |  |  |  | 0 |  | 15
| Fishing Operations (NPT) | 19a | 0 |  |  |  | 0 |  | 16
| Directional Services | 21a | 0 |  |  |  | 0 |  | 17
| Mud Services | 21b | 0 |  |  |  | 0 |  | 18
| MLU Services | 21c | 0 |  |  |  | 0 |  | 19
| UBD, MPD, Aerated Services | 21d | 0 |  |  |  | 0 |  | 20
| Casing Drilling Services | 21e | 0 |  |  |  | 0 |  | 21
| Cementing Services | 21f | 0 |  |  |  | 0 |  | 22
| Down Hole & Surface Services | 21g | 0 |  |  |  | 0 |  | 23
| Coiled Tubing Services | 21h | 0 |  |  |  | 0 |  | 24
| Wireline Services | 21i | 0 |  |  |  | 0 |  | 25
| Slick Line Services | 21j | 0 |  |  |  | 0 |  | 26
| RTO Services | 21k | 0 |  |  |  | 0 |  | 27
| Tubular Services | 21l | 0 |  |  |  | 0 |  | 28
| Well Head & X-Mastree Services | 21m | 0 |  |  |  | 0 |  | 29
| Solid Control Services (Pihak Ketiga) | 21n | 0 |  |  |  | 0 |  | 30
| Waste Management Services | 21o | 0 |  |  |  | 0 |  | 31
| H2S Services | 21p | 0 |  |  |  | 0 |  | 32
| Stimulation Services | 21q | 0 |  |  |  | 0 |  | 33
| Marine Support Services | 21r | 0 |  |  |  | 0 |  | 34
| Transportation Services | 21s | 0 |  |  |  | 0 |  | 35
| Others Services | 21t | 0 |  |  |  | 0 |  | 36
| Material Problems | 22a | 0 |  |  |  | 0 |  | 37
| Sosial Issue | 22b | 0 |  |  |  | 0 |  | 38
| Evironment Issue | 22c | 0 |  |  |  | 0 |  | 39
| Location Problem | 22d | 0 |  |  |  | 0 |  | 40
| Logistics Problem | 22e | 0 |  |  |  | 0 |  | 41
| Regulatory problems | 22f | 0 |  |  |  | 0 |  | 42
| Other Problem Time | 22g | 0 |  |  |  | 0 |  | 43
[7 empty] | 0 |  | 44
[7 empty] | 0 |  | 45
[7 empty] | 0 |  | 46
[7 empty] | 0 |  | 47
[7 empty] | 0 |  | 48
[7 empty] | 0 |  | 49
[7 empty] | 0 |  | 50
[7 empty] | 0 |  | 51
[7 empty] | 0 |  | 52
[7 empty] | 0 |  | 53
[7 empty] | 0 |  | 54
[7 empty] | 0 |  | 55
[7 empty] | 0 |  | 56
[7 empty] | 0 |  | 57
[7 empty] | 0 |  | 58
[7 empty] | 0 |  | 59
| TOTAL NPT |  | 11.5
| PROSENTASE NPT (AFE VERSION) |  | 2.087%
STEP 2). THE SELECTION ONLY
HOW TO ADJUST ROWS TO PREVENT UNREAD
| STEP 2.1). KLIK TOMBOL "BLOCK TABLE BELOW" DISAMPING INI wuwu |  |  | BLOCK TABLE BELOW | D:\PPP\PPP 2023\SPA-034\SPA-034 FINAL SHOW\[23. (EP1012-Form-DSpv-05) Workover Time_24_SPA-034_09-02-2023.xlsx]6_LESSON LEARN
| STEP 2.2). ARAHKAN CURSOR PADA SALAH SATU ROW |  |  |  | [23. (EP1012-Form-DSpv-05) Workover Time_24_SPA-034_09-02-2023.xlsx]6_LESSON LEARN
| STEP 2.3). DOUBLE CLICK DAN SEMUA BARIS AKAN MENYESUAIKAN LEBARNYA SESUAI DENGAN ISI CELL MSG-MSG |  |  |  | [23. (EP1012-Form-DSpv-05) Workover Time_24_SPA-034_09-02-2023.xlsx]
| NON PRODUCTIVE TIME (NPT) | IADC | HOURS | PROBLEM SOLVING | LESSON LEARN
| Tubular Problem (NPT) | 8f | 8
| Repair Rotating System (NPT) | 8d | 3.5
STEP 3). THE GRAPH
In Progress
In Progress
In Progress
In Progress
In Progress
In Progress
In Progress
In Progress
In Progress

## BUDGET PPP)
MONITORING BUDGET PEMBORAN SUMUR SPA-034
AFE NO. |  | : 23-190-221-OO | [8 empty] | 6812.1951
BUDGET. |  | 470258.4928
SPUD DATE |  | 2023-01-17 19:00 | [7 empty] | 9198.5169
HARI |  | TANGGAL | PLAN |  |  | ACTUAL
|  |  | DAILY COST | CUMM COST | % REAL | DAILY COST | CUMM COST | % REAL
0 | 0 | 2023-01-16 19:00 | 0 | 0 | 0% |  | 0 | 0% |  | 1 | 4007.5601 |  |  |  | 281.3897 | 281.3897 | 36.2931 | [9 empty] | 4606.6326
1 | 4.5 | 2023-01-17 19:00 | 5272.33 | 5272.33 | 1.121% | 9198.5169 | 9198.5169 | 1.956% | 77734.9296 | 2 | 4007.5601 |  |  |  | 281.3897 | 281.3897 | 36.2931 | [9 empty] | 4606.6326
2 | 5.4983 | 2023-01-18 19:00 | 5272.33 | 10544.66 | 2.242% | 75004.0136 | 84202.5305 | 17.91% | 6467.6008 | 3 | 4007.5601 |  |  |  | 281.3897 | 281.3897 | 36.2931 | [9 empty] | 4606.6326
3 | 6.4965 | 2023-01-19 19:00 | 5272.33 | 15816.99 | 3.363% | 6467.6008 | 90670.1313 | 19.28% | 6467.6008 | 1 | 39324.3243 | 2967.9997 | 5138.693 | 6335.1628 | 281.3897 | 281.3897 | 36.2931 | 62.5963 | 119.3788 | 112.1438 | 4000.5292 | 4915.5405 | 266.8039 | 1137.807 | 289.3054 | 1894.1567 | 67163.514
4 | 7.4948 | 2023-01-20 19:00 | 70589.09 | 86406.08 | 18.37% | 6467.6008 | 97137.7322 | 20.66% | 6467.6008 | 2 | 4350.0874 |  | 5138.693 |  | 281.3897 | 281.3897 | 36.2931 | 62.5963 | 119.3788 | 112.1438 |  |  | 266.8039 | 1137.807 | 289.3054 |  | 12075.8882
5 | 8.4931 | 2023-01-21 19:00 | 11540.41 | 97946.49 | 20.83% | 6467.6008 | 103605.333 | 22.03% | 6467.6008 | 3 | 10000 |  | 5138.693 |  | 281.3897 | 281.3897 | 36.2931 | 62.5963 | 119.3788 | 112.1438 |  |  | 266.8039 | 1137.807 | 289.3054 |  | 17725.8007
6 | 9.4913 | 2023-01-22 19:00 | 19190.32 | 117136.81 | 24.91% | 6467.6008 | 110072.9338 | 23.41% | 6467.6008 | 4 |  |  | 5138.693 |  | 281.3897 | 281.3897 | 36.2931 | 62.5963 | 119.3788 | 112.1438 |  |  | 266.8039 | 1137.807 | 289.3054 |  | 7725.8007
7 | 10.4896 | 2023-01-23 19:00 | 7190.32 | 124327.13 | 26.44% | 25020.0408 | 135092.9747 | 28.73% | 25020.0408 | 5 | 21235.1351 |  | 5138.693 |  | 281.3897 | 281.3897 | 36.2931 | 62.5963 | 119.3788 | 112.1438 |  |  | 266.8039 | 1137.807 | 289.3054 |  | 28960.9359
8 | 11.4878 | 2023-01-24 19:00 | 17807.89 | 142135.02 | 30.22% | 4853.5806 | 139946.5552 | 29.76% | 4853.5806 | 6 |  |  | 5138.693 |  | 281.3897 | 281.3897 | 36.2931 | 62.5963 | 119.3788 | 112.1438 |  |  | 266.8039 | 1137.807 | 289.3054 |  | 7725.8007
9 | 12.4861 | 2023-01-25 19:00 | 38158.23 | 180293.25 | 38.34% | 13267.6008 | 153214.1561 | 32.58% | 13267.6008 | 7 | 30967.9054 |  | 5138.693 |  | 281.3897 | 281.3897 | 36.2931 | 62.5963 | 119.3788 | 112.1438 |  |  | 266.8039 | 1137.807 | 289.3054 |  | 38693.7061
10 | 13.4844 | 2023-01-26 19:00 | 7190.32 | 187483.57 | 39.87% | 9473.8752 | 162688.0312 | 34.6% | 9473.8752 | 8 | 12000 | 10814.1892 | 5138.693 |  | 281.3897 | 281.3897 | 36.2931 | 62.5963 | 119.3788 | 112.1438 |  |  | 266.8039 | 1137.807 | 289.3054 |  | 30539.9899
11 | 14.4826 | 2023-01-27 19:00 | 17190.32 | 204673.89 | 43.52% | 6733.04 | 169421.0713 | 36.03% | 6733.04 | 9 |  |  | 5138.693 |  | 281.3897 | 281.3897 | 36.2931 | 62.5963 | 119.3788 | 112.1438 |  |  | 266.8039 | 1137.807 | 289.3054 |  | 7725.8007
12 | 15.4809 | 2023-01-28 19:00 | 7190.32 | 211864.21 | 45.05% | 6733.04 | 176154.1113 | 37.46% | 6733.04 | 10 |  |  | 5138.693 |  | 281.3897 | 281.3897 | 36.2931 | 62.5963 | 119.3788 | 112.1438 |  |  | 266.8039 | 1137.807 | 289.3054 |  | 7725.8007
13 | 16.4792 | 2023-01-29 19:00 | 7190.32 | 219054.53 | 46.58% | 6733.04 | 182887.1513 | 38.89% | 6733.04 | 11 | 20421.4524 | 8188.7428 | 5138.693 | 15729.7297 | 281.3897 | 281.3897 | 36.2931 | 62.5963 | 119.3788 | 112.1438 |  |  | 266.8039 | 1137.807 | 289.3054 |  | 52065.7257
14 | 17.4774 | 2023-01-30 19:00 | 69871.42 | 288925.95 | 61.44% | 6733.04 | 189620.1913 | 40.32% | 6733.04 | 12 |  |  | 5138.693 |  | 281.3897 | 281.3897 | 36.2931 | 62.5963 | 119.3788 | 112.1438 |  |  | 266.8039 | 1137.807 | 289.3054 |  | 7725.8007
15 | 18.4757 | 2023-01-31 19:00 | 7190.32 | 296116.27 | 62.97% | 7723.52 | 197343.7114 | 41.96% | 7723.52 | 13 |  |  | 5138.693 |  | 281.3897 | 281.3897 | 36.2931 | 62.5963 | 119.3788 | 112.1438 |  |  | 266.8039 | 1137.807 | 289.3054 |  | 7725.8007
16 | 19.474 | 2023-02-01 19:00 | 7593.03 | 303709.3 | 64.58% | 14893.04 | 212236.7514 | 45.13% | 14893.04 | 14 | 18858.108 |  | 5138.693 |  | 281.3897 | 281.3897 | 36.2931 | 62.5963 | 119.3788 | 112.1438 |  |  | 266.8039 | 1137.807 | 289.3054 |  | 26583.9087
17 | 20.4722 | 2023-02-02 19:00 | 7190.32 | 310899.62 | 66.11% | 6733.04 | 218969.7914 | 46.56% | 6733.04 | 15 |  |  | 5138.693 |  | 281.3897 | 281.3897 | 36.2931 | 62.5963 | 119.3788 | 112.1438 |  |  | 266.8039 | 1137.807 | 289.3054 |  | 7725.8007
18 | 21.4705 | 2023-02-03 19:00 | 7190.32 | 318089.94 | 67.64% | 6842.5707 | 225812.3621 | 48.02% | 6842.5707 | 16 | 54000 |  | 5138.693 |  | 281.3897 | 281.3897 | 36.2931 | 62.5963 | 119.3788 | 112.1438 |  |  | 266.8039 | 1137.807 | 289.3054 |  | 61725.8007
19 | 22.4688 | 2023-02-04 19:00 | 61190.32 | 379280.26 | 80.65% | 6733.04 | 232545.4022 | 49.45% | 6733.04 | 17 |  |  | 5138.693 |  | 281.3897 | 281.3897 | 36.2931 | 62.5963 | 119.3788 | 112.1438 |  |  | 266.8039 | 1137.807 | 289.3054 |  | 7725.8007
20 | 23.467 | 2023-02-05 19:00 | 7190.32 | 386470.58 | 82.18% | 6835.9325 | 239381.3347 | 50.9% | 6835.9325 | 18 | 5941.9351 | 33096.7501 | 5138.693 |  | 281.3897 | 281.3897 | 36.2931 | 62.5963 | 119.3788 | 112.1438 |  |  | 266.8039 | 1137.807 | 289.3054 |  | 46764.4859
21 | 24.4653 | 2023-02-06 19:00 | 7190.32 | 393660.9 | 83.71% | 7097.8669 | 246479.2016 | 52.41% | 7097.8669 | 18.9 |  |  | 5138.693 |  | 281.3897 | 281.3897 | 36.2931 | 62.5963 | 119.3788 | 112.1438 |  |  | 266.8039 | 1137.807 | 289.3054 |  | 7725.8007
21.7 | 25.4635 | 2023-02-07 19:00 | 72589.98 | 466250.88 | 99.15% | 32049.6616 | 278528.8632 | 59.23% | 32049.6616 | 1 | 4007.5601 |  |  |  | 281.3897 | 281.3897 | 36.2931 | [9 empty] | 4606.6326
22.7 | 26.4618 | 2023-02-08 19:00 | 4007.56 | 470258.44 | 100% | 32968.09 | 311496.9532 | 66.24% | 32968.09 | [17 empty] | 470258.4928
| 27.4601 | 2023-02-09 19:00 |  |  |  | 5243.1752 | 316740.1284 | 67.35% | 5243.1752
[12 empty] | 5496.8032 | 19
289.3054
Formulas:
TANGGAL = [TANGGAL, row above]+1