## Instruction
DEPARTEMEN AFE
DIVISI RENCANA ANGGARAN
AFE DRILLING INPUT
Di dalam pengajuan project sumur (Bor maupun Workover), KKKS diwajibkan melampirkan AFE Drilling Input dengan urutan pengisian data sebagai berikut :
1. Drilling Program
2. Well Design & Schematic
3. Casing Design
4. Rig
5. BS19 Detail 1 & 2 (apabila terdapat lebih dari 5 Sumur di dalam AFE ini)
6. Drilling Input Summary
7. Form Biaya
8. Seluruh keterangan teknis dan biaya yang diisikan sebelumnya akan langsung terangkum di dalam Sheet Drilling Input Summary, Sheet Form Biaya, dan Sheet BS-19 sehingga KKKS dapat langsung mencetak Budget Schedule 19
9. Dalam Sheet Actual Cost Summary, KKKS agar mencantumkan nilai actual untuk masing-masing pekerjaan sumur, hal ini diharapkan dapat mempermudah dan mempercepat proses Close Out

## Source (hidden)
Basin | Location | Product | Program | Project | Welltype | Wellsubtype | Welldesign | Core Type | Completion Type | Trajectory | Mudtype | Rigtype | Righp | proposedAFE | Oh No | AFE |  | Duration of Project (days) | Proposed | TRAJECTORY | CASING | DEPTH RANGE (ft)
Banggai Basin | Onshore | Oil | Conventional | Drilling | Development | Wildcat | Slim Hole | 0 | Single | Vertical | Water Basemud | Land Rig | 250 | Proposed Original | Yes | NO AFE |  |  |  |  | (inch) | From | To
Barito Basin | Offshore | Gas | Unconventional | Workover | Exploration | Appraisal | Optical Slim | Side Wall Core | Double | Horizontal | Oil Basemud | Jack Up | 350 | Proposed Revised-1 | No | ACTIVITY ID |  | Moving |  | 1
Bintuni Basin |  | Other |  | Well Services |  | Injection | HPHT |  | Triple | Directional | Completion Fluid | Workover Rig | 450 | Proposed Revised-2 |  |  |  | Rig up |  | 2
Bonaparte Basin | [5 empty] | Disposal | Deviated |  |  |  |  | Swamp Barge Rig | 550 | Approved Original |  |  |  | Drilling |  | 3
Central Sumatra Basin | [5 empty] | Production | Other |  |  |  |  | HWU/Snubbing Unit | 700 | Approved Revised-1 |  |  |  | Coring |  | 4
East Java Basin | [5 empty] | Core Hole | [5 empty] | Semi Submersible | 750 | Approved Revised -2 |  |  |  | Test |  | 5
East Java Shelf | [5 empty] | Core Hole & Explo | [5 empty] | Drill Ship | 1000 | Historical |  |  |  | Completion
East Natuna Basin | [5 empty] | Pilot Hole | [6 empty] | 1500 |  |  |  |  | P&A
Greater Tarakan Basin | [12 empty] | 2000 |  |  |  |  | Rig down
Kutei Basin | [12 empty] | 3000
Malay Basin | [17 empty] | Total Rig days | [8 empty] | MINIMUM | MAXIMUM | AVERAGE
Meulaboh Basin | [20 empty] | DEPTH |  | 12000 | ftMD |  | DEPTH (ft)
Nias Basin | [17 empty] | Depth (ft) |  |  | RIG DAYS |  | 85.95 | day |  | RIG DAYS
North Seram Basin | [20 empty] | DRILLING DAYS |  | 83.05 | day |  | COST/FT
North Sumatra Basin | [11 empty] | proposedAFE | ShortName | prev | aft |  |  | Rate of Penetration (ROP) |  |  | RIG POWER [HP] |  | 3000 |  |  | COST/RIG DAY
Ombilin Basin | [11 empty] | Proposed Original | Proposed | Historical | Approved | OO | 1 |  |  |  | CONTRACT RIG |  | 59850 | $/day |  | PREPARATION (US$)
Paus-Ranai High | [11 empty] | Proposed Revised-1 | Proposed R1 | Approved OO | Approved R1 | R1 | 2
Salawati Basin | [11 empty] | Proposed Revised-2 | Proposed R2 | Approved R1 | Approved R2 | R2 | 3 |  |  |  | DESCRIPTION |  | PROPOSED | ESTIMATED | REMARKS
Sekak Ridge | [11 empty] | Approved Original | [8 empty] | PREPARATION |  | 672120 |  | using HISTORICAL DATA SUMMARY
Sengkang Basin | [11 empty] | Approved Revised-1 | [8 empty] | DRILLING COST* |  | 16079931
South New Guniea Basin | [11 empty] | Approved Revised -2 | [8 empty] | TOTAL COST |  | 16752051
South Sumatra Basin | [11 empty] | Historical
South Waropean Basin | [15 empty] | 2dig | idx
Sukang Basin | [10 empty] | Actual Selected / AFEstat | Proposed Original | Proposed | Historical | Approved | OO | 1 | [9 empty] | MINIMUM | MAXIMUM | AVERAGE
Sula Basin | [10 empty] | original ? | TRUE | [8 empty] | DEPTH |  | 12000 | ftMD |  | DEPTH (ft)
West Java Basin | [20 empty] | RIG DAYS |  | 85.95 | day |  | RIG DAYS
West Luconia Province | [20 empty] | DRILLING DAYS |  | 83.05 | day |  | COST/FT
West Natuna Basin | [20 empty] | RIG POWER [HP] |  | 3000 |  |  | COST/RIG DAY
[21 empty] | CONTRACT RIG |  | 59850 | $/day |  | PREPARATION (US$)
[21 empty] | DESCRIPTION |  | PROPOSED | ESTIMATED | REMARKS
[21 empty] | PREPARATION |  | 672120 |  | using HISTORICAL DATA SUMMARY
[21 empty] | DRILLING COST* |  | 16079931
[21 empty] | TOTAL COST |  | 16752051

## Remark
Kontrak
teknis
TL
Optimasi
Mengacu sumur lain atau quotation
Trip, RIH & cement casing, BOP Job, RIH bit, Run Scrapper, CHL, Perforation 1st target, N/D BOP & N/U X-Masstree. Production Test
Kill well, BOP Job, POOH RPP, Squeeze Job, DOC, Run scrapper, Perforation 2nd target, RIH RPP, Production test
Kill well, BOP Job, POOH RPP, Fracturing Job, RIH RPP, N/D BOP & N/U X-Masstree. Production Test

## Referensi Harga Kontrak PEP A2
REFERENSI HARGA DAN KONTRAK UNTUK MATERIAL DRILLING
PT. PERTAMINA EP ASSET 2
No. | Material | UoM | Harga Satuan Kontrak |  | Jenis Komoditas (APDN) | Kategori Barang | ACUAN PERJANJIAN / KONTRAK - PT. PERTAMINA EP (SUMATERA)
|  |  | USD | IDR |  |  | OA. / PO. | TKDN (%) | Perusahaan | Berlaku sd.
TANGIBLE MATERIAL
CASING
1 | 30" Stove Pipe (12 mm X 6 meter) | Joint | 0 | 28332000 | 1.b. Pipa Pemboran (OCTG) - Low Grade | Diwajibkan | 4650013705 | 53.07% | PT. KHI PIPE INDUSTRIES | 2022-07-19
2 | Casing 20 in, K-55, 94,0 PPF, BTC, ERW | Joint | 0 | 88850000 | 1.b. Pipa Pemboran (OCTG) - Low Grade | Diwajibkan | 4650014279 | 54.76% | PT. BERTIES SUKSES MAKMUR | 2022-05-19
3 | Casing 13 3/8 in, K-55, 61 PPF, BTC, R3 | Joint | 1438.1 | 0 | 1.b. Pipa Pemboran (OCTG) - Low Grade | Dimaksimalkan | 4650009465 | 15.77% | PT. BERTIES SUKSES MAKMUR | 2023-02-26
4 | Casing 13 3/8 in, K-55, 54,5 PPF, BTC, R3 | Joint | 1344.12 | 0 | 1.b. Pipa Pemboran (OCTG) - Low Grade | Dimaksimalkan | 4650009465 | 15.77% | PT. BERTIES SUKSES MAKMUR | 2023-02-26
5 | Casing 9 5/8 in, L-80, 47 PPF, BTC, R3 | Joint | 1760.11 | 0 | 1.a. Pipa Pemboran (OCTG) - High Grade | Dimaksimalkan | 4650014546 | 29.79% | KONS. PT. CITRA TUBINDO - PT. ELNUSA FABRIKASI K. | 2022-01-19
6 | Casing 9 5/8 in, N-80, 43.5 PPF, BTC, R3 | Joint | 1613.9 | 0 | 1.a. Pipa Pemboran (OCTG) - High Grade | Dimaksimalkan | 4650014546 | 29.79% | KONS. PT. CITRA TUBINDO - PT. ELNUSA FABRIKASI K. | 2022-01-19
7 | Casing 9 5/8 in, N-80, 40 PPF, BTC, R3 | Joint | 1483.16 | 0 | 1.a. Pipa Pemboran (OCTG) - High Grade | Dimaksimalkan | 4650014546 | 29.79% | KONS. PT. CITRA TUBINDO - PT. ELNUSA FABRIKASI K. | 2022-01-19
8 | Casing 9 5/8 in, K-55, 43.5 PPF, BTC, R3 | Joint | 1078.11 | 0 | 1.b. Pipa Pemboran (OCTG) - Low Grade | Dimaksimalkan | 4650009465 | 15.77% | PT. BERTIES SUKSES MAKMUR | 2023-02-26
9 | Casing 9 5/8 in, K-55, 40 PPF, BTC, R3 | Joint | 991.37 | 0 | 1.b. Pipa Pemboran (OCTG) - Low Grade | Dimaksimalkan | 4650009465 | 15.77% | PT. BERTIES SUKSES MAKMUR | 2023-02-26
10 | Casing 9 5/8 in, K-55, 36 PPF, BTC, R3 | Joint | 862.08 | 0 | 1.b. Pipa Pemboran (OCTG) - Low Grade | Dimaksimalkan | 4650009465 | 15.77% | PT. BERTIES SUKSES MAKMUR | 2023-02-26
11 | Casing 7 in, N-80, 29 PPF, BTC, R3 | Joint | 1079.71 | 0 | 1.a. Pipa Pemboran (OCTG) - High Grade | Dimaksimalkan | 4650014546 | 29.79% | KONS. PT. CITRA TUBINDO - PT. ELNUSA FABRIKASI K. | 2022-01-19
12 | Casing 7 in, N-80, 26 PPF, BTC, R3 | Joint | 964.47 | 0 | 1.a. Pipa Pemboran (OCTG) - High Grade | Dimaksimalkan | 4650014546 | 29.79% | KONS. PT. CITRA TUBINDO - PT. ELNUSA FABRIKASI K. | 2022-01-19
13 | Casing 7 in, N-80, 23 PPF, BTC, R3 | Joint | 844.92 | 0 | 1.a. Pipa Pemboran (OCTG) - High Grade | Dimaksimalkan | 4650014546 | 29.79% | KONS. PT. CITRA TUBINDO - PT. ELNUSA FABRIKASI K. | 2022-01-19
14 | Casing 7 in, K-55, 29 PPF, BTC, R3 | Joint | 637.76 | 0 | 1.b. Pipa Pemboran (OCTG) - Low Grade | Dimaksimalkan | 4650009465 | 15.77% | PT. BERTIES SUKSES MAKMUR | 2023-02-26
15 | Casing 7 in, K-55, 26 PPF, BTC, R3 | Joint | 571.78 | 0 | 1.b. Pipa Pemboran (OCTG) - Low Grade | Dimaksimalkan | 4650009465 | 15.77% | PT. BERTIES SUKSES MAKMUR | 2023-02-26
16 | Casing 7 in, K-55, 23 PPF, BTC, R3 | Joint | 505.23 | 0 | 1.b. Pipa Pemboran (OCTG) - Low Grade | Dimaksimalkan | 4650009465 | 15.77% | PT. BERTIES SUKSES MAKMUR | 2023-02-26
CASING ACCESSORIES
1 | Reamer Shoe 13 3/8 in | Pcs | 0 | 92500000 | 10. Barang lain-lain | Diwajibkan | 4650014088 | 52% | PT. ASTAJAYA NIRWIGHNATA | 2022-10-05
2 | Reamer Shoe 9 5/8 in | Pcs | 0 | 72500000 | 10. Barang lain-lain | Diwajibkan | 4650014088 | 61.75% | PT. ASTAJAYA NIRWIGHNATA | 2022-10-05
3 | Reamer Shoe 7 in | Pcs | 0 | 65900000 | 10. Barang lain-lain | Diwajibkan | 4650014088 | 60.46% | PT. ASTAJAYA NIRWIGHNATA | 2022-10-05
4 | Float Shoe 20 in | Pcs | 0 | 29000000 | 10. Barang lain-lain | Diwajibkan | 4650010723 | 47.78% | PT. SAGATRADE MURNI | 2022-01-07
5 | Float Shoe 13 3/8 in | Pcs | 0 | 11156500 | 10. Barang lain-lain | Diwajibkan | 4650010723 | 47.78% | PT. SAGATRADE MURNI | 2022-01-07
6 | Float Shoe 9 5/8 in | Pcs | 0 | 8360750 | 10. Barang lain-lain | Diwajibkan | 4650010723 | 47.78% | PT. SAGATRADE MURNI | 2022-01-07
7 | Float Shoe 7 in | Pcs | 0 | 5379500 | 10. Barang lain-lain | Diwajibkan | 4650010723 | 47.78% | PT. SAGATRADE MURNI | 2022-01-07
8 | Float Collar 13 3/8 in | Pcs | 0 | 11885250 | 10. Barang lain-lain | Diwajibkan | 4650010723 | 42.96% | PT. SAGATRADE MURNI | 2022-01-07
9 | Float Collar 9 5/8 in | Pcs | 0 | 10692750 | 10. Barang lain-lain | Diwajibkan | 4650010723 | 42.96% | PT. SAGATRADE MURNI | 2022-01-07
10 | Float Collar 7 in | Pcs | 0 | 6545500 | 10. Barang lain-lain | Diwajibkan | 4650010723 | 42.96% | PT. SAGATRADE MURNI | 2022-01-07
11 | DSCC 13 3/8 in | Pcs | 0 | 140000000 | 10. Barang lain-lain | Diwajibkan | 4650010723 | 43.18% | PT. SAGATRADE MURNI | 2022-01-07
12 | DSCC 9 5/8 in | Pcs | 0 | 120000000 | 10. Barang lain-lain | Diwajibkan | 4650010723 | 43.18% | PT. SAGATRADE MURNI | 2022-01-07
13 | DSCC 7 in | Pcs | 0 | 100000000 | 10. Barang lain-lain | Diwajibkan | 4650010723 | 43.18% | PT. SAGATRADE MURNI | 2022-01-07
14 | Liner Hanger 7 in x 9.5/8 in (Rotatable) | Pcs | 0 | 1020000000 | 10. Barang lain-lain | Diwajibkan | 4650011738 | 52.97% | PT. SAGATRADE MURNI | 2021-06-16
15 | Liner Hanger 4.1/2 in x 7 in (Rotatable) | Pcs | 0 | 890000000 | 10. Barang lain-lain | Diwajibkan | 4650011738 | 52.97% | PT. SAGATRADE MURNI | 2021-06-16
16 | ECP 13 3/8 in | set | 0 | 472500000 | 10. Barang lain-lain | Diwajibkan | 4650009942 | 41.13% | PT. SAGATRADE MURNI | 2022-05-19
17 | ECP 9 5/8 in | set | 0 | 405000000 | 10. Barang lain-lain | Diwajibkan | 4650009942 | 41.13% | PT. SAGATRADE MURNI | 2022-05-19
18 | ECP 7 in | set | 0 | 370500000 | 10. Barang lain-lain | Diwajibkan | 4650009942 | 41.13% | PT. SAGATRADE MURNI | 2022-05-19
TUBING
1 | Tubing 2 7/8 in, J-55, 6,5 PPF, EUE, R2 | Joint | 153.31 | 0 | 1.b. Pipa Pemboran (OCTG) - Low Grade | Dimaksimalkan | 4650009465 | 16.54% | PT. BERTIES SUKSES MAKMUR | 2023-02-26
2 | Tubing 3 1/2 in, N-80, 9,3 PPF, EUE, R2 | Joint | 317.71 | 0 | 1.a. Pipa Pemboran (OCTG) - High Grade | Diwajibkan | 4650011614 | 46.43% | PT. ELNUSA FABRIKASI KONSTRUKSI | 2021-05-05
3 | Tubing 2 7/8 in, N-80, 6,5 PPF, EUE, R2 | Joint | 233.32 | 0 | 1.a. Pipa Pemboran (OCTG) - High Grade | Diwajibkan | 4650011614 | 46.43% | PT. ELNUSA FABRIKASI KONSTRUKSI | 2021-05-05
4 | Tubing 2 3/8 in, N-80, 4,7 PPF, EUE, R2 | Joint | 171.42 | 0 | 1.a. Pipa Pemboran (OCTG) - High Grade | Diwajibkan | 4650011614 | 46.43% | PT. ELNUSA FABRIKASI KONSTRUKSI | 2021-05-05
5 | Pup Joint 2 7/8 in, N-80, 6,5 PPF, EUE, 2 Feet | Pcs | 0 | 1914687 | 10. Barang lain-lain | Dimaksimalkan | 4650010636 | 21.04% | PT. TRIDAYA ESA PAKARTI | 2021-12-29
6 | Pup Joint 2 7/8 in, N-80, 6,5 PPF, EUE, 4 Feet | Pcs | 0 | 2173687 | 10. Barang lain-lain | Dimaksimalkan | 4650010636 | 21.04% | PT. TRIDAYA ESA PAKARTI | 2021-12-29
7 | Pup Joint 2 7/8 in, N-80, 6,5 PPF, EUE, 6 Feet | Pcs | 0 | 2554687 | 10. Barang lain-lain | Dimaksimalkan | 4650010636 | 21.04% | PT. TRIDAYA ESA PAKARTI | 2021-12-29
8 | Pup Joint 2 7/8 in, N-80, 6,5 PPF, EUE, 8 Feet | Pcs | 0 | 2950687 | 10. Barang lain-lain | Dimaksimalkan | 4650010636 | 21.04% | PT. TRIDAYA ESA PAKARTI | 2021-12-29
WELL EQUIPMENT - SURFACE
1 | Wellhead , 13 5/8"-3M X 11"-3M X 7 1/16"-3M & 3 1/8"-3M CLASS BB | Set | 53490.5 | 0 | 7.a. Wellhead dan X-mas Tree - Darat | Diberdayakan | 4650012497 | 0% | PT. ALLOY MAS OILFIELD SERVICES | 2021-04-08
2 | Wellhead , 13 5/8"-3M X 11"-5M X 7 1/16"-5M & 3 1/8"-5M CLASS BB | Set | 66062.7 | 0 | 7.a. Wellhead dan X-mas Tree - Darat | Diberdayakan | 4650012497 | 0% | PT. ALLOY MAS OILFIELD SERVICES | 2021-04-08
3 | X-MasTree , 3 1/8"-3M X 2 1/16"-3M CLASS: BB | Set | 36838 | 0 | 7.a. Wellhead dan X-mas Tree - Darat | Diberdayakan | 4650012497 | 0% | PT. ALLOY MAS OILFIELD SERVICES | 2021-04-08
4 | X-MasTree , 3 1/8"-5M X 2 1/16"-5M CLASS: BB | Set | 37544 | 0 | 7.a. Wellhead dan X-mas Tree - Darat | Diberdayakan | 4650012497 | 0% | PT. ALLOY MAS OILFIELD SERVICES | 2021-04-08
WELL EQUIPMENT - SUBSURFACE
1 | MECH. PACKER 7', SG, L80, 20-26 PPF, 2.7/8", EUE | Pcs | 0 | 36000000 | 10. Barang lain-lain | Diwajibkan | 4650014415 | 49.79% | PT. SAGATRADE MURNI | 2022-12-29
2 | MECH. PACKER 7', DG, L80, 17-26 PPF, 2.7/8", EUE | Pcs | 0 | 72200000 | 10. Barang lain-lain | Diwajibkan | 4650014415 | 46.89% | PT. SAGATRADE MURNI | 2022-12-29
3 | MECH. PACKER 9.5/8', DG, L80, 40-47 PPF, 2.7/8" or 3.1/2", EUE | Pcs | 0 | 172200000 | 10. Barang lain-lain | Diwajibkan | 4650014415 | 46.89% | PT. SAGATRADE MURNI | 2022-12-29
OTHER TANGIBLE COST
1 | BRIDGE PLUG 7", WIRELINE, 275 DEG F, 23-29 PPF | Pcs | 0 | 35100000 | 10. Barang lain-lain | Non-APDN | 4650011524 | 0% | CV. KHARISMA INDAH (brand MOT Saga) | 2022-04-15
2 | BRIDGE PLUG 4.1/2", WIRELINE, 275 DEG F, 9.5-15.1 PPF | Pcs | 0 | 20300000 | 10. Barang lain-lain | Non-APDN | 4650011524 | 0% | CV. KHARISMA INDAH (brand MOT Saga) | 2022-04-15
INTANGIBLE MATERIAL
DRILL BITS
1 | PDC Bit 17 1/2 in, Soft to Med, 519S (Steel) | Pcs | 0 | 206870000 | 10. Barang lain-lain | Non-APDN | 4650010155 | 0% | PT. NATIONAL OIL VARCO (Reed Hycalog) | 2021-08-19
2 | PDC Bit 12 1/4 in, Soft to Med, 519S (Steel) | Pcs | 0 | 132753000 | 10. Barang lain-lain | Non-APDN | 4650010155 | 0% | PT. NATIONAL OIL VARCO (Reed Hycalog) | 2021-08-19
3 | PDC Bit 8 1/2 in, Soft to Med, 519S (Steel) | Pcs | 0 | 96585000 | 10. Barang lain-lain | Non-APDN | 4650010155 | 0% | PT. NATIONAL OIL VARCO (Reed Hycalog) | 2021-08-19
4 | PDC Bit 8 1/2 in, Soft to Med, 616M (Matrix) | Pcs | 0 | 152987900 | 10. Barang lain-lain | Non-APDN | 4650010155 | 0% | PT. NATIONAL OIL VARCO (Reed Hycalog) | 2021-08-19
6 | Rock Bit 36 in, IADC 135 | Pcs | 36800 | 0 | 10. Barang lain-lain | Non-APDN | 4650013711 | 0% | PT. MULIA GRAHA ABADI (Varel) | 2022-09-29
7 | Rock Bit 26 in, IADC 111 | Pcs | 14750 | 0 | 10. Barang lain-lain | Non-APDN | 4650013711 | 0% | PT. MULIA GRAHA ABADI (Varel) | 2022-09-29
8 | Rock Bit 17 1/2 in, IADC 135/ 137 | Pcs | 8547 | 0 | 10. Barang lain-lain | Non-APDN | 4650014257 | 0% | KONS. PT. IMECO INTER SARANA - PT. SMITH TOOLS INDONESIA | 2022-05-19
9 | Rock Bit 12 1/4 in, IADC 137 | Pcs | 6059 | 0 | 10. Barang lain-lain | Non-APDN | 4650014257 | 0% | KONS. PT. IMECO INTER SARANA - PT. SMITH TOOLS INDONESIA | 2022-05-19
10 | Rock Bit 12 1/4 in, IADC 217 | Pcs | 5748 | 0 | 10. Barang lain-lain | Non-APDN | 4650014257 | 0% | KONS. PT. IMECO INTER SARANA - PT. SMITH TOOLS INDONESIA | 2022-05-19
11 | Rock Bit 8 1/2 in, IADC 127/ 137 | Pcs | 3136 | 0 | 10. Barang lain-lain | Non-APDN | 4650014257 | 0% | KONS. PT. IMECO INTER SARANA - PT. SMITH TOOLS INDONESIA | 2022-05-19
12 | Rock Bit 8 1/2 in, IADC 217 | Pcs | 3100 | 0 | 10. Barang lain-lain | Non-APDN | 4650014257 | 0% | KONS. PT. IMECO INTER SARANA - PT. SMITH TOOLS INDONESIA | 2022-05-19
13 | Rock Bit 6 in, IADC 217 | Pcs | 2800 | 0 | 10. Barang lain-lain | Non-APDN | 4650014257 | 0% | KONS. PT. IMECO INTER SARANA - PT. SMITH TOOLS INDONESIA | 2022-05-19
CEMENTING
0 | Oil Well Cement (OWC) Class G | Sax | 0 | 111000 | 3. Lumpur Pemboran, semen, dan bahan kimia | Diwajibkan | 4650009703 | 88.61% | PT. SUPRANIAGA NUSANTARA | 2022-04-30
1 | Bottom Plug 13 3/8 in | Pcs | 0 | 7368200 | 10. Barang lain-lain | Diwajibkan | 4650010723 | 40.5% | PT. SAGATRADE MURNI | 2022-01-07
2 | Bottom Plug 9 5/8 in | Pcs | 0 | 3551100 | 10. Barang lain-lain | Diwajibkan | 4650010723 | 40.5% | PT. SAGATRADE MURNI | 2022-01-07
3 | Bottom Plug 7 in | Pcs | 0 | 1549000 | 10. Barang lain-lain | Diwajibkan | 4650010723 | 40.5% | PT. SAGATRADE MURNI | 2022-01-07
4 | Top Plug 13 3/8 in | Pcs | 0 | 6118000 | 10. Barang lain-lain | Diwajibkan | 4650010723 | 40.04% | PT. SAGATRADE MURNI | 2022-01-07
5 | Top Plug 9 5/8 in | Pcs | 0 | 2553600 | 10. Barang lain-lain | Diwajibkan | 4650010723 | 40.04% | PT. SAGATRADE MURNI | 2022-01-07
6 | Top Plug 7 in | Pcs | 0 | 1549000 | 10. Barang lain-lain | Diwajibkan | 4650010723 | 40.04% | PT. SAGATRADE MURNI | 2022-01-07
7 | Centralizer 20 in | Pcs | 0 | 957600 | 10. Barang lain-lain | Diwajibkan | 4650010723 | 51.52% | PT. SAGATRADE MURNI | 2022-01-07
8 | Centralizer 13 3/8 in | Pcs | 0 | 638400 | 10. Barang lain-lain | Diwajibkan | 4650010723 | 51.52% | PT. SAGATRADE MURNI | 2022-01-07
9 | Centralizer 9 5/8 in | Pcs | 0 | 42500 | 10. Barang lain-lain | Diwajibkan | 4650010723 | 51.52% | PT. SAGATRADE MURNI | 2022-01-07
10 | Stop Ring 20 in | Pcs | 0 | 186200 | 10. Barang lain-lain | Diwajibkan | 4650010723 | 59.79% | PT. SAGATRADE MURNI | 2022-01-07
11 | Stop Ring 13 3/8 in | Pcs | 0 | 146500 | 10. Barang lain-lain | Diwajibkan | 4650010723 | 59.79% | PT. SAGATRADE MURNI | 2022-01-07
12 | Stop Ring 9 5/8 in | Pcs | 0 | 119700 | 10. Barang lain-lain | Diwajibkan | 4650010723 | 59.79% | PT. SAGATRADE MURNI | 2022-01-07
13 | Centralizer 13 3/8 in For Reamer Shoe | Pcs | 0 | 1400000 | 10. Barang lain-lain | Diwajibkan | 4650014088 | 46.02% | PT. ASTAJAYA NIRWIGHNATA | 2022-10-05
14 | Centralizer 9 5/8 in For Reamer Shoe | Pcs | 0 | 980000 | 10. Barang lain-lain | Diwajibkan | 4650014088 | 46.02% | PT. ASTAJAYA NIRWIGHNATA | 2022-10-05
15 | Stop Ring 13 3/8 in For Reamer Shoe | Pcs | 0 | 440000 | 10. Barang lain-lain | Diwajibkan | 4650014088 | 45.43% | PT. ASTAJAYA NIRWIGHNATA | 2022-10-05
16 | Stop Ring 9 5/8 in For Reamer Shoe | Pcs | 0 | 345000 | 10. Barang lain-lain | Diwajibkan | 4650014088 | 45.43% | PT. ASTAJAYA NIRWIGHNATA | 2022-10-05
CEMENTING COMPLETION
1 | Centralizer 7 in | Pcs | 0 | 332500 | 10. Barang lain-lain | Diwajibkan | 4650010723 | 51.52% | PT. SAGATRADE MURNI | 2022-01-07
2 | Stop Ring 7 in | Pcs | 0 | 93100 | 10. Barang lain-lain | Diwajibkan | 4650010723 | 59.79% | PT. SAGATRADE MURNI | 2022-01-07
3 | Centralizer 7 in For Reamer Shoe | Pcs | 0 | 780000 | 10. Barang lain-lain | Diwajibkan | 4650014088 | 46.02% | PT. ASTAJAYA NIRWIGHNATA | 2022-10-05
4 | Stop Ring 7 in For Reamer Shoe | Pcs | 0 | 245000 | 10. Barang lain-lain | Diwajibkan | 4650014088 | 45.43% | PT. ASTAJAYA NIRWIGHNATA | 2022-10-05
PRODUCTION TEST
1 | RUBBER SWAB 2.7/8" Heavy | Pcs | 0 | 1510000 | 10. Barang lain-lain | Non-APDN | 4650011004 | 0% | CV. ANPRISCO (brand Guiberson) | 2021-12-24
2 | RUBBER SWAB 2.7/8" Medium Load | Pcs | 0 | 637400 | 10. Barang lain-lain | Non-APDN | 4650011004 | 0% | CV. ANPRISCO (brand Guiberson) | 2021-12-24
3 | RUBBER SWAB 2.7/8" Light Load | Pcs | 0 | 698200 | 10. Barang lain-lain | Non-APDN | 4650011004 | 0% | CV. ANPRISCO (brand Guiberson) | 2021-12-24
GENERAL
1 | Diesel Fuel (FUELS) | Liter | 0 | 0 | 8. Bahan Bakar Minyak (BBM) | Diwajibkan | 4600003214 | 76.06% | PT. PERTAMINA (PERSERO) | 2021-08-19
2 | Diesel Fuel (LUBRICANTS) | Liter | 0 | 0 | 9. Pelumas | Diwajibkan | 4600003215 | 76.06% | PT. PERTAMINA LUBRICANTS | 2021-08-19

## FORM BIAYA
|  | SKKMIGAS |  |  |  | EF/AFE
DEPARTEMEN AFE
|  | EVALUATION FORM |  |  |  | BS.19
| SUBMISSION DATE | Pembahasan Biaya AFE Bundling tanggal 10 Oktober 2022
| OPERATOR | PERTAMINA EP
| CONTRACT AREA | INDONESIA
| FIELD | PENDOPO
| REFERENSI POD | POFD Lapangan Benakat Barat POFD Lapangan Talang Akar dan Pendopo
| NO AFE | 23-190-221-OO |  |  | Proposed Original
| PROJECT NAME | WO Bundling PENDOPO (6 sumur WO terdiri dari 4 sumur Tipe 2 dan 2 sumur Tipe 4)
| CONTACT PERSON | asep.suryana@pertamina.com / 0811-9945-381 ayi.yanuardi@pertamina.com / 0821-9969-0030 nayung.galih@pertamina.com / 081290469949
| LATEST DATA | Pembahasan Aspek Keteknikan Operasi 47 WO Sumur Bundling PT. Pertamina EP Asset 2 dan Ramba Tahun 2023
PROJECT BACKGROUND/OBJECTIVE
Proyek Workover Field Pendopo dimaksudkan untuk memproduksikan hidrokarbon. Target Produksi: Tipe 2 : 30 BOPD/Well; Tipe 4 : 40 BOPD/Well. Sumur ini akan ditajak pada : Februari 2023 - September 2023. Sumur ini merupakan usulan AFE Bundling WP&B tahun 2023.
Dalam evaluasi ini dilakukan optimasi utamanya yakni : 1. Unit price material mengacu pada kontrak eksisting. 2. Optimasi biaya jasa mengacu pada pekerjaan serupa tahun 2022. 3. Penggunaan kurs sudah mengacu pada ketentuan WP&B 2023 yaitu IDR 14.800.
DRILLING SUMMARY (diisi mengacu MoM atau PS Signed)
| PROJECT TYPE | Workover |  | PROGRAM TYPE |  | Conventional
| WELL TYPE | Development |  | SIDE TRACK |  | No
| WELL SUB-TYPE | Production |  | CORING |  | No
| WELL DESIGN | Slim Hole |  | CORING TYPE |  | 0
| TRAJECTORY | Vertical |  | COMPLETION |  | Yes
| RIG TYPE | Land Rig |  | COMPLETION TYPE |  | Single
| RIG POWER [HP] | 350 |  | DST |  | No
| LOCATION | Onshore
| DEPTH [ft] | 50199.3 |  | Water Depth [ft] |  | 0
| DURATION of PROJECT | Proposed | Evaluated | Remarks
| RIG DAYS | 141.3333 | 141.3333
| Moving | 6 | 6 | Pembahasan Teknis tentang Pembahasan Aspek Keteknikan Operasi 47 WO Sumur Bundling PT. Pertamina EP Asset 2 dan Ramba Tahun 2023 tanggal 26-29 Juli 2022.
| Rig up | 12 | 12
| Workover | 117.3333 | 117.3333
Coring
Test
Completion
P & A
| Rig down | 6 | 6
Referensi 1. MOM Subsurface tentang Pembahasan Pembahasan Teknis Subsurface Rencana Kerja Pemboran & Workover PT. Pertamina EP Asset 2 Tahun 2022 tanggal 26-29 Juli 2022 dengan Departemen Manajemen Reservoir dan Produksi dan Departeman Keteknikan Geologi Produksi. 2. MOM Teknis tentang Pembahasan Aspek Keteknikan Operasi 47 WO Sumur Bundling PT. Pertamina EP Asset 2 dan Ramba Tahun 2023 tanggal 26-29 Juli 2022 dengan Departemen Keteknikan Pengeboran Pengembangan. 3. Pembahasan AFE Bundling WP&B 2023 KKKS PT Pertamina EP tanggal 10-14 Oktober 2022 dengan Departemen AFE – Divisi Rencana Anggaran SKK Migas.
Print | COST ESTIMATION ANALYSIS | [5 empty] | Reapply Filter di cell A48 saat merubah Original / Revisi
TRUE | Project Cost | Proposed (US$) | Evaluated (US$) | Remarks
TRUE | Tangible Cost | 494737.2393 | 450670.4408 | - Optimasi (mengacu pada kontrak harga Tubing Zona 1) dan perubahan kurs biaya Tubing 2-7/8" dari $ 162,514 menjadi $ 124,059. - Perubahan kurs biaya Well Equipment - Surface dari $ 83,904 menjadi $ 82,487 dan Well Equipment - Sub surface dari $ 248,319 menjadi $ 244,125.
TRUE | Intangible Cost | 3078903.5755 | 2969102.5639
TRUE | Survey & Preparation | 363859.9542 | 359493.0898 | - Perubahan kurs biaya Wellsite Preparation dari $ 240,000 menjadi $ 235,946, Service Line & Communication dari $ 18,518 menjadi $ 18,206.
TRUE | Drilling/Workover | 734330.0266 | 733284.1976 | - Perubahan kurs biaya Mud Chemical dari $ 38,664 menjadi $ 38,011 dan Bit dari $ 23,249 menjadi $ 22,856.
TRUE | Formation Evaluation | 0 | 0
TRUE | Completion | 1565547.7715 | 1496719.5997 | - Optimasi Stimulation dari $ 840,000 menjadi $ 816,000. - Optimasi dan perubahan kurs biaya Logging Service dari $ 354,000 menjadi $ 313,218. - Perubahan kurs biaya Perforating dari $ 162,000 menjadi $ 159,264 dan Production Test dari $ 77,548 menjadi $ 76,238.
TRUE | General | 415165.8232 | 379605.6768 | - Optimasi Permit dari $ 53,731 menjadi $ 29,493 dan Fuel dari $ 136,842 menjadi $ 129,313. - Perubahan kurs biaya Project Management Team dari $ 122,477 menjadi $ 120,408, Insurance dari $ 24,416 menjadi $ 24,003, Land Transportation dari $ 32,204 menjadi $ 31,660, Camp Facilities dari $ 34,920 menjadi $ 34,330, Overhead dari $ 10,576 menjadi $10,398.
TRUE | TOTAL COST | 3573640.8148 | 3419773.0047 | Optimasi sebesar -4% atau sebesar US$-153867.8
TRUE | Cost/day (US$/day) | 25285.1944 | 24196.5071
TRUE | Cost/depth (US$/ft) | 71.1891 | 68.1239
TRUE | Tangible Cost/depth (US$/ft) | 9.8555 | 8.9776
TRUE | Tangible Cost/day (US$/day) | 3500.4993 | 3188.7059
TRUE | Intangible Cost/day (US$/day)* | 21784.6951 | 21007.8012
TRUE | Contract Rig Rate (US$/day) | 4714.7766 | 4714.7766
TRUE | Site Preparation | 240000 | 235945.9459
FALSE | Project Cost | Historical (US$) | Proposed (US$) | Evaluated (US$) | Remarks
FALSE | Tangible Cost | 494737.2393 | 494737.2393 | 450670.4408
FALSE | Intangible Cost | 3078903.5755 | 3078903.5755 | 2969102.5639
FALSE | Survey & Preparation | 363859.9542 | 363859.9542 | 359493.0898 | keterangan optimasi biaya
FALSE | Drilling/Workover | 734330.0266 | 734330.0266 | 733284.1976 | keterangan optimasi biaya
FALSE | Formation Evaluation | 0 | 0 | 0 | keterangan optimasi biaya
FALSE | Completion | 1565547.7715 | 1565547.7715 | 1496719.5997 | keterangan optimasi biaya
FALSE | General | 415165.8232 | 415165.8232 | 379605.6768 | keterangan optimasi biaya
FALSE | TOTAL COST | 3573640.8148 | 3573640.8148 | 3419773.0047
FALSE | Cost/day (US$/day) | 25285.1944 | 25285.1944 | 24196.5071
FALSE | Cost/depth (US$/ft) | 71.1891 | 71.1891 | 68.1239
FALSE | Tangible Cost/depth (US$/ft) | 9.8555 | 9.8555 | 8.9776
FALSE | Tangible Cost/day (US$/day) | 3500.4993 | 3500.4993 | 3188.7059
FALSE | Intangible Cost/day (US$/day)* | 21784.6951 | 21784.6951 | 21007.8012
FALSE | Contract Rig Rate (US$/day) | 0 | 672416.953 | 672416.953
FALSE | Site Preparation | 0 | 240000 | 235945.9459
UNIT COST
KESIMPULAN
Mengacu hasil evaluasi teknis dan biaya yang telah dilakukan, maka AFE ini dapat direkomendasikan untuk disetujui dengan rekomendasi anggaran sebesar US$ 3,419,773
| ORIGINAL (US$) |  | REVISED-1 (US$) |  | REVISED-2 (US$)
| PROPOSED | APPROVED | PROPOSED | APPROVED | PROPOSED | APPROVED
| 3573640.8148 | 3419773.0047
DEPARTEMEN AFE
| Hendra Nugraha |  | Tommy W. Poerwanto
LAMPIRAN UNIT COST
"keterangan apabila nilai evaluasi berada diluar range biaya Unit Cost"
Referensi :
1.
2.
3.
4.
5.

## BS19 Detail 1
[6 empty] | SUM of Wells | [6 empty] | 1. Sumur Pendopo Tipe 2 | [11 empty] | 2. Sumur Pendopo Tipe 2 | [8 empty] | 3. Sumur Pendopo Tipe 2 | [8 empty] | 4. Sumur Pendopo Tipe 2 | [8 empty] | 5. Sumur Pendopo Tipe 4 | [8 empty] | 6. Sumur Pendopo Tipe 4 | [8 empty] | 0 | [8 empty] | 0 | [8 empty] | 0
DEPARTEMEN AFE
DIVISI RENCANA ANGGARAN
BUDGET SCHEDULE 19_ DETAIL
| Line | DESCRIPTION | Historical |  |  | Proposed Original |  |  |  | EVALUATED |  |  | Historical |  |  | Proposed Original |  |  | EVALUATED |  |  | DIFFERENCE 1 | DIFFERENCE 2 | DIFFERENCE 3 | Historical |  |  | Proposed Original |  |  | EVALUATED |  |  | Historical |  |  | Proposed Original |  |  | EVALUATED |  |  | Historical |  |  | Proposed Original |  |  | EVALUATED |  |  | Historical |  |  | Proposed Original |  |  | EVALUATED |  |  | Historical |  |  | Proposed Original |  |  | EVALUATED |  |  | Historical |  |  | Proposed Original |  |  | EVALUATED |  |  | Historical |  |  | Proposed Original |  |  | EVALUATED |  |  | Historical |  |  | Proposed Original |  |  | EVALUATED |  |  | Variance (Aw vs Ak) |  | Justifikasi Teknis | Data Pendukung
[97 empty] | Quantity | Unit price
| 1 | TANGIBLE COST |  |  | 0 |  |  |  | 494737.2393 |  |  | 450670.4408 |  |  | 0 |  |  | 74785.4626 |  |  | 67648.8804 | 0 | 0 | -7136.5822 |  |  | 0 |  |  | 74785.4626 |  |  | 67648.8804 |  |  | 0 |  |  | 74785.4626 |  |  | 67648.8804 |  |  | 0 |  |  | 74785.4626 |  |  | 67648.8804 |  |  | 0 |  |  | 97797.6944 |  |  | 90037.4595 |  |  | 0 |  |  | 97797.6944 |  |  | 90037.4595 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0
| 2 | Casing | Qty | Unit Price | 0 | Unit | Qty | Unit Price | 0 | Qty | Unit Price | 0 | Qty | Unit Price | 0 | Qty | Unit Price | 0 | Qty | Unit Price | 0 | 0 | 0 | 0 | Qty | Unit Price | 0 | Qty | Unit Price | 0 | Qty | Unit Price | 0 | Qty | Unit Price | 0 | Qty | Unit Price | 0 | Qty | Unit Price | 0 | Qty | Unit Price | 0 | Qty | Unit Price | 0 | Qty | Unit Price | 0 | Qty | Unit Price | 0 | Qty | Unit Price | 0 | Qty | Unit Price | 0 | Qty | Unit Price | 0 | Qty | Unit Price | 0 | Qty | Unit Price | 0 | Qty | Unit Price | 0 | Qty | Unit Price | 0 | Qty | Unit Price | 0 | Qty | Unit Price | 0 | Qty | Unit Price | 0 | Qty | Unit Price | 0 | Qty | Unit Price | 0 | Qty | Unit Price | 0 | Qty | Unit Price | 0
|  |  | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[22 empty] | 0 | 0 | 0
| Line | DESCRIPTION | Historical |  |  | Proposed Original |  |  |  | EVALUATED |  |  | Historical |  |  | Proposed Original |  |  | EVALUATED |  |  | 0 | 0 | 0 | Historical |  |  | Proposed Original |  |  | EVALUATED |  |  | Historical |  |  | Proposed Original |  |  | EVALUATED |  |  | Historical |  |  | Proposed Original |  |  | EVALUATED |  |  | Historical |  |  | Proposed Original |  |  | EVALUATED |  |  | Historical |  |  | Proposed Original |  |  | EVALUATED |  |  | Historical |  |  | Proposed Original |  |  | EVALUATED |  |  | Historical |  |  | Proposed Original |  |  | EVALUATED |  |  | Historical |  |  | Proposed Original |  |  | EVALUATED |  |  | Variance (Aw vs Ak) |  | Justifikasi Teknis | Data Pendukung
[22 empty] | 0 | 0 | 0 | [72 empty] | Quantity | Unit price
| 3 | Casing Accessories | Qty | Unit Price | 0 | Unit | Qty | Unit Price | 0 | Qty | Unit Price | 0 | Qty | Unit Price | 0 | Qty | Unit Price | 0 | Qty | Unit Price | 0 | 0 | 0 | 0 | Qty | Unit Price | 0 | Qty | Unit Price | 0 | Qty | Unit Price | 0 | Qty | Unit Price | 0 | Qty | Unit Price | 0 | Qty | Unit Price | 0 | Qty | Unit Price | 0 | Qty | Unit Price | 0 | Qty | Unit Price | 0 | Qty | Unit Price | 0 | Qty | Unit Price | 0 | Qty | Unit Price | 0 | Qty | Unit Price | 0 | Qty | Unit Price | 0 | Qty | Unit Price | 0 | Qty | Unit Price | 0 | Qty | Unit Price | 0 | Qty | Unit Price | 0 | Qty | Unit Price | 0 | Qty | Unit Price | 0 | Qty | Unit Price | 0 | Qty | Unit Price | 0 | Qty | Unit Price | 0 | Qty | Unit Price | 0
|  | Dry Hole Based | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | 9.5/8" REAMER SHOE, BTC, 40-47 PPF | 0 | 0 | 0 | PCS | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | 9.5/8" FLOAT COLLAR, 40-47 PPF, BTC | 0 | 0 | 0 | PCS | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | DSCC 9.5/8", L-80, 43.5-53.5 PPF, BTC | 0 | 0 | 0 | PCS | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | ECP 9.5/8", L-80, 40-47 PPF, BTC | 0 | 0 | 0 | PCS | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Completion Based | 0 | 0 | 0 | PCS | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | 9.5/8 x 7" HYDR. ROTATING LINER HANGER, 26-47 PPF, BTC | 0 | 0 | 0 | PCS | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[22 empty] | 0 | 0 | 0
| Line | DESCRIPTION | Historical |  |  | Proposed Original |  |  |  | EVALUATED |  |  | Historical |  |  | Proposed Original |  |  | EVALUATED |  |  | 0 | 0 | 0 | Historical |  |  | Proposed Original |  |  | EVALUATED |  |  | Historical |  |  | Proposed Original |  |  | EVALUATED |  |  | Historical |  |  | Proposed Original |  |  | EVALUATED |  |  | Historical |  |  | Proposed Original |  |  | EVALUATED |  |  | Historical |  |  | Proposed Original |  |  | EVALUATED |  |  | Historical |  |  | Proposed Original |  |  | EVALUATED |  |  | Historical |  |  | Proposed Original |  |  | EVALUATED |  |  | Historical |  |  | Proposed Original |  |  | EVALUATED |  |  | Variance (Aw vs Ak) |  | Justifikasi Teknis | Data Pendukung
[22 empty] | 0 | 0 | 0 | [72 empty] | Quantity | Unit price
| 4 | Tubing | Qty | Unit Price | 0 | Unit | Qty | Unit Price | 162513.6278 | Qty | Unit Price | 124058.7146 | Qty | Unit Price | 0 | Qty | Unit Price | 26746.5668 | Qty | Unit Price | 20421.4524 | 0 | 0 | -6325.1144 | Qty | Unit Price | 0 | Qty | Unit Price | 26746.5668 | Qty | Unit Price | 20421.4524 | Qty | Unit Price | 0 | Qty | Unit Price | 26746.5668 | Qty | Unit Price | 20421.4524 | Qty | Unit Price | 0 | Qty | Unit Price | 26746.5668 | Qty | Unit Price | 20421.4524 | Qty | Unit Price | 0 | Qty | Unit Price | 27763.6803 | Qty | Unit Price | 21186.4524 | Qty | Unit Price | 0 | Qty | Unit Price | 27763.6803 | Qty | Unit Price | 21186.4524 | Qty | Unit Price | 0 | Qty | Unit Price | 0 | Qty | Unit Price | 0 | Qty | Unit Price | 0 | Qty | Unit Price | 0 | Qty | Unit Price | 0 | Qty | Unit Price | 0 | Qty | Unit Price | 0 | Qty | Unit Price | 0
|  | 2-7/8" TBG, J55, 6.30 PPF, EU, R2 | 0 | 0 | 0 |  | 760 | 203.4227 | 154601.2583 | 760 | 153 | 116280 | 0 | 0 | 0 | 125 | 203.4227 | 25427.8385 | 125 | 153 | 19125 | 0 | -50.4227 | -6302.8385 | 0 | 0 | 0 | 125 | 203.4227 | 25427.8385 | 125 | 153 | 19125 | 0 | 0 | 0 | 125 | 203.4227 | 25427.8385 | 125 | 153 | 19125 | 0 | 0 | 0 | 125 | 203.4227 | 25427.8385 | 125 | 153 | 19125 | 0 | 0 | 0 | 130 | 203.4227 | 26444.9521 | 130 | 153 | 19890 | 0 | 0 | 0 | 130 | 203.4227 | 26444.9521 | 130 | 153 | 19890 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -50.4227
|  | Pup Joint 2-7/8" x 2 ft | 0 | 0 | 0 |  | 12 | 131.5936 | 1579.1233 | 12 | 129.3707 | 1552.4489 |  |  | 0 | 2 | 131.5936 | 263.1872 | 2 | 129.3707 | 258.7415 | 0 | -2.2229 | -4.4457 | 0 | 0 | 0 | 2 | 131.5936 | 263.1872 | 2 | 129.3707 | 258.7415 | 0 | 0 | 0 | 2 | 131.5936 | 263.1872 | 2 | 129.3707 | 258.7415 | 0 | 0 | 0 | 2 | 131.5936 | 263.1872 | 2 | 129.3707 | 258.7415 | 0 | 0 | 0 | 2 | 131.5936 | 263.1872 | 2 | 129.3707 | 258.7415 | 0 | 0 | 0 | 2 | 131.5936 | 263.1872 | 2 | 129.3707 | 258.7415 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -2.2229
|  | Pup Joint 2-7/8" x 4 ft | 0 | 0 | 0 |  | 12 | 149.3943 | 1792.7315 | 12 | 146.8707 | 1762.4489 |  |  | 0 | 2 | 149.3943 | 298.7886 | 2 | 146.8707 | 293.7415 | 0 | -2.5236 | -5.0471 | 0 | 0 | 0 | 2 | 149.3943 | 298.7886 | 2 | 146.8707 | 293.7415 | 0 | 0 | 0 | 2 | 149.3943 | 298.7886 | 2 | 146.8707 | 293.7415 | 0 | 0 | 0 | 2 | 149.3943 | 298.7886 | 2 | 146.8707 | 293.7415 | 0 | 0 | 0 | 2 | 149.3943 | 298.7886 | 2 | 146.8707 | 293.7415 | 0 | 0 | 0 | 2 | 149.3943 | 298.7886 | 2 | 146.8707 | 293.7415 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -2.5236
|  | Pup Joint 2-7/8" x 6 ft | 0 | 0 | 0 |  | 12 | 175.5799 | 2106.9584 | 12 | 172.614 | 2071.3678 |  |  | 0 | 2 | 175.5799 | 351.1597 | 2 | 172.614 | 345.228 | 0 | -2.9659 | -5.9318 | 0 | 0 | 0 | 2 | 175.5799 | 351.1597 | 2 | 172.614 | 345.228 | 0 | 0 | 0 | 2 | 175.5799 | 351.1597 | 2 | 172.614 | 345.228 | 0 | 0 | 0 | 2 | 175.5799 | 351.1597 | 2 | 172.614 | 345.228 | 0 | 0 | 0 | 2 | 175.5799 | 351.1597 | 2 | 172.614 | 345.228 | 0 | 0 | 0 | 2 | 175.5799 | 351.1597 | 2 | 172.614 | 345.228 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -2.9659
|  | Pup Joint 2-7/8" x 8 ft | 0 | 0 | 0 |  | 12 | 202.7964 | 2433.5563 | 12 | 199.3707 | 2392.4489 |  |  | 0 | 2 | 202.7964 | 405.5927 | 2 | 199.3707 | 398.7415 | 0 | -3.4256 | -6.8512 | 0 | 0 | 0 | 2 | 202.7964 | 405.5927 | 2 | 199.3707 | 398.7415 | 0 | 0 | 0 | 2 | 202.7964 | 405.5927 | 2 | 199.3707 | 398.7415 | 0 | 0 | 0 | 2 | 202.7964 | 405.5927 | 2 | 199.3707 | 398.7415 | 0 | 0 | 0 | 2 | 202.7964 | 405.5927 | 2 | 199.3707 | 398.7415 | 0 | 0 | 0 | 2 | 202.7964 | 405.5927 | 2 | 199.3707 | 398.7415 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -3.4256
|  |  | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[22 empty] | 0 | 0 | 0
| Line | DESCRIPTION | Historical |  |  | Proposed Original |  |  |  | EVALUATED |  |  | Historical |  |  | Proposed Original |  |  | EVALUATED |  |  | 0 | 0 | 0 | Historical |  |  | Proposed Original |  |  | EVALUATED |  |  | Historical |  |  | Proposed Original |  |  | EVALUATED |  |  | Historical |  |  | Proposed Original |  |  | EVALUATED |  |  | Historical |  |  | Proposed Original |  |  | EVALUATED |  |  | Historical |  |  | Proposed Original |  |  | EVALUATED |  |  | Historical |  |  | Proposed Original |  |  | EVALUATED |  |  | Historical |  |  | Proposed Original |  |  | EVALUATED |  |  | Historical |  |  | Proposed Original |  |  | EVALUATED |  |  | Variance (Aw vs Ak) |  | Justifikasi Teknis | Data Pendukung
[22 empty] | 0 | 0 | 0 | [72 empty] | Quantity | Unit price
| 5 | Well Equipment Surface | Qty | Unit Price | 0 | Unit | Qty | Unit Price | 83904.344 | Qty | Unit Price | 82487.0409 | Qty | Unit Price | 0 | Qty | Unit Price | 6044.0302 | Qty | Unit Price | 5941.9351 | 0 | 0 | -102.0951 | Qty | Unit Price | 0 | Qty | Unit Price | 6044.0302 | Qty | Unit Price | 5941.9351 | Qty | Unit Price | 0 | Qty | Unit Price | 6044.0302 | Qty | Unit Price | 5941.9351 | Qty | Unit Price | 0 | Qty | Unit Price | 6044.0302 | Qty | Unit Price | 5941.9351 | Qty | Unit Price | 0 | Qty | Unit Price | 29864.1115 | Qty | Unit Price | 29359.6502 | Qty | Unit Price | 0 | Qty | Unit Price | 29864.1115 | Qty | Unit Price | 29359.6502 | Qty | Unit Price | 0 | Qty | Unit Price | 0 | Qty | Unit Price | 0 | Qty | Unit Price | 0 | Qty | Unit Price | 0 | Qty | Unit Price | 0 | Qty | Unit Price | 0 | Qty | Unit Price | 0 | Qty | Unit Price | 0
|  | X-MASTREE,7.1/16 X 3.1/8 IN,3.000 BB | 0 | 0 | 0 |  | 2 | 29864.1115 | 59728.223 | 2 | 29359.6502 | 58719.3003 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 29864.1115 | 29864.1115 | 1 | 29359.6502 | 29359.6502 | 0 | 0 | 0 | 1 | 29864.1115 | 29864.1115 | 1 | 29359.6502 | 29359.6502 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -504.4613
|  | ADAPTER FLANGE | 0 | 0 | 0 |  | 4 | 4006.7794 | 16027.1175 | 4 | 3939.0973 | 15756.3892 | 0 | 0 | 0 | 1 | 4006.7794 | 4006.7794 | 1 | 3939.0973 | 3939.0973 | 0 | -67.6821 | -67.6821 | 0 | 0 | 0 | 1 | 4006.7794 | 4006.7794 | 1 | 3939.0973 | 3939.0973 | 0 | 0 | 0 | 1 | 4006.7794 | 4006.7794 | 1 | 3939.0973 | 3939.0973 | 0 | 0 | 0 | 1 | 4006.7794 | 4006.7794 | 1 | 3939.0973 | 3939.0973 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -67.6821
|  | GATE VLV, X-MAST TREE,3.1/8 IN, 3000 PSI | 0 | 0 | 0 |  | 4 | 2037.2509 | 8149.0034 | 4 | 2002.8378 | 8011.3514 |  |  | 0 | 1 | 2037.2509 | 2037.2509 | 1 | 2002.8378 | 2002.8378 | 0 | -34.413 | -34.413 | 0 | 0 | 0 | 1 | 2037.2509 | 2037.2509 | 1 | 2002.8378 | 2002.8378 | 0 | 0 | 0 | 1 | 2037.2509 | 2037.2509 | 1 | 2002.8378 | 2002.8378 | 0 | 0 | 0 | 1 | 2037.2509 | 2037.2509 | 1 | 2002.8378 | 2002.8378 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -34.413
|  |  | 0 | 0 | 0 |  | 1 | 0 | 0 | 1 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  | 0 | 0 | 0 |  | 1 | 0 | 0 | 1 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  | 0 | 0 | 0 |  | 1 | 0 | 0 | 1 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  | 0 | 0 | 0 |  | 2 | 0 | 0 | 2 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2 | 0 | 0 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  | 0 | 0 | 0 |  | 2 | 0 | 0 | 2 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2 | 0 | 0 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  | 0 | 0 | 0 |  | 1 | 0 | 0 | 1 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  | 0 | 0 | 0 |  | 1 | 0 | 0 | 1 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  | 0 | 0 | 0 |  | 0 | 0 | 0 | 1 | 0 | 0 |  |  | 0 |  |  |  | 0 | 0 | 0
|  |  | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[22 empty] | 0 | 0 | 0
| Line | DESCRIPTION | Historical |  |  | Proposed Original |  |  |  | EVALUATED |  |  | Historical |  |  | Proposed Original |  |  | EVALUATED |  |  | 0 | 0 | 0 | Historical |  |  | Proposed Original |  |  | EVALUATED |  |  | Historical |  |  | Proposed Original |  |  | EVALUATED |  |  | Historical |  |  | Proposed Original |  |  | EVALUATED |  |  | Historical |  |  | Proposed Original |  |  | EVALUATED |  |  | Historical |  |  | Proposed Original |  |  | EVALUATED |  |  | Historical |  |  | Proposed Original |  |  | EVALUATED |  |  | Historical |  |  | Proposed Original |  |  | EVALUATED |  |  | Historical |  |  | Proposed Original |  |  | EVALUATED |  |  | Variance (Aw vs Ak) |  | Justifikasi Teknis | Data Pendukung
[22 empty] | 0 | 0 | 0 | [72 empty] | Quantity | Unit price
| 6 | Well Equipment Sub-surface | Qty | Unit Price | 0 | Unit | Qty | Unit Price | 248319.2675 | Qty | Unit Price | 244124.6853 | Qty | Unit Price | 0 | Qty | Unit Price | 41994.8656 | Qty | Unit Price | 41285.4929 | 0 | 0 | -709.3727 | Qty | Unit Price | 0 | Qty | Unit Price | 41994.8656 | Qty | Unit Price | 41285.4929 | Qty | Unit Price | 0 | Qty | Unit Price | 41994.8656 | Qty | Unit Price | 41285.4929 | Qty | Unit Price | 0 | Qty | Unit Price | 41994.8656 | Qty | Unit Price | 41285.4929 | Qty | Unit Price | 0 | Qty | Unit Price | 40169.9026 | Qty | Unit Price | 39491.3569 | Qty | Unit Price | 0 | Qty | Unit Price | 40169.9026 | Qty | Unit Price | 39491.3569 | Qty | Unit Price | 0 | Qty | Unit Price | 0 | Qty | Unit Price | 0 | Qty | Unit Price | 0 | Qty | Unit Price | 0 | Qty | Unit Price | 0 | Qty | Unit Price | 0 | Qty | Unit Price | 0 | Qty | Unit Price | 0
|  | PACKER 7", SG, 20-26 PPF, 2 7/8" EU | 0 | 0 | 0 |  | 6 | 6504.4798 | 39026.879 | 6 | 6394.6069 | 38367.6412 | 0 | 0 | 0 | 1 | 6504.4798 | 6504.4798 | 1 | 6394.6069 | 6394.6069 | 0 | -109.873 | -109.873 | 0 | 0 | 0 | 1 | 6504.4798 | 6504.4798 | 1 | 6394.6069 | 6394.6069 | 0 | 0 | 0 | 1 | 6504.4798 | 6504.4798 | 1 | 6394.6069 | 6394.6069 | 0 | 0 | 0 | 1 | 6504.4798 | 6504.4798 | 1 | 6394.6069 | 6394.6069 | 0 | 0 | 0 | 1 | 6504.4798 | 6504.4798 | 1 | 6394.6069 | 6394.6069 | 0 | 0 | 0 | 1 | 6504.4798 | 6504.4798 | 1 | 6394.6069 | 6394.6069 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -109.873
|  | Redress Kit Packer 5-1/2 in | 0 | 0 | 0 |  | 8 | 131.4904 | 1051.9236 | 8 | 129.2693 | 1034.1546 |  |  | 0 | 2 | 131.4904 | 262.9809 | 2 | 129.2693 | 258.5386 | 0 | -2.2211 | -4.4422 | 0 | 0 | 0 | 2 | 131.4904 | 262.9809 | 2 | 129.2693 | 258.5386 | 0 | 0 | 0 | 2 | 131.4904 | 262.9809 | 2 | 129.2693 | 258.5386 | 0 | 0 | 0 | 2 | 131.4904 | 262.9809 | 2 | 129.2693 | 258.5386 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -2.2211
|  | Redress Kit Packer 6-5/8 in | 0 | 0 | 0 |  | 8 | 192.4401 | 1539.5205 | 8 | 189.1894 | 1513.5151 |  |  | 0 | 2 | 192.4401 | 384.8801 | 2 | 189.1894 | 378.3788 | 0 | -3.2507 | -6.5014 | 0 | 0 | 0 | 2 | 192.4401 | 384.8801 | 2 | 189.1894 | 378.3788 | 0 | 0 | 0 | 2 | 192.4401 | 384.8801 | 2 | 189.1894 | 378.3788 | 0 | 0 | 0 | 2 | 192.4401 | 384.8801 | 2 | 189.1894 | 378.3788 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -3.2507
|  | Redress Kit Packer 7 in SG | 0 | 0 | 0 |  | 8 | 487.1524 | 3897.219 | 8 | 478.9234 | 3831.3876 |  |  | 0 | 2 | 487.1524 | 974.3047 | 2 | 478.9234 | 957.8469 | 0 | -8.2289 | -16.4579 | 0 | 0 | 0 | 2 | 487.1524 | 974.3047 | 2 | 478.9234 | 957.8469 | 0 | 0 | 0 | 2 | 487.1524 | 974.3047 | 2 | 478.9234 | 957.8469 | 0 | 0 | 0 | 2 | 487.1524 | 974.3047 | 2 | 478.9234 | 957.8469 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -8.2289
|  | REDRESS KIT,PACKER 4-1/2 IN-2-3/8 IN | 0 | 0 | 0 |  | 8 | 101.3986 | 811.189 | 8 | 99.6858 | 797.4865 |  |  | 0 | 2 | 101.3986 | 202.7973 | 2 | 99.6858 | 199.3716 | 0 | -1.7128 | -3.4256 | 0 | 0 | 0 | 2 | 101.3986 | 202.7973 | 2 | 99.6858 | 199.3716 | 0 | 0 | 0 | 2 | 101.3986 | 202.7973 | 2 | 99.6858 | 199.3716 | 0 | 0 | 0 | 2 | 101.3986 | 202.7973 | 2 | 99.6858 | 199.3716 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -1.7128
|  | SRP Equipment | 0 | 0 | 0 |  | 6 | 33665.4227 | 201992.5364 | 6 | 33096.7501 | 198580.5003 |  |  | 0 | 1 | 33665.4227 | 33665.4227 | 1 | 33096.7501 | 33096.7501 | 0 | -568.6727 | -568.6727 | 0 | 0 | 0 | 1 | 33665.4227 | 33665.4227 | 1 | 33096.7501 | 33096.7501 | 0 | 0 | 0 | 1 | 33665.4227 | 33665.4227 | 1 | 33096.7501 | 33096.7501 | 0 | 0 | 0 | 1 | 33665.4227 | 33665.4227 | 1 | 33096.7501 | 33096.7501 | 0 | 0 | 0 | 1 | 33665.4227 | 33665.4227 | 1 | 33096.7501 | 33096.7501 | 0 | 0 | 0 | 1 | 33665.4227 | 33665.4227 | 1 | 33096.7501 | 33096.7501 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -568.6727
|  |  | 0 | 0 | 0 |  | 120 | 0 | 0 | 120 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 120 | 0 | 0 | 120 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  | 0 | 0 | 0 |  | 1 | 0 | 0 | 1 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  | 0 | 0 | 0 |  | 1 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  | 0 | 0 | 0 |  | 1 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  | 0 | 0 | 0 |  | 1 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  | 0 | 0 | 0 |  | 1 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  | 0 | 0 | 0 |  | 1 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  | 0 | 0 | 0 |  | 1 | 0 | 0 | 1 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  | 0 | 0 | 0 |  | 1 | 0 | 0 | 1 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  | 0 | 0 | 0 |  | 1 | 0 | 0 | 1 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  | 0 | 0 | 0 |  | 1 | 0 | 0 | 1 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  | 0 | 0 | 0 |  | 1 | 0 | 0 | 1 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  | 0 | 0 | 0 |  | 1 | 0 | 0 | 1 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  | 0 | 0 | 0 |  | 1 | 0 | 0 | 1 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  | 0 | 0 | 0 |  | 60 | 0 | 0 | 60 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 60 | 0 | 0 | 60 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  | 0 | 0 | 0 |  | 60 | 0 | 0 | 60 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 60 | 0 | 0 | 60 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  | 0 | 0 | 0 |  | 60 | 0 | 0 | 60 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 60 | 0 | 0 | 60 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  | 0 | 0 | 0 |  | 1 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  | 0 | 0 | 0 |  | 1 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  | 0 | 0 | 0 |  | 1 | 0 | 0 | 1 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  | 0 | 0 | 0 |  | 1 | 0 | 0 | 1 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[22 empty] | 0 | 0 | 0
| Line | DESCRIPTION | Historical |  |  | Proposed Original |  |  |  | EVALUATED |  |  | Historical |  |  | Proposed Original |  |  | EVALUATED |  |  | 0 | 0 | 0 | Historical |  |  | Proposed Original |  |  | EVALUATED |  |  | Historical |  |  | Proposed Original |  |  | EVALUATED |  |  | Historical |  |  | Proposed Original |  |  | EVALUATED |  |  | Historical |  |  | Proposed Original |  |  | EVALUATED |  |  | Historical |  |  | Proposed Original |  |  | EVALUATED |  |  | Historical |  |  | Proposed Original |  |  | EVALUATED |  |  | Historical |  |  | Proposed Original |  |  | EVALUATED |  |  | Historical |  |  | Proposed Original |  |  | EVALUATED |  |  | Variance (Aw vs Ak) |  | Justifikasi Teknis | Data Pendukung
[22 empty] | 0 | 0 | 0 | [72 empty] | Quantity | Unit price
| 7 | Other Tangible Cost | Qty | Unit Price | 0 | Unit | Qty | Unit Price | 0 | Qty | Unit Price | 0 | Qty | Unit Price | 0 | Qty | Unit Price | 0 | Qty | Unit Price | 0 | 0 | 0 | 0 | Qty | Unit Price | 0 | Qty | Unit Price | 0 | Qty | Unit Price | 0 | Qty | Unit Price | 0 | Qty | Unit Price | 0 | Qty | Unit Price | 0 | Qty | Unit Price | 0 | Qty | Unit Price | 0 | Qty | Unit Price | 0 | Qty | Unit Price | 0 | Qty | Unit Price | 0 | Qty | Unit Price | 0 | Qty | Unit Price | 0 | Qty | Unit Price | 0 | Qty | Unit Price | 0 | Qty | Unit Price | 0 | Qty | Unit Price | 0 | Qty | Unit Price | 0 | Qty | Unit Price | 0 | Qty | Unit Price | 0 | Qty | Unit Price | 0 | Qty | Unit Price | 0 | Qty | Unit Price | 0 | Qty | Unit Price | 0
|  | Dry Hole Based | 0 | 0 | 0 |  | 30 | 0 | 0 | 30 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 10 | 0 | 0 | 10 | 0 | 0 | 0 | 0 | 0 | 10 | 0 | 0 | 10 | 0 | 0 | 0 | 0 | 0 | 10 | 0 | 0 | 10 | 0 | 0 | 0 | 0
|  |  | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[22 empty] | 0 | 0 | 0
[22 empty] | 0 | 0 | 0
|  | INTANGIBLE COST |  |  | 0 |  |  |  | 3078903.5755 |  |  | 2969102.5639 |  |  | 0 |  |  | 423010.779 |  |  | 402609.6123 | 0 | 0 | -20401.1667 |  |  | 0 |  |  | 423010.779 |  |  | 402609.6123 |  |  | 0 |  |  | 423010.779 |  |  | 402609.6123 |  |  | 0 |  |  | 423010.779 |  |  | 402609.6123 |  |  | 0 |  |  | 693430.2297 |  |  | 679332.0573 |  |  | 0 |  |  | 693430.2297 |  |  | 679332.0573 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0
| Line | DESCRIPTION | Historical |  |  | Proposed Original |  |  |  | EVALUATED |  |  | Historical |  |  | Proposed Original |  |  | EVALUATED |  |  | 0 | 0 | 0 | Historical |  |  | Proposed Original |  |  | EVALUATED |  |  | Historical |  |  | Proposed Original |  |  | EVALUATED |  |  | Historical |  |  | Proposed Original |  |  | EVALUATED |  |  | Historical |  |  | Proposed Original |  |  | EVALUATED |  |  | Historical |  |  | Proposed Original |  |  | EVALUATED |  |  | Historical |  |  | Proposed Original |  |  | EVALUATED |  |  | Historical |  |  | Proposed Original |  |  | EVALUATED |  |  | Historical |  |  | Proposed Original |  |  | EVALUATED |  |  | Variance (Aw vs Ak) |  | Justifikasi Teknis | Data Pendukung
[22 empty] | 0 | 0 | 0 | [72 empty] | Quantity | Unit price
| 10 | PREPARATION AND TERMINATION |  |  | 0 |  |  |  | 363859.9542 |  |  | 359493.0898 |  |  | 0 |  |  | 59049.2368 |  |  | 58322.5646 | 0 | 0 | -726.6722 |  |  | 0 |  |  | 59049.2368 |  |  | 58322.5646 |  |  | 0 |  |  | 59049.2368 |  |  | 58322.5646 |  |  | 0 |  |  | 59049.2368 |  |  | 58322.5646 |  |  | 0 |  |  | 63831.5034 |  |  | 63101.4157 |  |  | 0 |  |  | 63831.5034 |  |  | 63101.4157 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0
| 11 | Survey | Qty | Unit Price | 0 | Unit | Qty | Unit Price | 0 | Qty | Unit Price | 0 | Qty | Unit Price | 0 | Qty | Unit Price | 0 | Qty | Unit Price | 0 | 0 | 0 | 0 | Qty | Unit Price | 0 | Qty | Unit Price | 0 | Qty | Unit Price | 0 | Qty | Unit Price | 0 | Qty | Unit Price | 0 | Qty | Unit Price | 0 | Qty | Unit Price | 0 | Qty | Unit Price | 0 | Qty | Unit Price | 0 | Qty | Unit Price | 0 | Qty | Unit Price | 0 | Qty | Unit Price | 0 | Qty | Unit Price | 0 | Qty | Unit Price | 0 | Qty | Unit Price | 0 | Qty | Unit Price | 0 | Qty | Unit Price | 0 | Qty | Unit Price | 0 | Qty | Unit Price | 0 | Qty | Unit Price | 0 | Qty | Unit Price | 0 | Qty | Unit Price | 0 | Qty | Unit Price | 0 | Qty | Unit Price | 0
|  | SURVEY TOFOGRAFIS, PEMETAAN DAN LEVELING | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[22 empty] | 0 | 0 | 0
| Line | DESCRIPTION | Historical |  |  | Proposed Original |  |  |  | EVALUATED |  |  | Historical |  |  | Proposed Original |  |  | EVALUATED |  |  | 0 | 0 | 0 | Historical |  |  | Proposed Original |  |  | EVALUATED |  |  | Historical |  |  | Proposed Original |  |  | EVALUATED |  |  | Historical |  |  | Proposed Original |  |  | EVALUATED |  |  | Historical |  |  | Proposed Original |  |  | EVALUATED |  |  | Historical |  |  | Proposed Original |  |  | EVALUATED |  |  | Historical |  |  | Proposed Original |  |  | EVALUATED |  |  | Historical |  |  | Proposed Original |  |  | EVALUATED |  |  | Historical |  |  | Proposed Original |  |  | EVALUATED |  |  | Variance (Aw vs Ak) |  | Justifikasi Teknis | Data Pendukung
[22 empty] | 0 | 0 | 0 | [72 empty] | Quantity | Unit price
| 12 | LOCATION STACKING AND POSITIONING | Qty | Unit Price | 0 | Unit | Qty | Unit Price | 0 | Qty | Unit Price | 0 | Qty | Unit Price | 0 | Qty | Unit Price | 0 | Qty | Unit Price | 0 | 0 | 0 | 0 | Qty | Unit Price | 0 | Qty | Unit Price | 0 | Qty | Unit Price | 0 | Qty | Unit Price | 0 | Qty | Unit Price | 0 | Qty | Unit Price | 0 | Qty | Unit Price | 0 | Qty | Unit Price | 0 | Qty | Unit Price | 0 | Qty | Unit Price | 0 | Qty | Unit Price | 0 | Qty | Unit Price | 0 | Qty | Unit Price | 0 | Qty | Unit Price | 0 | Qty | Unit Price | 0 | Qty | Unit Price | 0 | Qty | Unit Price | 0 | Qty | Unit Price | 0 | Qty | Unit Price | 0 | Qty | Unit Price | 0 | Qty | Unit Price | 0 | Qty | Unit Price | 0 | Qty | Unit Price | 0 | Qty | Unit Price | 0
|  |  | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[22 empty] | 0 | 0 | 0
| Line | DESCRIPTION | Historical |  |  | Proposed Original |  |  |  | EVALUATED |  |  | Historical |  |  | Proposed Original |  |  | EVALUATED |  |  | 0 | 0 | 0 | Historical |  |  | Proposed Original |  |  | EVALUATED |  |  | Historical |  |  | Proposed Original |  |  | EVALUATED |  |  | Historical |  |  | Proposed Original |  |  | EVALUATED |  |  | Historical |  |  | Proposed Original |  |  | EVALUATED |  |  | Historical |  |  | Proposed Original |  |  | EVALUATED |  |  | Historical |  |  | Proposed Original |  |  | EVALUATED |  |  | Historical |  |  | Proposed Original |  |  | EVALUATED |  |  | Historical |  |  | Proposed Original |  |  | EVALUATED |  |  | Variance (Aw vs Ak) |  | Justifikasi Teknis | Data Pendukung
[22 empty] | 0 | 0 | 0 | [72 empty] | Quantity | Unit price
| 13 | Wellsite and Access Road Preparation | Qty | Unit Price | 0 | Unit | Qty | Unit Price | 240000 | Qty | Unit Price | 235945.9459 | Qty | Unit Price | 0 | Qty | Unit Price | 40000 | Qty | Unit Price | 39324.3243 | 0 | 0 | -675.6757 | Qty | Unit Price | 0 | Qty | Unit Price | 40000 | Qty | Unit Price | 39324.3243 | Qty | Unit Price | 0 | Qty | Unit Price | 40000 | Qty | Unit Price | 39324.3243 | Qty | Unit Price | 0 | Qty | Unit Price | 40000 | Qty | Unit Price | 39324.3243 | Qty | Unit Price | 0 | Qty | Unit Price | 40000 | Qty | Unit Price | 39324.3243 | Qty | Unit Price | 0 | Qty | Unit Price | 40000 | Qty | Unit Price | 39324.3243 | Qty | Unit Price | 0 | Qty | Unit Price | 0 | Qty | Unit Price | 0 | Qty | Unit Price | 0 | Qty | Unit Price | 0 | Qty | Unit Price | 0 | Qty | Unit Price | 0 | Qty | Unit Price | 0 | Qty | Unit Price | 0
|  | Dry Hole Based | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Penyiapan Lokasi Workover | 0 | 0 | 0 |  | 6 | 40000 | 240000 | 6 | 39324.3243 | 235945.9459 | 0 | 0 | 0 | 1 | 40000 | 40000 | 1 | 39324.3243 | 39324.3243 | 0 | -675.6757 | -675.6757 | 0 | 0 | 0 | 1 | 40000 | 40000 | 1 | 39324.3243 | 39324.3243 | 0 | 0 | 0 | 1 | 40000 | 40000 | 1 | 39324.3243 | 39324.3243 | 0 | 0 | 0 | 1 | 40000 | 40000 | 1 | 39324.3243 | 39324.3243 | 0 | 0 | 0 | 1 | 40000 | 40000 | 1 | 39324.3243 | 39324.3243 | 0 | 0 | 0 | 1 | 40000 | 40000 | 1 | 39324.3243 | 39324.3243 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 39324.3243 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 39324.3243 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 39324.3243 | 0 | 0 | -675.6757
|  | Pekerjaan Jalan & Lokasi | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Pekerjaan Balong & Saluran Air | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Sewa Alat Berat | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Pembuatan Pondasi dan SILO | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[22 empty] | 0 | 0 | 0
| Line | DESCRIPTION | Historical |  |  | Proposed Original |  |  |  | EVALUATED |  |  | Historical |  |  | Proposed Original |  |  | EVALUATED |  |  | 0 | 0 | 0 | Historical |  |  | Proposed Original |  |  | EVALUATED |  |  | Historical |  |  | Proposed Original |  |  | EVALUATED |  |  | Historical |  |  | Proposed Original |  |  | EVALUATED |  |  | Historical |  |  | Proposed Original |  |  | EVALUATED |  |  | Historical |  |  | Proposed Original |  |  | EVALUATED |  |  | Historical |  |  | Proposed Original |  |  | EVALUATED |  |  | Historical |  |  | Proposed Original |  |  | EVALUATED |  |  | Historical |  |  | Proposed Original |  |  | EVALUATED |  |  | Variance (Aw vs Ak) |  | Justifikasi Teknis | Data Pendukung
[22 empty] | 0 | 0 | 0 | [72 empty] | Quantity | Unit price
| 14 | Service Lines & Communications | Qty | Unit Price | 0 | Unit | Qty | Unit Price | 18518.3734 | Qty | Unit Price | 18205.5631 | Qty | Unit Price | 0 | Qty | Unit Price | 3018.9963 | Qty | Unit Price | 2967.9997 | 0 | 0 | -50.9966 | Qty | Unit Price | 0 | Qty | Unit Price | 3018.9963 | Qty | Unit Price | 2967.9997 | Qty | Unit Price | 0 | Qty | Unit Price | 3018.9963 | Qty | Unit Price | 2967.9997 | Qty | Unit Price | 0 | Qty | Unit Price | 3018.9963 | Qty | Unit Price | 2967.9997 | Qty | Unit Price | 0 | Qty | Unit Price | 3221.1942 | Qty | Unit Price | 3166.7821 | Qty | Unit Price | 0 | Qty | Unit Price | 3221.1942 | Qty | Unit Price | 3166.7821 | Qty | Unit Price | 0 | Qty | Unit Price | 0 | Qty | Unit Price | 0 | Qty | Unit Price | 0 | Qty | Unit Price | 0 | Qty | Unit Price | 0 | Qty | Unit Price | 0 | Qty | Unit Price | 0 | Qty | Unit Price | 0
|  | Dry Hole Based | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | SERVICE LINE & COMMUNICATION (AREA ASSET 2) | 0 | 0 | 0 |  | 6 | 3086.3956 | 18518.3734 | 6 | 3034.2605 | 18205.5631 | 0 |  | 0 | 1 | 3018.9963 | 3018.9963 | 1 | 2967.9997 | 2967.9997 | 0 | -50.9966 | -50.9966 | 0 | 0 | 0 | 1 | 3018.9963 | 3018.9963 | 1 | 2967.9997 | 2967.9997 | 0 | 0 | 0 | 1 | 3018.9963 | 3018.9963 | 1 | 2967.9997 | 2967.9997 | 0 | 0 | 0 | 1 | 3018.9963 | 3018.9963 | 1 | 2967.9997 | 2967.9997 | 0 | 0 | 0 | 1 | 3221.1942 | 3221.1942 | 1 | 3166.7821 | 3166.7821 | 0 | 0 | 0 | 1 | 3221.1942 | 3221.1942 | 1 | 3166.7821 | 3166.7821 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -52.1351
|  |  | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[22 empty] | 0 | 0 | 0
| Line | DESCRIPTION | Historical |  |  | Proposed Original |  |  |  | EVALUATED |  |  | Historical |  |  | Proposed Original |  |  | EVALUATED |  |  | 0 | 0 | 0 | Historical |  |  | Proposed Original |  |  | EVALUATED |  |  | Historical |  |  | Proposed Original |  |  | EVALUATED |  |  | Historical |  |  | Proposed Original |  |  | EVALUATED |  |  | Historical |  |  | Proposed Original |  |  | EVALUATED |  |  | Historical |  |  | Proposed Original |  |  | EVALUATED |  |  | Historical |  |  | Proposed Original |  |  | EVALUATED |  |  | Historical |  |  | Proposed Original |  |  | EVALUATED |  |  | Historical |  |  | Proposed Original |  |  | EVALUATED |  |  | Variance (Aw vs Ak) |  | Justifikasi Teknis | Data Pendukung
[22 empty] | 0 | 0 | 0 | [72 empty] | Quantity | Unit price
| 15 | Water System | Qty | Unit Price | 0 | Unit | Qty | Unit Price | 0 | Qty | Unit Price | 0 | Qty | Unit Price | 0 | Qty | Unit Price | 0 | Qty | Unit Price | 0 | 0 | 0 | 0 | Qty | Unit Price | 0 | Qty | Unit Price | 0 | Qty | Unit Price | 0 | Qty | Unit Price | 0 | Qty | Unit Price | 0 | Qty | Unit Price | 0 | Qty | Unit Price | 0 | Qty | Unit Price | 0 | Qty | Unit Price | 0 | Qty | Unit Price | 0 | Qty | Unit Price | 0 | Qty | Unit Price | 0 | Qty | Unit Price | 0 | Qty | Unit Price | 0 | Qty | Unit Price | 0 | Qty | Unit Price | 0 | Qty | Unit Price | 0 | Qty | Unit Price | 0 | Qty | Unit Price | 0 | Qty | Unit Price | 0 | Qty | Unit Price | 0 | Qty | Unit Price | 0 | Qty | Unit Price | 0 | Qty | Unit Price | 0
|  | Dry Hole Based | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  | 1 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 1 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  | 1 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 1 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  | 1 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 1 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[22 empty] | 0 | 0 | 0
| Line | DESCRIPTION | Historical |  |  | Proposed Original |  |  |  | EVALUATED |  |  | Historical |  |  | Proposed Original |  |  | EVALUATED |  |  | 0 | 0 | 0 | Historical |  |  | Proposed Original |  |  | EVALUATED |  |  | Historical |  |  | Proposed Original |  |  | EVALUATED |  |  | Historical |  |  | Proposed Original |  |  | EVALUATED |  |  | Historical |  |  | Proposed Original |  |  | EVALUATED |  |  | Historical |  |  | Proposed Original |  |  | EVALUATED |  |  | Historical |  |  | Proposed Original |  |  | EVALUATED |  |  | Historical |  |  | Proposed Original |  |  | EVALUATED |  |  | Historical |  |  | Proposed Original |  |  | EVALUATED |  |  | Variance (Aw vs Ak) |  | Justifikasi Teknis | Data Pendukung
[22 empty] | 0 | 0 | 0 | [72 empty] | Quantity | Unit price
| 16 | Rigging Up / Rigging Down | Qty | Unit Price | 0 | Unit | Qty | Unit Price | 105341.5808 | Qty | Unit Price | 105341.5808 | Qty | Unit Price | 0 | Qty | Unit Price | 16030.2405 | Qty | Unit Price | 16030.2405 | 0 | 0 | 0 | Qty | Unit Price | 0 | Qty | Unit Price | 16030.2405 | Qty | Unit Price | 16030.2405 | Qty | Unit Price | 0 | Qty | Unit Price | 16030.2405 | Qty | Unit Price | 16030.2405 | Qty | Unit Price | 0 | Qty | Unit Price | 16030.2405 | Qty | Unit Price | 16030.2405 | Qty | Unit Price | 0 | Qty | Unit Price | 20610.3093 | Qty | Unit Price | 20610.3093 | Qty | Unit Price | 0 | Qty | Unit Price | 20610.3093 | Qty | Unit Price | 20610.3093 | Qty | Unit Price | 0 | Qty | Unit Price | 0 | Qty | Unit Price | 0 | Qty | Unit Price | 0 | Qty | Unit Price | 0 | Qty | Unit Price | 0 | Qty | Unit Price | 0 | Qty | Unit Price | 0 | Qty | Unit Price | 0
|  | Rig Moving 350HP (No TDS) | 0 | 0 | 0 |  | 6 | 4389.2325 | 26335.3952 | 6 | 4389.2325 | 26335.3952 | 0 | 0 | 0 | 1 | 4007.5601 | 4007.5601 | 1 | 4007.5601 | 4007.5601 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 4007.5601 | 4007.5601 | 1 | 4007.5601 | 4007.5601 | 0 | 0 | 0 | 1 | 4007.5601 | 4007.5601 | 1 | 4007.5601 | 4007.5601 | 0 | 0 | 0 | 1 | 4007.5601 | 4007.5601 | 1 | 4007.5601 | 4007.5601 | 0 | 0 | 0 | 1 | 5152.5773 | 5152.5773 | 1 | 5152.5773 | 5152.5773 | 0 | 0 | 0 | 1 | 5152.5773 | 5152.5773 | 1 | 5152.5773 | 5152.5773 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Rig Up & Rig Down 350HP (No TDS) | 0 | 0 | 0 |  | 18 | 4389.2325 | 79006.1856 | 18 | 4389.2325 | 79006.1856 | 0 |  | 0 | 3 | 4007.5601 | 12022.6804 | 3 | 4007.5601 | 12022.6804 | 0 | 0 | 0 | 0 | 0 | 0 | 3 | 4007.5601 | 12022.6804 | 3 | 4007.5601 | 12022.6804 | 0 | 0 | 0 | 3 | 4007.5601 | 12022.6804 | 3 | 4007.5601 | 12022.6804 | 0 | 0 | 0 | 3 | 4007.5601 | 12022.6804 | 3 | 4007.5601 | 12022.6804 | 0 | 0 | 0 | 3 | 5152.5773 | 15457.732 | 3 | 5152.5773 | 15457.732 | 0 | 0 | 0 | 3 | 5152.5773 | 15457.732 | 3 | 5152.5773 | 15457.732 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | MOVING LAUT | 1 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[22 empty] | 0 | 0 | 0
[22 empty] | 0 | 0 | 0
| Line | DESCRIPTION | Historical |  |  | Proposed Original |  |  |  | EVALUATED |  |  | Historical |  |  | Proposed Original |  |  | EVALUATED |  |  | 0 | 0 | 0 | Historical |  |  | Proposed Original |  |  | EVALUATED |  |  | Historical |  |  | Proposed Original |  |  | EVALUATED |  |  | Historical |  |  | Proposed Original |  |  | EVALUATED |  |  | Historical |  |  | Proposed Original |  |  | EVALUATED |  |  | Historical |  |  | Proposed Original |  |  | EVALUATED |  |  | Historical |  |  | Proposed Original |  |  | EVALUATED |  |  | Historical |  |  | Proposed Original |  |  | EVALUATED |  |  | Historical |  |  | Proposed Original |  |  | EVALUATED |  |  | Variance (Aw vs Ak) |  | Justifikasi Teknis | Data Pendukung
[22 empty] | 0 | 0 | 0 | [72 empty] | Quantity | Unit price
| 18 | DRILLING/WORKOVER OPERATIONS |  |  | 0 |  |  |  | 734330.0266 |  |  | 733284.1976 |  |  | 0 |  |  | 108504.0117 |  |  | 108320.4163 | 0 | 0 | -183.5954 |  |  | 0 |  |  | 108504.0117 |  |  | 108320.4163 |  |  | 0 |  |  | 108504.0117 |  |  | 108320.4163 |  |  | 0 |  |  | 108504.0117 |  |  | 108320.4163 |  |  | 0 |  |  | 150156.9899 |  |  | 150001.2662 |  |  | 0 |  |  | 150156.9899 |  |  | 150001.2662 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0
| 19 | Contract Rig | Qty | Unit Price | 0 | Unit | Qty | Unit Price | 672416.953 | Qty | Unit Price | 672416.953 | Qty | Unit Price | 0 | Qty | Unit Price | 97635.1661 | Qty | Unit Price | 97635.1661 | 0 | 0 | 0 | Qty | Unit Price | 0 | Qty | Unit Price | 97635.1661 | Qty | Unit Price | 97635.1661 | Qty | Unit Price | 0 | Qty | Unit Price | 97635.1661 | Qty | Unit Price | 97635.1661 | Qty | Unit Price | 0 | Qty | Unit Price | 97635.1661 | Qty | Unit Price | 97635.1661 | Qty | Unit Price | 0 | Qty | Unit Price | 140938.1443 | Qty | Unit Price | 140938.1443 | Qty | Unit Price | 0 | Qty | Unit Price | 140938.1443 | Qty | Unit Price | 140938.1443 | Qty | Unit Price | 0 | Qty | Unit Price | 0 | Qty | Unit Price | 0 | Qty | Unit Price | 0 | Qty | Unit Price | 0 | Qty | Unit Price | 0 | Qty | Unit Price | 0 | Qty | Unit Price | 0 | Qty | Unit Price | 0
|  | Dry Hole Based | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Operation Rig Cost 350HP (No TDS) | 0 | 0 | 0 |  | 129.3333 | 5199.1002 | 672416.953 | 129.3333 | 5199.1002 | 672416.953 | 0 | 0 | 0 | 20.7083 | 4714.7766 | 97635.1661 | 20.7083 | 4714.7766 | 97635.1661 | 0 | 0 | 0 | 0 | 0 | 0 | 20.7083 | 4714.7766 | 97635.1661 | 20.7083 | 4714.7766 | 97635.1661 | 0 | 0 | 0 | 20.7083 | 4714.7766 | 97635.1661 | 20.7083 | 4714.7766 | 97635.1661 | 0 | 0 | 0 | 20.7083 | 4714.7766 | 97635.1661 | 20.7083 | 4714.7766 | 97635.1661 | 0 | 0 | 0 | 23.25 | 6061.8557 | 140938.1443 | 23.25 | 6061.8557 | 140938.1443 | 0 | 0 | 0 | 23.25 | 6061.8557 | 140938.1443 | 23.25 | 6061.8557 | 140938.1443 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Completion Based | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | OPERASI | 0 | 0 | 0 |  | 0 | 0 | 0 | 35.6917 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 35.6917 | 0 | 0 | 35.6917 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 35.6917 | 0
|  | POMPA LUMPUR TAMBAHAN | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | SHALE SHAKER TAMBAHAN | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[22 empty] | 0 | 0 | 0
| Line | DESCRIPTION | Historical |  |  | Proposed Original |  |  |  | EVALUATED |  |  | Historical |  |  | Proposed Original |  |  | EVALUATED |  |  | 0 | 0 | 0 | Historical |  |  | Proposed Original |  |  | EVALUATED |  |  | Historical |  |  | Proposed Original |  |  | EVALUATED |  |  | Historical |  |  | Proposed Original |  |  | EVALUATED |  |  | Historical |  |  | Proposed Original |  |  | EVALUATED |  |  | Historical |  |  | Proposed Original |  |  | EVALUATED |  |  | Historical |  |  | Proposed Original |  |  | EVALUATED |  |  | Historical |  |  | Proposed Original |  |  | EVALUATED |  |  | Historical |  |  | Proposed Original |  |  | EVALUATED |  |  | Variance (Aw vs Ak) |  | Justifikasi Teknis | Data Pendukung
[22 empty] | 0 | 0 | 0 | [72 empty] | Quantity | Unit price
| 20 | Drilling Rig Crew/ Contract Rig Crew | Qty | Unit Price | 0 | Unit | Qty | Unit Price | 0 | Qty | Unit Price | 0 | Qty | Unit Price | 0 | Qty | Unit Price | 0 | Qty | Unit Price | 0 | 0 | 0 | 0 | Qty | Unit Price | 0 | Qty | Unit Price | 0 | Qty | Unit Price | 0 | Qty | Unit Price | 0 | Qty | Unit Price | 0 | Qty | Unit Price | 0 | Qty | Unit Price | 0 | Qty | Unit Price | 0 | Qty | Unit Price | 0 | Qty | Unit Price | 0 | Qty | Unit Price | 0 | Qty | Unit Price | 0 | Qty | Unit Price | 0 | Qty | Unit Price | 0 | Qty | Unit Price | 0 | Qty | Unit Price | 0 | Qty | Unit Price | 0 | Qty | Unit Price | 0 | Qty | Unit Price | 0 | Qty | Unit Price | 0 | Qty | Unit Price | 0 | Qty | Unit Price | 0 | Qty | Unit Price | 0 | Qty | Unit Price | 0
|  |  | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[22 empty] | 0 | 0 | 0
| Line | DESCRIPTION | Historical |  |  | Proposed Original |  |  |  | EVALUATED |  |  | Historical |  |  | Proposed Original |  |  | EVALUATED |  |  | 0 | 0 | 0 | Historical |  |  | Proposed Original |  |  | EVALUATED |  |  | Historical |  |  | Proposed Original |  |  | EVALUATED |  |  | Historical |  |  | Proposed Original |  |  | EVALUATED |  |  | Historical |  |  | Proposed Original |  |  | EVALUATED |  |  | Historical |  |  | Proposed Original |  |  | EVALUATED |  |  | Historical |  |  | Proposed Original |  |  | EVALUATED |  |  | Historical |  |  | Proposed Original |  |  | EVALUATED |  |  | Historical |  |  | Proposed Original |  |  | EVALUATED |  |  | Variance (Aw vs Ak) |  | Justifikasi Teknis | Data Pendukung
[22 empty] | 0 | 0 | 0 | [72 empty] | Quantity | Unit price
| 21 | Mud, Chemical & Engin. Services | Qty | Unit Price | 0 | Unit | Qty | Unit Price | 38664.0862 | Qty | Unit Price | 38010.9767 | Qty | Unit Price | 0 | Qty | Unit Price | 6444.0144 | Qty | Unit Price | 6335.1628 | 0 | 0 | -108.8516 | Qty | Unit Price | 0 | Qty | Unit Price | 6444.0144 | Qty | Unit Price | 6335.1628 | Qty | Unit Price | 0 | Qty | Unit Price | 6444.0144 | Qty | Unit Price | 6335.1628 | Qty | Unit Price | 0 | Qty | Unit Price | 6444.0144 | Qty | Unit Price | 6335.1628 | Qty | Unit Price | 0 | Qty | Unit Price | 6444.0144 | Qty | Unit Price | 6335.1628 | Qty | Unit Price | 0 | Qty | Unit Price | 6444.0144 | Qty | Unit Price | 6335.1628 | Qty | Unit Price | 0 | Qty | Unit Price | 0 | Qty | Unit Price | 0 | Qty | Unit Price | 0 | Qty | Unit Price | 0 | Qty | Unit Price | 0 | Qty | Unit Price | 0 | Qty | Unit Price | 0 | Qty | Unit Price | 0
|  | Dry Hole Based | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | MUD, CHEMICAL & ENG SERVICES | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | MUD, CHEMICAL & ENG SERVICES | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | POTASSIUM CHLORIDE (KCl) | 0 | 0 | 0 |  | 1200 | 20.98 | 25176 | 1200 | 20.6256 | 24750.7297 |  |  | 0 | 200 | 20.98 | 4196 | 200 | 20.6256 | 4125.1216 | 0 | -0.35439 | -70.8784 | 0 | 0 | 0 | 200 | 20.98 | 4196 | 200 | 20.6256 | 4125.1216 | 0 | 0 | 0 | 200 | 20.98 | 4196 | 200 | 20.6256 | 4125.1216 | 0 | 0 | 0 | 200 | 20.98 | 4196 | 200 | 20.6256 | 4125.1216 | 0 | 0 | 0 | 200 | 20.98 | 4196 | 200 | 20.6256 | 4125.1216 | 0 | 0 | 0 | 200 | 20.98 | 4196 | 200 | 20.6256 | 4125.1216 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -0.35439
|  | Corrosion Inhibitor (BEKA-4612) | 0 | 0 | 0 |  | 6 | 1086.9403 | 6521.6418 | 6 | 1068.5798 | 6411.4789 |  |  | 0 | 1 | 1086.9403 | 1086.9403 | 1 | 1068.5798 | 1068.5798 | 0 | -18.3605 | -18.3605 | 0 | 0 | 0 | 1 | 1086.9403 | 1086.9403 | 1 | 1068.5798 | 1068.5798 | 0 | 0 | 0 | 1 | 1086.9403 | 1086.9403 | 1 | 1068.5798 | 1068.5798 | 0 | 0 | 0 | 1 | 1086.9403 | 1086.9403 | 1 | 1068.5798 | 1068.5798 | 0 | 0 | 0 | 1 | 1086.9403 | 1086.9403 | 1 | 1068.5798 | 1068.5798 | 0 | 0 | 0 | 1 | 1086.9403 | 1086.9403 | 1 | 1068.5798 | 1068.5798 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -18.3605
|  | Tawas | 0 | 0 | 0 |  | 3000 | 0.29815 | 894.4444 | 3000 | 0.29311 | 879.3356 |  |  | 0 | 500 | 0.29815 | 149.0741 | 500 | 0.29311 | 146.5559 | 0 | -0.0050363 | -2.5181 | 0 | 0 | 0 | 500 | 0.29815 | 149.0741 | 500 | 0.29311 | 146.5559 | 0 | 0 | 0 | 500 | 0.29815 | 149.0741 | 500 | 0.29311 | 146.5559 | 0 | 0 | 0 | 500 | 0.29815 | 149.0741 | 500 | 0.29311 | 146.5559 | 0 | 0 | 0 | 500 | 0.29815 | 149.0741 | 500 | 0.29311 | 146.5559 | 0 | 0 | 0 | 500 | 0.29815 | 149.0741 | 500 | 0.29311 | 146.5559 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -0.0050363
|  | XCD | 0 | 0 | 0 |  | 60 | 101.2 | 6072 | 60 | 99.4905 | 5969.4324 | 0 | 0 | 0 | 10 | 101.2 | 1012 | 10 | 99.4905 | 994.9054 | 0 | -1.7095 | -17.0946 | 0 | 0 | 0 | 10 | 101.2 | 1012 | 10 | 99.4905 | 994.9054 | 0 | 0 | 0 | 10 | 101.2 | 1012 | 10 | 99.4905 | 994.9054 | 0 | 0 | 0 | 10 | 101.2 | 1012 | 10 | 99.4905 | 994.9054 | 0 | 0 | 0 | 10 | 101.2 | 1012 | 10 | 99.4905 | 994.9054 | 0 | 0 | 0 | 10 | 101.2 | 1012 | 10 | 99.4905 | 994.9054 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -1.7095
|  |  | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[22 empty] | 0 | 0 | 0
| Line | DESCRIPTION | Historical |  |  | Proposed Original |  |  |  | EVALUATED |  |  | Historical |  |  | Proposed Original |  |  | EVALUATED |  |  | 0 | 0 | 0 | Historical |  |  | Proposed Original |  |  | EVALUATED |  |  | Historical |  |  | Proposed Original |  |  | EVALUATED |  |  | Historical |  |  | Proposed Original |  |  | EVALUATED |  |  | Historical |  |  | Proposed Original |  |  | EVALUATED |  |  | Historical |  |  | Proposed Original |  |  | EVALUATED |  |  | Historical |  |  | Proposed Original |  |  | EVALUATED |  |  | Historical |  |  | Proposed Original |  |  | EVALUATED |  |  | Historical |  |  | Proposed Original |  |  | EVALUATED |  |  | Variance (Aw vs Ak) |  | Justifikasi Teknis | Data Pendukung
[22 empty] | 0 | 0 | 0 | [72 empty] | Quantity | Unit price
| 22 | Water | Qty | Unit Price | 0 | Unit | Qty | Unit Price | 0 | Qty | Unit Price | 0 | Qty | Unit Price | 0 | Qty | Unit Price | 0 | Qty | Unit Price | 0 | 0 | 0 | 0 | Qty | Unit Price | 0 | Qty | Unit Price | 0 | Qty | Unit Price | 0 | Qty | Unit Price | 0 | Qty | Unit Price | 0 | Qty | Unit Price | 0 | Qty | Unit Price | 0 | Qty | Unit Price | 0 | Qty | Unit Price | 0 | Qty | Unit Price | 0 | Qty | Unit Price | 0 | Qty | Unit Price | 0 | Qty | Unit Price | 0 | Qty | Unit Price | 0 | Qty | Unit Price | 0 | Qty | Unit Price | 0 | Qty | Unit Price | 0 | Qty | Unit Price | 0 | Qty | Unit Price | 0 | Qty | Unit Price | 0 | Qty | Unit Price | 0 | Qty | Unit Price | 0 | Qty | Unit Price | 0 | Qty | Unit Price | 0
|  | Dry Hole Based | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[22 empty] | 0 | 0 | 0
| Line | DESCRIPTION | Historical |  |  | Proposed Original |  |  |  | EVALUATED |  |  | Historical |  |  | Proposed Original |  |  | EVALUATED |  |  | 0 | 0 | 0 | Historical |  |  | Proposed Original |  |  | EVALUATED |  |  | Historical |  |  | Proposed Original |  |  | EVALUATED |  |  | Historical |  |  | Proposed Original |  |  | EVALUATED |  |  | Historical |  |  | Proposed Original |  |  | EVALUATED |  |  | Historical |  |  | Proposed Original |  |  | EVALUATED |  |  | Historical |  |  | Proposed Original |  |  | EVALUATED |  |  | Historical |  |  | Proposed Original |  |  | EVALUATED |  |  | Historical |  |  | Proposed Original |  |  | EVALUATED |  |  | Variance (Aw vs Ak) |  | Justifikasi Teknis | Data Pendukung
[22 empty] | 0 | 0 | 0 | [72 empty] | Quantity | Unit price
| 23 | Bit, Reamers and Coreheads | Qty | Unit Price | 0 | Unit | Qty | Unit Price | 23248.9873 | Qty | Unit Price | 22856.2679 | Qty | Unit Price | 0 | Qty | Unit Price | 4424.8312 | Qty | Unit Price | 4350.0874 | 0 | 0 | -74.7438 | Qty | Unit Price | 0 | Qty | Unit Price | 4424.8312 | Qty | Unit Price | 4350.0874 | Qty | Unit Price | 0 | Qty | Unit Price | 4424.8312 | Qty | Unit Price | 4350.0874 | Qty | Unit Price | 0 | Qty | Unit Price | 4424.8312 | Qty | Unit Price | 4350.0874 | Qty | Unit Price | 0 | Qty | Unit Price | 2774.8312 | Qty | Unit Price | 2727.9591 | Qty | Unit Price | 0 | Qty | Unit Price | 2774.8312 | Qty | Unit Price | 2727.9591 | Qty | Unit Price | 0 | Qty | Unit Price | 0 | Qty | Unit Price | 0 | Qty | Unit Price | 0 | Qty | Unit Price | 0 | Qty | Unit Price | 0 | Qty | Unit Price | 0 | Qty | Unit Price | 0 | Qty | Unit Price | 0
|  | Rock Bit 6 in, IADC 217 | 0 | 0 | 0 |  | 6 | 2774.8312 | 16648.9873 | 6 | 2727.9591 | 16367.7544 |  |  | 0 | 1 | 2774.8312 | 2774.8312 | 1 | 2727.9591 | 2727.9591 | 0 | -46.8721 | -46.8721 | 0 | 0 | 0 | 1 | 2774.8312 | 2774.8312 | 1 | 2727.9591 | 2727.9591 | 0 | 0 | 0 | 1 | 2774.8312 | 2774.8312 | 1 | 2727.9591 | 2727.9591 | 0 | 0 | 0 | 1 | 2774.8312 | 2774.8312 | 1 | 2727.9591 | 2727.9591 | 0 | 0 | 0 | 1 | 2774.8312 | 2774.8312 | 1 | 2727.9591 | 2727.9591 | 0 | 0 | 0 | 1 | 2774.8312 | 2774.8312 | 1 | 2727.9591 | 2727.9591 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -46.8721
|  | Rock Bit 5 1/4 in, IADC 211 | 0 | 0 | 0 |  | 4 | 1200 | 4800 | 4 | 1179.7297 | 4718.9189 |  |  | 0 | 1 | 1200 | 1200 | 1 | 1179.7297 | 1179.7297 | 0 | -20.2703 | -20.2703 | 0 | 0 | 0 | 1 | 1200 | 1200 | 1 | 1179.7297 | 1179.7297 | 0 | 0 | 0 | 1 | 1200 | 1200 | 1 | 1179.7297 | 1179.7297 | 0 | 0 | 0 | 1 | 1200 | 1200 | 1 | 1179.7297 | 1179.7297 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -20.2703
|  | Rock Bit 3 3/4 in, IADC 211 | 0 | 0 | 0 |  | 4 | 450 | 1800 | 4 | 442.3986 | 1769.5946 |  |  | 0 | 1 | 450 | 450 | 1 | 442.3986 | 442.3986 | 0 | -7.6014 | -7.6014 | 0 | 0 | 0 | 1 | 450 | 450 | 1 | 442.3986 | 442.3986 | 0 | 0 | 0 | 1 | 450 | 450 | 1 | 442.3986 | 442.3986 | 0 | 0 | 0 | 1 | 450 | 450 | 1 | 442.3986 | 442.3986 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -7.6014
|  |  | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[22 empty] | 0 | 0 | 0
| Line | DESCRIPTION | Historical |  |  | Proposed Original |  |  |  | EVALUATED |  |  | Historical |  |  | Proposed Original |  |  | EVALUATED |  |  | 0 | 0 | 0 | Historical |  |  | Proposed Original |  |  | EVALUATED |  |  | Historical |  |  | Proposed Original |  |  | EVALUATED |  |  | Historical |  |  | Proposed Original |  |  | EVALUATED |  |  | Historical |  |  | Proposed Original |  |  | EVALUATED |  |  | Historical |  |  | Proposed Original |  |  | EVALUATED |  |  | Historical |  |  | Proposed Original |  |  | EVALUATED |  |  | Historical |  |  | Proposed Original |  |  | EVALUATED |  |  | Historical |  |  | Proposed Original |  |  | EVALUATED |  |  | Variance (Aw vs Ak) |  | Justifikasi Teknis | Data Pendukung
[22 empty] | 0 | 0 | 0 | [72 empty] | Quantity | Unit price
| 24 | Equipments Rental | Qty | Unit Price | 0 | Unit | Qty | Unit Price | 0 | Qty | Unit Price | 0 | Qty | Unit Price | 0 | Qty | Unit Price | 0 | Qty | Unit Price | 0 | 0 | 0 | 0 | Qty | Unit Price | 0 | Qty | Unit Price | 0 | Qty | Unit Price | 0 | Qty | Unit Price | 0 | Qty | Unit Price | 0 | Qty | Unit Price | 0 | Qty | Unit Price | 0 | Qty | Unit Price | 0 | Qty | Unit Price | 0 | Qty | Unit Price | 0 | Qty | Unit Price | 0 | Qty | Unit Price | 0 | Qty | Unit Price | 0 | Qty | Unit Price | 0 | Qty | Unit Price | 0 | Qty | Unit Price | 0 | Qty | Unit Price | 0 | Qty | Unit Price | 0 | Qty | Unit Price | 0 | Qty | Unit Price | 0 | Qty | Unit Price | 0 | Qty | Unit Price | 0 | Qty | Unit Price | 0 | Qty | Unit Price | 0
|  | Dry Hole Based | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | [6 empty] | 0 | 0 | 0
|  |  | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | [6 empty] | 0 | 0 | 0
|  |  | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | [6 empty] | 0 | 0 | 0
|  |  | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | [6 empty] | 0 | 0 | 0
|  |  | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[22 empty] | 0 | 0 | 0
| Line | DESCRIPTION | Historical |  |  | Proposed Original |  |  |  | EVALUATED |  |  | Historical |  |  | Proposed Original |  |  | EVALUATED |  |  | 0 | 0 | 0 | Historical |  |  | Proposed Original |  |  | EVALUATED |  |  | Historical |  |  | Proposed Original |  |  | EVALUATED |  |  | Historical |  |  | Proposed Original |  |  | EVALUATED |  |  | Historical |  |  | Proposed Original |  |  | EVALUATED |  |  | Historical |  |  | Proposed Original |  |  | EVALUATED |  |  | Historical |  |  | Proposed Original |  |  | EVALUATED |  |  | Historical |  |  | Proposed Original |  |  | EVALUATED |  |  | Historical |  |  | Proposed Original |  |  | EVALUATED |  |  | Variance (Aw vs Ak) |  | Justifikasi Teknis | Data Pendukung
[22 empty] | 0 | 0 | 0 | [72 empty] | Quantity | Unit price
| 25 | Directional Drilling and Surveys | Qty | Unit Price | 0 | Unit | Qty | Unit Price | 0 | Qty | Unit Price | 0 | Qty | Unit Price | 0 | Qty | Unit Price | 0 | Qty | Unit Price | 0 | 0 | 0 | 0 | Qty | Unit Price | 0 | Qty | Unit Price | 0 | Qty | Unit Price | 0 | Qty | Unit Price | 0 | Qty | Unit Price | 0 | Qty | Unit Price | 0 | Qty | Unit Price | 0 | Qty | Unit Price | 0 | Qty | Unit Price | 0 | Qty | Unit Price | 0 | Qty | Unit Price | 0 | Qty | Unit Price | 0 | Qty | Unit Price | 0 | Qty | Unit Price | 0 | Qty | Unit Price | 0 | Qty | Unit Price | 0 | Qty | Unit Price | 0 | Qty | Unit Price | 0 | Qty | Unit Price | 0 | Qty | Unit Price | 0 | Qty | Unit Price | 0 | Qty | Unit Price | 0 | Qty | Unit Price | 0 | Qty | Unit Price | 0
|  |  | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[22 empty] | 0 | 0 | 0
| Line | DESCRIPTION | Historical |  |  | Proposed Original |  |  |  | EVALUATED |  |  | Historical |  |  | Proposed Original |  |  | EVALUATED |  |  | 0 | 0 | 0 | Historical |  |  | Proposed Original |  |  | EVALUATED |  |  | Historical |  |  | Proposed Original |  |  | EVALUATED |  |  | Historical |  |  | Proposed Original |  |  | EVALUATED |  |  | Historical |  |  | Proposed Original |  |  | EVALUATED |  |  | Historical |  |  | Proposed Original |  |  | EVALUATED |  |  | Historical |  |  | Proposed Original |  |  | EVALUATED |  |  | Historical |  |  | Proposed Original |  |  | EVALUATED |  |  | Historical |  |  | Proposed Original |  |  | EVALUATED |  |  | Variance (Aw vs Ak) |  | Justifikasi Teknis | Data Pendukung
[22 empty] | 0 | 0 | 0 | [72 empty] | Quantity | Unit price
| 26 | Diving Service | Qty | Unit Price | 0 | Unit | Qty | Unit Price | 0 | Qty | Unit Price | 0 | Qty | Unit Price | 0 | Qty | Unit Price | 0 | Qty | Unit Price | 0 | 0 | 0 | 0 | Qty | Unit Price | 0 | Qty | Unit Price | 0 | Qty | Unit Price | 0 | Qty | Unit Price | 0 | Qty | Unit Price | 0 | Qty | Unit Price | 0 | Qty | Unit Price | 0 | Qty | Unit Price | 0 | Qty | Unit Price | 0 | Qty | Unit Price | 0 | Qty | Unit Price | 0 | Qty | Unit Price | 0 | Qty | Unit Price | 0 | Qty | Unit Price | 0 | Qty | Unit Price | 0 | Qty | Unit Price | 0 | Qty | Unit Price | 0 | Qty | Unit Price | 0 | Qty | Unit Price | 0 | Qty | Unit Price | 0 | Qty | Unit Price | 0 | Qty | Unit Price | 0 | Qty | Unit Price | 0 | Qty | Unit Price | 0
|  |  | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[22 empty] | 0 | 0 | 0
| Line | DESCRIPTION | Historical |  |  | Proposed Original |  |  |  | EVALUATED |  |  | Historical |  |  | Proposed Original |  |  | EVALUATED |  |  | 0 | 0 | 0 | Historical |  |  | Proposed Original |  |  | EVALUATED |  |  | Historical |  |  | Proposed Original |  |  | EVALUATED |  |  | Historical |  |  | Proposed Original |  |  | EVALUATED |  |  | Historical |  |  | Proposed Original |  |  | EVALUATED |  |  | Historical |  |  | Proposed Original |  |  | EVALUATED |  |  | Historical |  |  | Proposed Original |  |  | EVALUATED |  |  | Historical |  |  | Proposed Original |  |  | EVALUATED |  |  | Historical |  |  | Proposed Original |  |  | EVALUATED |  |  | Variance (Aw vs Ak) |  | Justifikasi Teknis | Data Pendukung
[22 empty] | 0 | 0 | 0 | [72 empty] | Quantity | Unit price
| 27 | Casing Installation | Qty | Unit Price | 0 | Unit | Qty | Unit Price | 0 | Qty | Unit Price | 0 | Qty | Unit Price | 0 | Qty | Unit Price | 0 | Qty | Unit Price | 0 | 0 | 0 | 0 | Qty | Unit Price | 0 | Qty | Unit Price | 0 | Qty | Unit Price | 0 | Qty | Unit Price | 0 | Qty | Unit Price | 0 | Qty | Unit Price | 0 | Qty | Unit Price | 0 | Qty | Unit Price | 0 | Qty | Unit Price | 0 | Qty | Unit Price | 0 | Qty | Unit Price | 0 | Qty | Unit Price | 0 | Qty | Unit Price | 0 | Qty | Unit Price | 0 | Qty | Unit Price | 0 | Qty | Unit Price | 0 | Qty | Unit Price | 0 | Qty | Unit Price | 0 | Qty | Unit Price | 0 | Qty | Unit Price | 0 | Qty | Unit Price | 0 | Qty | Unit Price | 0 | Qty | Unit Price | 0 | Qty | Unit Price | 0
|  | CASING CHROME RUNNING TOOL 7" | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | TUBING CHROME RUNNING TOOL | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[22 empty] | 0 | 0 | 0
| Line | DESCRIPTION | Historical |  |  | Proposed Original |  |  |  | EVALUATED |  |  | Historical |  |  | Proposed Original |  |  | EVALUATED |  |  | 0 | 0 | 0 | Historical |  |  | Proposed Original |  |  | EVALUATED |  |  | Historical |  |  | Proposed Original |  |  | EVALUATED |  |  | Historical |  |  | Proposed Original |  |  | EVALUATED |  |  | Historical |  |  | Proposed Original |  |  | EVALUATED |  |  | Historical |  |  | Proposed Original |  |  | EVALUATED |  |  | Historical |  |  | Proposed Original |  |  | EVALUATED |  |  | Historical |  |  | Proposed Original |  |  | EVALUATED |  |  | Historical |  |  | Proposed Original |  |  | EVALUATED |  |  | Variance (Aw vs Ak) |  | Justifikasi Teknis | Data Pendukung
[22 empty] | 0 | 0 | 0 | [72 empty] | Quantity | Unit price
| 28 | Cement, Cementing and Pump Fees | Qty | Unit Price | 0 | Unit | Qty | Unit Price | 0 | Qty | Unit Price | 0 | Qty | Unit Price | 0 | Qty | Unit Price | 0 | Qty | Unit Price | 0 | 0 | 0 | 0 | Qty | Unit Price | 0 | Qty | Unit Price | 0 | Qty | Unit Price | 0 | Qty | Unit Price | 0 | Qty | Unit Price | 0 | Qty | Unit Price | 0 | Qty | Unit Price | 0 | Qty | Unit Price | 0 | Qty | Unit Price | 0 | Qty | Unit Price | 0 | Qty | Unit Price | 0 | Qty | Unit Price | 0 | Qty | Unit Price | 0 | Qty | Unit Price | 0 | Qty | Unit Price | 0 | Qty | Unit Price | 0 | Qty | Unit Price | 0 | Qty | Unit Price | 0 | Qty | Unit Price | 0 | Qty | Unit Price | 0 | Qty | Unit Price | 0 | Qty | Unit Price | 0 | Qty | Unit Price | 0 | Qty | Unit Price | 0
|  | Dry Hole Based | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[22 empty] | 0 | 0 | 0
[22 empty] | 0 | 0 | 0
| Line | DESCRIPTION | Historical |  |  | Proposed Original |  |  |  | EVALUATED |  |  | Historical |  |  | Proposed Original |  |  | EVALUATED |  |  | 0 | 0 | 0 | Historical |  |  | Proposed Original |  |  | EVALUATED |  |  | Historical |  |  | Proposed Original |  |  | EVALUATED |  |  | Historical |  |  | Proposed Original |  |  | EVALUATED |  |  | Historical |  |  | Proposed Original |  |  | EVALUATED |  |  | Historical |  |  | Proposed Original |  |  | EVALUATED |  |  | Historical |  |  | Proposed Original |  |  | EVALUATED |  |  | Historical |  |  | Proposed Original |  |  | EVALUATED |  |  | Historical |  |  | Proposed Original |  |  | EVALUATED |  |  | Variance (Aw vs Ak) |  | Justifikasi Teknis | Data Pendukung
[22 empty] | 0 | 0 | 0 | [72 empty] | Quantity | Unit price
| 30 | FORMATION EVALUATION |  |  | 0 |  |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 | 0 | 0 | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0
| 31 | Coring | Qty | Unit Price | 0 | Unit | Qty | Unit Price | 0 | Qty | Unit Price | 0 | Qty | Unit Price | 0 | Qty | Unit Price | 0 | Qty | Unit Price | 0 | 0 | 0 | 0 | Qty | Unit Price | 0 | Qty | Unit Price | 0 | Qty | Unit Price | 0 | Qty | Unit Price | 0 | Qty | Unit Price | 0 | Qty | Unit Price | 0 | Qty | Unit Price | 0 | Qty | Unit Price | 0 | Qty | Unit Price | 0 | Qty | Unit Price | 0 | Qty | Unit Price | 0 | Qty | Unit Price | 0 | Qty | Unit Price | 0 | Qty | Unit Price | 0 | Qty | Unit Price | 0 | Qty | Unit Price | 0 | Qty | Unit Price | 0 | Qty | Unit Price | 0 | Qty | Unit Price | 0 | Qty | Unit Price | 0 | Qty | Unit Price | 0 | Qty | Unit Price | 0 | Qty | Unit Price | 0 | Qty | Unit Price | 0
|  |  | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[22 empty] | 0 | 0 | 0
| Line | DESCRIPTION | Historical |  |  | Proposed Original |  |  |  | EVALUATED |  |  | Historical |  |  | Proposed Original |  |  | EVALUATED |  |  | 0 | 0 | 0 | Historical |  |  | Proposed Original |  |  | EVALUATED |  |  | Historical |  |  | Proposed Original |  |  | EVALUATED |  |  | Historical |  |  | Proposed Original |  |  | EVALUATED |  |  | Historical |  |  | Proposed Original |  |  | EVALUATED |  |  | Historical |  |  | Proposed Original |  |  | EVALUATED |  |  | Historical |  |  | Proposed Original |  |  | EVALUATED |  |  | Historical |  |  | Proposed Original |  |  | EVALUATED |  |  | Historical |  |  | Proposed Original |  |  | EVALUATED |  |  | Variance (Aw vs Ak) |  | Justifikasi Teknis | Data Pendukung
[22 empty] | 0 | 0 | 0 | [72 empty] | Quantity | Unit price
| 32 | Mud Logging services | Qty | Unit Price | 0 | Unit | Qty | Unit Price | 0 | Qty | Unit Price | 0 | Qty | Unit Price | 0 | Qty | Unit Price | 0 | Qty | Unit Price | 0 | 0 | 0 | 0 | Qty | Unit Price | 0 | Qty | Unit Price | 0 | Qty | Unit Price | 0 | Qty | Unit Price | 0 | Qty | Unit Price | 0 | Qty | Unit Price | 0 | Qty | Unit Price | 0 | Qty | Unit Price | 0 | Qty | Unit Price | 0 | Qty | Unit Price | 0 | Qty | Unit Price | 0 | Qty | Unit Price | 0 | Qty | Unit Price | 0 | Qty | Unit Price | 0 | Qty | Unit Price | 0 | Qty | Unit Price | 0 | Qty | Unit Price | 0 | Qty | Unit Price | 0 | Qty | Unit Price | 0 | Qty | Unit Price | 0 | Qty | Unit Price | 0 | Qty | Unit Price | 0 | Qty | Unit Price | 0 | Qty | Unit Price | 0
|  |  | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[22 empty] | 0 | 0 | 0
| Line | DESCRIPTION | Historical |  |  | Proposed Original |  |  |  | EVALUATED |  |  | Historical |  |  | Proposed Original |  |  | EVALUATED |  |  | 0 | 0 | 0 | Historical |  |  | Proposed Original |  |  | EVALUATED |  |  | Historical |  |  | Proposed Original |  |  | EVALUATED |  |  | Historical |  |  | Proposed Original |  |  | EVALUATED |  |  | Historical |  |  | Proposed Original |  |  | EVALUATED |  |  | Historical |  |  | Proposed Original |  |  | EVALUATED |  |  | Historical |  |  | Proposed Original |  |  | EVALUATED |  |  | Historical |  |  | Proposed Original |  |  | EVALUATED |  |  | Historical |  |  | Proposed Original |  |  | EVALUATED |  |  | Variance (Aw vs Ak) |  | Justifikasi Teknis | Data Pendukung
[22 empty] | 0 | 0 | 0 | [72 empty] | Quantity | Unit price
| 33 | Drill Stem Test | Qty | Unit Price | 0 | Unit | Qty | Unit Price | 0 | Qty | Unit Price | 0 | Qty | Unit Price | 0 | Qty | Unit Price | 0 | Qty | Unit Price | 0 | 0 | 0 | 0 | Qty | Unit Price | 0 | Qty | Unit Price | 0 | Qty | Unit Price | 0 | Qty | Unit Price | 0 | Qty | Unit Price | 0 | Qty | Unit Price | 0 | Qty | Unit Price | 0 | Qty | Unit Price | 0 | Qty | Unit Price | 0 | Qty | Unit Price | 0 | Qty | Unit Price | 0 | Qty | Unit Price | 0 | Qty | Unit Price | 0 | Qty | Unit Price | 0 | Qty | Unit Price | 0 | Qty | Unit Price | 0 | Qty | Unit Price | 0 | Qty | Unit Price | 0 | Qty | Unit Price | 0 | Qty | Unit Price | 0 | Qty | Unit Price | 0 | Qty | Unit Price | 0 | Qty | Unit Price | 0 | Qty | Unit Price | 0
|  |  | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[22 empty] | 0 | 0 | 0
| Line | DESCRIPTION | Historical |  |  | Proposed Original |  |  |  | EVALUATED |  |  | Historical |  |  | Proposed Original |  |  | EVALUATED |  |  | 0 | 0 | 0 | Historical |  |  | Proposed Original |  |  | EVALUATED |  |  | Historical |  |  | Proposed Original |  |  | EVALUATED |  |  | Historical |  |  | Proposed Original |  |  | EVALUATED |  |  | Historical |  |  | Proposed Original |  |  | EVALUATED |  |  | Historical |  |  | Proposed Original |  |  | EVALUATED |  |  | Historical |  |  | Proposed Original |  |  | EVALUATED |  |  | Historical |  |  | Proposed Original |  |  | EVALUATED |  |  | Historical |  |  | Proposed Original |  |  | EVALUATED |  |  | Variance (Aw vs Ak) |  | Justifikasi Teknis | Data Pendukung
[22 empty] | 0 | 0 | 0 | [72 empty] | Quantity | Unit price
| 34 | Open Hole Logging and Services | Qty | Unit Price | 0 | Unit | Qty | Unit Price | 0 | Qty | Unit Price | 0 | Qty | Unit Price | 0 | Qty | Unit Price | 0 | Qty | Unit Price | 0 | 0 | 0 | 0 | Qty | Unit Price | 0 | Qty | Unit Price | 0 | Qty | Unit Price | 0 | Qty | Unit Price | 0 | Qty | Unit Price | 0 | Qty | Unit Price | 0 | Qty | Unit Price | 0 | Qty | Unit Price | 0 | Qty | Unit Price | 0 | Qty | Unit Price | 0 | Qty | Unit Price | 0 | Qty | Unit Price | 0 | Qty | Unit Price | 0 | Qty | Unit Price | 0 | Qty | Unit Price | 0 | Qty | Unit Price | 0 | Qty | Unit Price | 0 | Qty | Unit Price | 0 | Qty | Unit Price | 0 | Qty | Unit Price | 0 | Qty | Unit Price | 0 | Qty | Unit Price | 0 | Qty | Unit Price | 0 | Qty | Unit Price | 0
|  |  | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  | 1 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 1 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  | 1 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 1 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  | 2 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 2 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  | 2 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 2 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  |  | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[22 empty] | 0 | 0 | 0
[22 empty] | 0 | 0 | 0
| Line | DESCRIPTION | Historical |  |  | Proposed Original |  |  |  | EVALUATED |  |  | Historical |  |  | Proposed Original |  |  | EVALUATED |  |  | 0 | 0 | 0 | Historical |  |  | Proposed Original |  |  | EVALUATED |  |  | Historical |  |  | Proposed Original |  |  | EVALUATED |  |  | Historical |  |  | Proposed Original |  |  | EVALUATED |  |  | Historical |  |  | Proposed Original |  |  | EVALUATED |  |  | Historical |  |  | Proposed Original |  |  | EVALUATED |  |  | Historical |  |  | Proposed Original |  |  | EVALUATED |  |  | Historical |  |  | Proposed Original |  |  | EVALUATED |  |  | Historical |  |  | Proposed Original |  |  | EVALUATED |  |  | Variance (Aw vs Ak) |  | Justifikasi Teknis | Data Pendukung
[22 empty] | 0 | 0 | 0 | [72 empty] | Quantity | Unit price
| 36 | COMPLETION |  |  | 0 |  |  |  | 1565547.7715 |  |  | 1496719.5997 |  |  | 0 |  |  | 187182.1304 |  |  | 173605.0674 | 0 | 0 | -13577.063 |  |  | 0 |  |  | 187182.1304 |  |  | 173605.0674 |  |  | 0 |  |  | 187182.1304 |  |  | 173605.0674 |  |  | 0 |  |  | 187182.1304 |  |  | 173605.0674 |  |  | 0 |  |  | 408409.6249 |  |  | 401149.665 |  |  | 0 |  |  | 408409.6249 |  |  | 401149.665 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0
| 37 | Casing, Liner and Tubing Installation | Qty | Unit Price | 0 | Unit | Qty | Unit Price | 0 | Qty | Unit Price | 0 | Qty | Unit Price | 0 | Qty | Unit Price | 0 | Qty | Unit Price | 0 | 0 | 0 | 0 | Qty | Unit Price | 0 | Qty | Unit Price | 0 | Qty | Unit Price | 0 | Qty | Unit Price | 0 | Qty | Unit Price | 0 | Qty | Unit Price | 0 | Qty | Unit Price | 0 | Qty | Unit Price | 0 | Qty | Unit Price | 0 | Qty | Unit Price | 0 | Qty | Unit Price | 0 | Qty | Unit Price | 0 | Qty | Unit Price | 0 | Qty | Unit Price | 0 | Qty | Unit Price | 0 | Qty | Unit Price | 0 | Qty | Unit Price | 0 | Qty | Unit Price | 0 | Qty | Unit Price | 0 | Qty | Unit Price | 0 | Qty | Unit Price | 0 | Qty | Unit Price | 0 | Qty | Unit Price | 0 | Qty | Unit Price | 0
|  |  | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[22 empty] | 0 | 0 | 0
| Line | DESCRIPTION | Historical |  |  | Proposed Original |  |  |  | EVALUATED |  |  | Historical |  |  | Proposed Original |  |  | EVALUATED |  |  | 0 | 0 | 0 | Historical |  |  | Proposed Original |  |  | EVALUATED |  |  | Historical |  |  | Proposed Original |  |  | EVALUATED |  |  | Historical |  |  | Proposed Original |  |  | EVALUATED |  |  | Historical |  |  | Proposed Original |  |  | EVALUATED |  |  | Historical |  |  | Proposed Original |  |  | EVALUATED |  |  | Historical |  |  | Proposed Original |  |  | EVALUATED |  |  | Historical |  |  | Proposed Original |  |  | EVALUATED |  |  | Historical |  |  | Proposed Original |  |  | EVALUATED |  |  | Variance (Aw vs Ak) |  | Justifikasi Teknis | Data Pendukung
[22 empty] | 0 | 0 | 0 | [72 empty] | Quantity | Unit price
| 38 | Cement, Cementing and Pump Fees | Qty | Unit Price | 0 | Unit | Qty | Unit Price | 132000 | Qty | Unit Price | 132000 | Qty | Unit Price | 0 | Qty | Unit Price | 22000 | Qty | Unit Price | 22000 | 0 | 0 | 0 | Qty | Unit Price | 0 | Qty | Unit Price | 22000 | Qty | Unit Price | 22000 | Qty | Unit Price | 0 | Qty | Unit Price | 22000 | Qty | Unit Price | 22000 | Qty | Unit Price | 0 | Qty | Unit Price | 22000 | Qty | Unit Price | 22000 | Qty | Unit Price | 0 | Qty | Unit Price | 22000 | Qty | Unit Price | 22000 | Qty | Unit Price | 0 | Qty | Unit Price | 22000 | Qty | Unit Price | 22000 | Qty | Unit Price | 0 | Qty | Unit Price | 0 | Qty | Unit Price | 0 | Qty | Unit Price | 0 | Qty | Unit Price | 0 | Qty | Unit Price | 0 | Qty | Unit Price | 0 | Qty | Unit Price | 0 | Qty | Unit Price | 0
|  | CEMENTS AND MATERIALS | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Plug Back Cementing Job | 0 | 0 | 0 |  | 6 | 10000 | 60000 | 6 | 10000 | 60000 |  |  | 0 | 1 | 10000 | 10000 | 1 | 10000 | 10000 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 10000 | 10000 | 1 | 10000 | 10000 | 0 | 0 | 0 | 1 | 10000 | 10000 | 1 | 10000 | 10000 | 0 | 0 | 0 | 1 | 10000 | 10000 | 1 | 10000 | 10000 | 0 | 0 | 0 | 1 | 10000 | 10000 | 1 | 10000 | 10000 | 0 | 0 | 0 | 1 | 10000 | 10000 | 1 | 10000 | 10000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Squeeze Cementing Job | 0 | 0 | 0 |  | 6 | 12000 | 72000 | 6 | 12000 | 72000 |  |  | 0 | 1 | 12000 | 12000 | 1 | 12000 | 12000 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 12000 | 12000 | 1 | 12000 | 12000 | 0 | 0 | 0 | 1 | 12000 | 12000 | 1 | 12000 | 12000 | 0 | 0 | 0 | 1 | 12000 | 12000 | 1 | 12000 | 12000 | 0 | 0 | 0 | 1 | 12000 | 12000 | 1 | 12000 | 12000 | 0 | 0 | 0 | 1 | 12000 | 12000 | 1 | 12000 | 12000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[22 empty] | 0 | 0 | 0
| Line | DESCRIPTION | Historical |  |  | Proposed Original |  |  |  | EVALUATED |  |  | Historical |  |  | Proposed Original |  |  | EVALUATED |  |  | 0 | 0 | 0 | Historical |  |  | Proposed Original |  |  | EVALUATED |  |  | Historical |  |  | Proposed Original |  |  | EVALUATED |  |  | Historical |  |  | Proposed Original |  |  | EVALUATED |  |  | Historical |  |  | Proposed Original |  |  | EVALUATED |  |  | Historical |  |  | Proposed Original |  |  | EVALUATED |  |  | Historical |  |  | Proposed Original |  |  | EVALUATED |  |  | Historical |  |  | Proposed Original |  |  | EVALUATED |  |  | Historical |  |  | Proposed Original |  |  | EVALUATED |  |  | Variance (Aw vs Ak) |  | Justifikasi Teknis | Data Pendukung
[22 empty] | 0 | 0 | 0 | [72 empty] | Quantity | Unit price
| 39 | Cased Hole Electrical Logging Services | Qty | Unit Price | 0 | Unit | Qty | Unit Price | 354000 | Qty | Unit Price | 313218.2432 | Qty | Unit Price | 0 | Qty | Unit Price | 59000 | Qty | Unit Price | 52203.0405 | 0 | 0 | -6796.9595 | Qty | Unit Price | 0 | Qty | Unit Price | 59000 | Qty | Unit Price | 52203.0405 | Qty | Unit Price | 0 | Qty | Unit Price | 59000 | Qty | Unit Price | 52203.0405 | Qty | Unit Price | 0 | Qty | Unit Price | 59000 | Qty | Unit Price | 52203.0405 | Qty | Unit Price | 0 | Qty | Unit Price | 59000 | Qty | Unit Price | 52203.0405 | Qty | Unit Price | 0 | Qty | Unit Price | 59000 | Qty | Unit Price | 52203.0405 | Qty | Unit Price | 0 | Qty | Unit Price | 0 | Qty | Unit Price | 0 | Qty | Unit Price | 0 | Qty | Unit Price | 0 | Qty | Unit Price | 0 | Qty | Unit Price | 0 | Qty | Unit Price | 0 | Qty | Unit Price | 0
|  | GR-CBL-VDL | 0 | 0 | 0 |  | 12 | 12000 | 144000 | 12 | 10617.5676 | 127410.8108 | 0 | 0 | 0 | 2 | 12000 | 24000 | 2 | 10617.5676 | 21235.1351 | 0 | -1382.4324 | -2764.8649 | 0 | 0 | 0 | 2 | 12000 | 24000 | 2 | 10617.5676 | 21235.1351 | 0 | 0 | 0 | 2 | 12000 | 24000 | 2 | 10617.5676 | 21235.1351 | 0 | 0 | 0 | 2 | 12000 | 24000 | 2 | 10617.5676 | 21235.1351 | 0 | 0 | 0 | 2 | 12000 | 24000 | 2 | 10617.5676 | 21235.1351 | 0 | 0 | 0 | 2 | 12000 | 24000 | 2 | 10617.5676 | 21235.1351 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -1382.4324
|  | GR-CBL-CNL | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | CASED HOLE LOG RST | 0 | 0 | 0 |  | 6 | 35000 | 210000 | 6 | 30967.9054 | 185807.4324 |  |  | 0 | 1 | 35000 | 35000 | 1 | 30967.9054 | 30967.9054 | 0 | -4032.0946 | -4032.0946 | 0 | 0 | 0 | 1 | 35000 | 35000 | 1 | 30967.9054 | 30967.9054 | 0 | 0 | 0 | 1 | 35000 | 35000 | 1 | 30967.9054 | 30967.9054 | 0 | 0 | 0 | 1 | 35000 | 35000 | 1 | 30967.9054 | 30967.9054 | 0 | 0 | 0 | 1 | 35000 | 35000 | 1 | 30967.9054 | 30967.9054 | 0 | 0 | 0 | 1 | 35000 | 35000 | 1 | 30967.9054 | 30967.9054 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -4032.0946 | Mengacu kepada pekerjaan serupa
|  | CASED HOLE LOG 7" : CBL-CCL-VDL | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[22 empty] | 0 | 0 | 0
| Line | DESCRIPTION | Historical |  |  | Proposed Original |  |  |  | EVALUATED |  |  | Historical |  |  | Proposed Original |  |  | EVALUATED |  |  | 0 | 0 | 0 | Historical |  |  | Proposed Original |  |  | EVALUATED |  |  | Historical |  |  | Proposed Original |  |  | EVALUATED |  |  | Historical |  |  | Proposed Original |  |  | EVALUATED |  |  | Historical |  |  | Proposed Original |  |  | EVALUATED |  |  | Historical |  |  | Proposed Original |  |  | EVALUATED |  |  | Historical |  |  | Proposed Original |  |  | EVALUATED |  |  | Historical |  |  | Proposed Original |  |  | EVALUATED |  |  | Historical |  |  | Proposed Original |  |  | EVALUATED |  |  | Variance (Aw vs Ak) |  | Justifikasi Teknis | Data Pendukung
[22 empty] | 0 | 0 | 0 | [72 empty] | Quantity | Unit price
| 40 | Perforating and Wireline Services | Qty | Unit Price | 0 | Unit | Qty | Unit Price | 162000 | Qty | Unit Price | 159263.5135 | Qty | Unit Price | 0 | Qty | Unit Price | 27000 | Qty | Unit Price | 26543.9189 | 0 | 0 | -456.0811 | Qty | Unit Price | 0 | Qty | Unit Price | 27000 | Qty | Unit Price | 26543.9189 | Qty | Unit Price | 0 | Qty | Unit Price | 27000 | Qty | Unit Price | 26543.9189 | Qty | Unit Price | 0 | Qty | Unit Price | 27000 | Qty | Unit Price | 26543.9189 | Qty | Unit Price | 0 | Qty | Unit Price | 27000 | Qty | Unit Price | 26543.9189 | Qty | Unit Price | 0 | Qty | Unit Price | 27000 | Qty | Unit Price | 26543.9189 | Qty | Unit Price | 0 | Qty | Unit Price | 0 | Qty | Unit Price | 0 | Qty | Unit Price | 0 | Qty | Unit Price | 0 | Qty | Unit Price | 0 | Qty | Unit Price | 0 | Qty | Unit Price | 0 | Qty | Unit Price | 0
|  | 4-1/2" HSD 6 SPF STD | 0 | 0 | 0 |  | 6 | 16000 | 96000 | 6 | 15729.7297 | 94378.3784 | 0 |  | 0 | 1 | 16000 | 16000 | 1 | 15729.7297 | 15729.7297 | 0 | -270.2703 | -270.2703 | 0 | 0 | 0 | 1 | 16000 | 16000 | 1 | 15729.7297 | 15729.7297 | 0 | 0 | 0 | 1 | 16000 | 16000 | 1 | 15729.7297 | 15729.7297 | 0 | 0 | 0 | 1 | 16000 | 16000 | 1 | 15729.7297 | 15729.7297 | 0 | 0 | 0 | 1 | 16000 | 16000 | 1 | 15729.7297 | 15729.7297 | 0 | 0 | 0 | 1 | 16000 | 16000 | 1 | 15729.7297 | 15729.7297 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -270.2703
|  | 4-1/2" HSD 12 SPF STD (REMEDIAL) | 0 | 0 | 0 |  | 6 | 11000 | 66000 | 6 | 10814.1892 | 64885.1351 | 0 | 0 | 0 | 1 | 11000 | 11000 | 1 | 10814.1892 | 10814.1892 | 0 | -185.8108 | -185.8108 | 0 | 0 | 0 | 1 | 11000 | 11000 | 1 | 10814.1892 | 10814.1892 | 0 | 0 | 0 | 1 | 11000 | 11000 | 1 | 10814.1892 | 10814.1892 | 0 | 0 | 0 | 1 | 11000 | 11000 | 1 | 10814.1892 | 10814.1892 | 0 | 0 | 0 | 1 | 11000 | 11000 | 1 | 10814.1892 | 10814.1892 | 0 | 0 | 0 | 1 | 11000 | 11000 | 1 | 10814.1892 | 10814.1892 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -185.8108
|  |  | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[22 empty] | 0 | 0 | 0
| Line | DESCRIPTION | Historical |  |  | Proposed Original |  |  |  | EVALUATED |  |  | Historical |  |  | Proposed Original |  |  | EVALUATED |  |  | 0 | 0 | 0 | Historical |  |  | Proposed Original |  |  | EVALUATED |  |  | Historical |  |  | Proposed Original |  |  | EVALUATED |  |  | Historical |  |  | Proposed Original |  |  | EVALUATED |  |  | Historical |  |  | Proposed Original |  |  | EVALUATED |  |  | Historical |  |  | Proposed Original |  |  | EVALUATED |  |  | Historical |  |  | Proposed Original |  |  | EVALUATED |  |  | Historical |  |  | Proposed Original |  |  | EVALUATED |  |  | Historical |  |  | Proposed Original |  |  | EVALUATED |  |  | Variance (Aw vs Ak) |  | Justifikasi Teknis | Data Pendukung
[22 empty] | 0 | 0 | 0 | [72 empty] | Quantity | Unit price
| 41 | Stimulation Treatment / Completion Fluids | Qty | Unit Price | 0 | Unit | Qty | Unit Price | 840000 | Qty | Unit Price | 816000 | Qty | Unit Price | 0 | Qty | Unit Price | 60000 | Qty | Unit Price | 54000 | 0 | 0 | -6000 | Qty | Unit Price | 0 | Qty | Unit Price | 60000 | Qty | Unit Price | 54000 | Qty | Unit Price | 0 | Qty | Unit Price | 60000 | Qty | Unit Price | 54000 | Qty | Unit Price | 0 | Qty | Unit Price | 60000 | Qty | Unit Price | 54000 | Qty | Unit Price | 0 | Qty | Unit Price | 300000 | Qty | Unit Price | 300000 | Qty | Unit Price | 0 | Qty | Unit Price | 300000 | Qty | Unit Price | 300000 | Qty | Unit Price | 0 | Qty | Unit Price | 0 | Qty | Unit Price | 0 | Qty | Unit Price | 0 | Qty | Unit Price | 0 | Qty | Unit Price | 0 | Qty | Unit Price | 0 | Qty | Unit Price | 0 | Qty | Unit Price | 0
|  | NITRIFIED ACIDIZING | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | UNLOADING NITROGEN | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | HYDRAULIC FRACTURING | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | STIMULATION ACID | 0 | 0 | 0 |  | 2 | 300000 | 600000 | 2 | 300000 | 600000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 300000 | 300000 | 1 | 300000 | 300000 | 0 | 0 | 0 | 1 | 300000 | 300000 | 1 | 300000 | 300000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Stimulasi (Acid, Solvent) / CTU | 0 | 0 | 0 |  | 4 | 60000 | 240000 | 4 | 54000 | 216000 | 0 | 0 | 0 | 1 | 60000 | 60000 | 1 | 54000 | 54000 | 0 | -6000 | -6000 | 0 | 0 | 0 | 1 | 60000 | 60000 | 1 | 54000 | 54000 | 0 | 0 | 0 | 1 | 60000 | 60000 | 1 | 54000 | 54000 | 0 | 0 | 0 | 1 | 60000 | 60000 | 1 | 54000 | 54000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -6000
|  |  | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[22 empty] | 0 | 0 | 0
| Line | DESCRIPTION | Historical |  |  | Proposed Original |  |  |  | EVALUATED |  |  | Historical |  |  | Proposed Original |  |  | EVALUATED |  |  | 0 | 0 | 0 | Historical |  |  | Proposed Original |  |  | EVALUATED |  |  | Historical |  |  | Proposed Original |  |  | EVALUATED |  |  | Historical |  |  | Proposed Original |  |  | EVALUATED |  |  | Historical |  |  | Proposed Original |  |  | EVALUATED |  |  | Historical |  |  | Proposed Original |  |  | EVALUATED |  |  | Historical |  |  | Proposed Original |  |  | EVALUATED |  |  | Historical |  |  | Proposed Original |  |  | EVALUATED |  |  | Historical |  |  | Proposed Original |  |  | EVALUATED |  |  | Variance (Aw vs Ak) |  | Justifikasi Teknis | Data Pendukung
[22 empty] | 0 | 0 | 0 | [72 empty] | Quantity | Unit price
| 42 | Production Test | Qty | Unit Price | 0 | Unit | Qty | Unit Price | 77547.7715 | Qty | Unit Price | 76237.8429 | Qty | Unit Price | 0 | Qty | Unit Price | 19182.1304 | Qty | Unit Price | 18858.108 | 0 | 0 | -324.0225 | Qty | Unit Price | 0 | Qty | Unit Price | 19182.1304 | Qty | Unit Price | 18858.108 | Qty | Unit Price | 0 | Qty | Unit Price | 19182.1304 | Qty | Unit Price | 18858.108 | Qty | Unit Price | 0 | Qty | Unit Price | 19182.1304 | Qty | Unit Price | 18858.108 | Qty | Unit Price | 0 | Qty | Unit Price | 409.6249 | Qty | Unit Price | 402.7055 | Qty | Unit Price | 0 | Qty | Unit Price | 409.6249 | Qty | Unit Price | 402.7055 | Qty | Unit Price | 0 | Qty | Unit Price | 0 | Qty | Unit Price | 0 | Qty | Unit Price | 0 | Qty | Unit Price | 0 | Qty | Unit Price | 0 | Qty | Unit Price | 0 | Qty | Unit Price | 0 | Qty | Unit Price | 0
|  | Rubber Swab 2.7/8" MV | 0 | 0 | 0 |  | 60 | 40.9625 | 2457.7493 | 60 | 40.2706 | 2416.2332 | 0 | 0 | 0 | 10 | 40.9625 | 409.6249 | 10 | 40.2706 | 402.7055 | 0 | -0.69193 | -6.9193 | 0 | 0 | 0 | 10 | 40.9625 | 409.6249 | 10 | 40.2706 | 402.7055 | 0 | 0 | 0 | 10 | 40.9625 | 409.6249 | 10 | 40.2706 | 402.7055 | 0 | 0 | 0 | 10 | 40.9625 | 409.6249 | 10 | 40.2706 | 402.7055 | 0 | 0 | 0 | 10 | 40.9625 | 409.6249 | 10 | 40.2706 | 402.7055 | 0 | 0 | 0 | 10 | 40.9625 | 409.6249 | 10 | 40.2706 | 402.7055 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -0.69193
|  | MIT-PBU TESTING | 0 | 0 | 0 |  | 4 | 18772.5056 | 75090.0223 | 4 | 18455.4024 | 73821.6097 | 0 |  | 0 | 1 | 18772.5056 | 18772.5056 | 1 | 18455.4024 | 18455.4024 | 0 | -317.1031 | -317.1031 | 0 | 0 | 0 | 1 | 18772.5056 | 18772.5056 | 1 | 18455.4024 | 18455.4024 | 0 | 0 | 0 | 1 | 18772.5056 | 18772.5056 | 1 | 18455.4024 | 18455.4024 | 0 | 0 | 0 | 1 | 18772.5056 | 18772.5056 | 1 | 18455.4024 | 18455.4024 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -317.1031
|  |  | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[22 empty] | 0 | 0 | 0
[22 empty] | 0 | 0 | 0
| Line | DESCRIPTION | Historical |  |  | Proposed Original |  |  |  | EVALUATED |  |  | Historical |  |  | Proposed Original |  |  | EVALUATED |  |  | 0 | 0 | 0 | Historical |  |  | Proposed Original |  |  | EVALUATED |  |  | Historical |  |  | Proposed Original |  |  | EVALUATED |  |  | Historical |  |  | Proposed Original |  |  | EVALUATED |  |  | Historical |  |  | Proposed Original |  |  | EVALUATED |  |  | Historical |  |  | Proposed Original |  |  | EVALUATED |  |  | Historical |  |  | Proposed Original |  |  | EVALUATED |  |  | Historical |  |  | Proposed Original |  |  | EVALUATED |  |  | Historical |  |  | Proposed Original |  |  | EVALUATED |  |  | Variance (Aw vs Ak) |  | Justifikasi Teknis | Data Pendukung
[22 empty] | 0 | 0 | 0 | [72 empty] | Quantity | Unit price
| 44 | GENERAL |  |  | 0 |  |  |  | 415165.8232 |  |  | 379605.6768 |  |  | 0 |  |  | 68275.4001 |  |  | 62361.564 | 0 | 0 | -5913.8361 |  |  | 0 |  |  | 68275.4001 |  |  | 62361.564 |  |  | 0 |  |  | 68275.4001 |  |  | 62361.564 |  |  | 0 |  |  | 68275.4001 |  |  | 62361.564 |  |  | 0 |  |  | 71032.1114 |  |  | 65079.7104 |  |  | 0 |  |  | 71032.1114 |  |  | 65079.7104 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0
| 45 | Project Management Team | Qty | Unit Price | 0 | Unit | Qty | Unit Price | 122476.929 | Qty | Unit Price | 120408.0619 | Qty | Unit Price | 0 | Qty | Unit Price | 19699.692 | Qty | Unit Price | 19366.927 | 0 | 0 | -332.7651 | Qty | Unit Price | 0 | Qty | Unit Price | 19699.692 | Qty | Unit Price | 19366.927 | Qty | Unit Price | 0 | Qty | Unit Price | 19699.692 | Qty | Unit Price | 19366.927 | Qty | Unit Price | 0 | Qty | Unit Price | 19699.692 | Qty | Unit Price | 19366.927 | Qty | Unit Price | 0 | Qty | Unit Price | 21839.0804 | Qty | Unit Price | 21470.1771 | Qty | Unit Price | 0 | Qty | Unit Price | 21839.0804 | Qty | Unit Price | 21470.1771 | Qty | Unit Price | 0 | Qty | Unit Price | 0 | Qty | Unit Price | 0 | Qty | Unit Price | 0 | Qty | Unit Price | 0 | Qty | Unit Price | 0 | Qty | Unit Price | 0 | Qty | Unit Price | 0 | Qty | Unit Price | 0
|  | Dry Hole Based | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | DAY COMPANY MAN | 0 | 0 | 0 |  | 153.3333 | 266.435 | 40853.3696 | 153.3333 | 261.9344 | 40163.2789 |  |  | 0 | 24.7083 | 266.435 | 6583.1653 | 24.7083 | 261.9344 | 6471.9631 | 0 | -4.5006 | -111.2021 | 0 | 0 | 0 | 24.7083 | 266.435 | 6583.1653 | 24.7083 | 261.9344 | 6471.9631 | 0 | 0 | 0 | 24.7083 | 266.435 | 6583.1653 | 24.7083 | 261.9344 | 6471.9631 | 0 | 0 | 0 | 24.7083 | 266.435 | 6583.1653 | 24.7083 | 261.9344 | 6471.9631 | 0 | 0 | 0 | 27.25 | 266.435 | 7260.3543 | 27.25 | 261.9344 | 7137.7131 | 0 | 0 | 0 | 27.25 | 266.435 | 7260.3543 | 27.25 | 261.9344 | 7137.7131 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -4.5006
|  | NIGHT COMPANY MAN | 0 | 0 | 0 |  | 153.3333 | 266.435 | 40853.3696 | 153.3333 | 261.9344 | 40163.2789 |  |  | 0 | 24.7083 | 266.435 | 6583.1653 | 24.7083 | 261.9344 | 6471.9631 | 0 | -4.5006 | -111.2021 | 0 | 0 | 0 | 24.7083 | 266.435 | 6583.1653 | 24.7083 | 261.9344 | 6471.9631 | 0 | 0 | 0 | 24.7083 | 266.435 | 6583.1653 | 24.7083 | 261.9344 | 6471.9631 | 0 | 0 | 0 | 24.7083 | 266.435 | 6583.1653 | 24.7083 | 261.9344 | 6471.9631 | 0 | 0 | 0 | 27.25 | 266.435 | 7260.3543 | 27.25 | 261.9344 | 7137.7131 | 0 | 0 | 0 | 27.25 | 266.435 | 7260.3543 | 27.25 | 261.9344 | 7137.7131 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -4.5006
|  | WELLSITE GEOLOGIST | 0 | 0 | 0 |  | 129.3333 | 58.4192 | 7555.5556 | 129.3333 | 57.4324 | 7427.9279 |  |  | 0 | 20.7083 | 58.4192 | 1209.7652 | 20.7083 | 57.4324 | 1189.33 | 0 | -0.98681 | -20.4352 | 0 | 0 | 0 | 20.7083 | 58.4192 | 1209.7652 | 20.7083 | 57.4324 | 1189.33 | 0 | 0 | 0 | 20.7083 | 58.4192 | 1209.7652 | 20.7083 | 57.4324 | 1189.33 | 0 | 0 | 0 | 20.7083 | 58.4192 | 1209.7652 | 20.7083 | 57.4324 | 1189.33 | 0 | 0 | 0 | 23.25 | 58.4192 | 1358.2474 | 23.25 | 57.4324 | 1335.3041 | 0 | 0 | 0 | 23.25 | 58.4192 | 1358.2474 | 23.25 | 57.4324 | 1335.3041 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -0.98681
|  | HSE SUPERVISOR | 0 | 0 | 0 |  | 129.3333 | 111.4127 | 14409.3714 | 129.3333 | 109.5307 | 14165.9699 |  |  | 0 | 20.7083 | 111.4127 | 2307.1706 | 20.7083 | 109.5307 | 2268.1981 | 0 | -1.882 | -38.9725 | 0 | 0 | 0 | 20.7083 | 111.4127 | 2307.1706 | 20.7083 | 109.5307 | 2268.1981 | 0 | 0 | 0 | 20.7083 | 111.4127 | 2307.1706 | 20.7083 | 109.5307 | 2268.1981 | 0 | 0 | 0 | 20.7083 | 111.4127 | 2307.1706 | 20.7083 | 109.5307 | 2268.1981 | 0 | 0 | 0 | 23.25 | 111.4127 | 2590.3445 | 23.25 | 109.5307 | 2546.5887 | 0 | 0 | 0 | 23.25 | 111.4127 | 2590.3445 | 23.25 | 109.5307 | 2546.5887 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -1.882
|  | MATERIAL MAN | 0 | 0 | 0 |  | 129.3333 | 104.6604 | 13536.0762 | 129.3333 | 102.8925 | 13307.4263 |  |  | 0 | 20.7083 | 104.6604 | 2167.3421 | 20.7083 | 102.8925 | 2130.7316 | 0 | -1.7679 | -36.6105 | 0 | 0 | 0 | 20.7083 | 104.6604 | 2167.3421 | 20.7083 | 102.8925 | 2130.7316 | 0 | 0 | 0 | 20.7083 | 104.6604 | 2167.3421 | 20.7083 | 102.8925 | 2130.7316 | 0 | 0 | 0 | 20.7083 | 104.6604 | 2167.3421 | 20.7083 | 102.8925 | 2130.7316 | 0 | 0 | 0 | 23.25 | 104.6604 | 2433.3539 | 23.25 | 102.8925 | 2392.25 | 0 | 0 | 0 | 23.25 | 104.6604 | 2433.3539 | 23.25 | 102.8925 | 2392.25 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -1.7679
|  | Bantuan Security Lokal | 0 | 0 | 0 |  | 153.3333 | 34.3643 | 5269.1867 | 153.3333 | 33.7838 | 5180.1802 |  |  | 0 | 24.7083 | 34.3643 | 849.0836 | 24.7083 | 33.7838 | 834.741 | 0 | -0.58048 | -14.3426 | 0 | 0 | 0 | 24.7083 | 34.3643 | 849.0836 | 24.7083 | 33.7838 | 834.741 | 0 | 0 | 0 | 24.7083 | 34.3643 | 849.0836 | 24.7083 | 33.7838 | 834.741 | 0 | 0 | 0 | 24.7083 | 34.3643 | 849.0836 | 24.7083 | 33.7838 | 834.741 | 0 | 0 | 0 | 27.25 | 34.3643 | 936.4261 | 27.25 | 33.7838 | 920.6081 | 0 | 0 | 0 | 27.25 | 34.3643 | 936.4261 | 27.25 | 33.7838 | 920.6081 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -0.58048
|  |  | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[22 empty] | 0 | 0 | 0
| Line | DESCRIPTION | Historical |  |  | Proposed Original |  |  |  | EVALUATED |  |  | Historical |  |  | Proposed Original |  |  | EVALUATED |  |  | 0 | 0 | 0 | Historical |  |  | Proposed Original |  |  | EVALUATED |  |  | Historical |  |  | Proposed Original |  |  | EVALUATED |  |  | Historical |  |  | Proposed Original |  |  | EVALUATED |  |  | Historical |  |  | Proposed Original |  |  | EVALUATED |  |  | Historical |  |  | Proposed Original |  |  | EVALUATED |  |  | Historical |  |  | Proposed Original |  |  | EVALUATED |  |  | Historical |  |  | Proposed Original |  |  | EVALUATED |  |  | Historical |  |  | Proposed Original |  |  | EVALUATED |  |  | Variance (Aw vs Ak) |  | Justifikasi Teknis | Data Pendukung
[22 empty] | 0 | 0 | 0 | [72 empty] | Quantity | Unit price
| 46 | Insurance | Qty | Unit Price | 0 | Unit | Qty | Unit Price | 24415.6009 | Qty | Unit Price | 24003.1752 | Qty | Unit Price | 0 | Qty | Unit Price | 4069.2668 | Qty | Unit Price | 4000.5292 | 0 | 0 | -68.7376 | Qty | Unit Price | 0 | Qty | Unit Price | 4069.2668 | Qty | Unit Price | 4000.5292 | Qty | Unit Price | 0 | Qty | Unit Price | 4069.2668 | Qty | Unit Price | 4000.5292 | Qty | Unit Price | 0 | Qty | Unit Price | 4069.2668 | Qty | Unit Price | 4000.5292 | Qty | Unit Price | 0 | Qty | Unit Price | 4069.2668 | Qty | Unit Price | 4000.5292 | Qty | Unit Price | 0 | Qty | Unit Price | 4069.2668 | Qty | Unit Price | 4000.5292 | Qty | Unit Price | 0 | Qty | Unit Price | 0 | Qty | Unit Price | 0 | Qty | Unit Price | 0 | Qty | Unit Price | 0 | Qty | Unit Price | 0 | Qty | Unit Price | 0 | Qty | Unit Price | 0 | Qty | Unit Price | 0
|  |  | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | INSURANCES | 0 | 0 | 0 |  | 55238.916 | 0.442 | 24415.6009 | 55238.916 | 0.43453 | 24003.1752 |  |  | 0 | 9206.486 | 0.442 | 4069.2668 | 9206.486 | 0.43453 | 4000.5292 | 0 | -0.0074662 | -68.7376 | 0 | 0 | 0 | 9206.486 | 0.442 | 4069.2668 | 9206.486 | 0.43453 | 4000.5292 | 0 | 0 | 0 | 9206.486 | 0.442 | 4069.2668 | 9206.486 | 0.43453 | 4000.5292 | 0 | 0 | 0 | 9206.486 | 0.442 | 4069.2668 | 9206.486 | 0.43453 | 4000.5292 | 0 | 0 | 0 | 9206.486 | 0.442 | 4069.2668 | 9206.486 | 0.43453 | 4000.5292 | 0 | 0 | 0 | 9206.486 | 0.442 | 4069.2668 | 9206.486 | 0.43453 | 4000.5292 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -0.0074662
|  |  | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[22 empty] | 0 | 0 | 0
| Line | DESCRIPTION | Historical |  |  | Proposed Original |  |  |  | EVALUATED |  |  | Historical |  |  | Proposed Original |  |  | EVALUATED |  |  | 0 | 0 | 0 | Historical |  |  | Proposed Original |  |  | EVALUATED |  |  | Historical |  |  | Proposed Original |  |  | EVALUATED |  |  | Historical |  |  | Proposed Original |  |  | EVALUATED |  |  | Historical |  |  | Proposed Original |  |  | EVALUATED |  |  | Historical |  |  | Proposed Original |  |  | EVALUATED |  |  | Historical |  |  | Proposed Original |  |  | EVALUATED |  |  | Historical |  |  | Proposed Original |  |  | EVALUATED |  |  | Historical |  |  | Proposed Original |  |  | EVALUATED |  |  | Variance (Aw vs Ak) |  | Justifikasi Teknis | Data Pendukung
[22 empty] | 0 | 0 | 0 | [72 empty] | Quantity | Unit price
| 47 | Permit and Fees | Qty | Unit Price | 0 | Unit | Qty | Unit Price | 53731.3433 | Qty | Unit Price | 29493.2432 | Qty | Unit Price | 0 | Qty | Unit Price | 8955.2239 | Qty | Unit Price | 4915.5405 | 0 | 0 | -4039.6833 | Qty | Unit Price | 0 | Qty | Unit Price | 8955.2239 | Qty | Unit Price | 4915.5405 | Qty | Unit Price | 0 | Qty | Unit Price | 8955.2239 | Qty | Unit Price | 4915.5405 | Qty | Unit Price | 0 | Qty | Unit Price | 8955.2239 | Qty | Unit Price | 4915.5405 | Qty | Unit Price | 0 | Qty | Unit Price | 8955.2239 | Qty | Unit Price | 4915.5405 | Qty | Unit Price | 0 | Qty | Unit Price | 8955.2239 | Qty | Unit Price | 4915.5405 | Qty | Unit Price | 0 | Qty | Unit Price | 0 | Qty | Unit Price | 0 | Qty | Unit Price | 0 | Qty | Unit Price | 0 | Qty | Unit Price | 0 | Qty | Unit Price | 0 | Qty | Unit Price | 0 | Qty | Unit Price | 0
|  | Permit and Fees | 0 | 0 | 0 |  | 6 | 8955.2239 | 53731.3433 | 6 | 4915.5405 | 29493.2432 |  |  | 0 | 1 | 8955.2239 | 8955.2239 | 1 | 4915.5405 | 4915.5405 | 0 | -4039.6833 | -4039.6833 | 0 | 0 | 0 | 1 | 8955.2239 | 8955.2239 | 1 | 4915.5405 | 4915.5405 | 0 | 0 | 0 | 1 | 8955.2239 | 8955.2239 | 1 | 4915.5405 | 4915.5405 | 0 | 0 | 0 | 1 | 8955.2239 | 8955.2239 | 1 | 4915.5405 | 4915.5405 | 0 | 0 | 0 | 1 | 8955.2239 | 8955.2239 | 1 | 4915.5405 | 4915.5405 | 0 | 0 | 0 | 1 | 8955.2239 | 8955.2239 | 1 | 4915.5405 | 4915.5405 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -4039.6833
|  |  | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | SAFETY CHECK LIST | 1 | 0 | 0 |  | 0 | 0 | 0 | 1 | 0 | 0 | 1 |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0
|  |  | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[22 empty] | 0 | 0 | 0
| Line | DESCRIPTION | Historical |  |  | Proposed Original |  |  |  | EVALUATED |  |  | Historical |  |  | Proposed Original |  |  | EVALUATED |  |  | 0 | 0 | 0 | Historical |  |  | Proposed Original |  |  | EVALUATED |  |  | Historical |  |  | Proposed Original |  |  | EVALUATED |  |  | Historical |  |  | Proposed Original |  |  | EVALUATED |  |  | Historical |  |  | Proposed Original |  |  | EVALUATED |  |  | Historical |  |  | Proposed Original |  |  | EVALUATED |  |  | Historical |  |  | Proposed Original |  |  | EVALUATED |  |  | Historical |  |  | Proposed Original |  |  | EVALUATED |  |  | Historical |  |  | Proposed Original |  |  | EVALUATED |  |  | Variance (Aw vsAk) |  | Justifikasi Teknis | Data Pendukung
[22 empty] | 0 | 0 | 0 | [72 empty] | Quantity | Unit price
| 48 | Marine Rental & charter | Qty | Unit Price | 0 | Unit | Qty | Unit Price | 0 | Qty | Unit Price | 0 | Qty | Unit Price | 0 | Qty | Unit Price | 0 | Qty | Unit Price | 0 | 0 | 0 | 0 | Qty | Unit Price | 0 | Qty | Unit Price | 0 | Qty | Unit Price | 0 | Qty | Unit Price | 0 | Qty | Unit Price | 0 | Qty | Unit Price | 0 | Qty | Unit Price | 0 | Qty | Unit Price | 0 | Qty | Unit Price | 0 | Qty | Unit Price | 0 | Qty | Unit Price | 0 | Qty | Unit Price | 0 | Qty | Unit Price | 0 | Qty | Unit Price | 0 | Qty | Unit Price | 0 | Qty | Unit Price | 0 | Qty | Unit Price | 0 | Qty | Unit Price | 0 | Qty | Unit Price | 0 | Qty | Unit Price | 0 | Qty | Unit Price | 0 | Qty | Unit Price | 0 | Qty | Unit Price | 0 | Qty | Unit Price | 0
|  |  | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[22 empty] | 0 | 0 | 0
| Line | DESCRIPTION | Historical |  |  | Proposed Original |  |  |  | EVALUATED |  |  | Historical |  |  | Proposed Original |  |  | EVALUATED |  |  | 0 | 0 | 0 | Historical |  |  | Proposed Original |  |  | EVALUATED |  |  | Historical |  |  | Proposed Original |  |  | EVALUATED |  |  | Historical |  |  | Proposed Original |  |  | EVALUATED |  |  | Historical |  |  | Proposed Original |  |  | EVALUATED |  |  | Historical |  |  | Proposed Original |  |  | EVALUATED |  |  | Historical |  |  | Proposed Original |  |  | EVALUATED |  |  | Historical |  |  | Proposed Original |  |  | EVALUATED |  |  | Historical |  |  | Proposed Original |  |  | EVALUATED |  |  | Variance (Aw vs Ak) |  | Justifikasi Teknis | Data Pendukung
[22 empty] | 0 | 0 | 0 | [72 empty] | Quantity | Unit price
| 49 | Helicopter / charter flight | Qty | Unit Price | 0 | Unit | Qty | Unit Price | 0 | Qty | Unit Price | 0 | Qty | Unit Price | 0 | Qty | Unit Price | 0 | Qty | Unit Price | 0 | 0 | 0 | 0 | Qty | Unit Price | 0 | Qty | Unit Price | 0 | Qty | Unit Price | 0 | Qty | Unit Price | 0 | Qty | Unit Price | 0 | Qty | Unit Price | 0 | Qty | Unit Price | 0 | Qty | Unit Price | 0 | Qty | Unit Price | 0 | Qty | Unit Price | 0 | Qty | Unit Price | 0 | Qty | Unit Price | 0 | Qty | Unit Price | 0 | Qty | Unit Price | 0 | Qty | Unit Price | 0 | Qty | Unit Price | 0 | Qty | Unit Price | 0 | Qty | Unit Price | 0 | Qty | Unit Price | 0 | Qty | Unit Price | 0 | Qty | Unit Price | 0 | Qty | Unit Price | 0 | Qty | Unit Price | 0 | Qty | Unit Price | 0
|  |  | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[22 empty] | 0 | 0 | 0
| Line | DESCRIPTION | Historical |  |  | Proposed Original |  |  |  | EVALUATED |  |  | Historical |  |  | Proposed Original |  |  | EVALUATED |  |  | 0 | 0 | 0 | Historical |  |  | Proposed Original |  |  | EVALUATED |  |  | Historical |  |  | Proposed Original |  |  | EVALUATED |  |  | Historical |  |  | Proposed Original |  |  | EVALUATED |  |  | Historical |  |  | Proposed Original |  |  | EVALUATED |  |  | Historical |  |  | Proposed Original |  |  | EVALUATED |  |  | Historical |  |  | Proposed Original |  |  | EVALUATED |  |  | Historical |  |  | Proposed Original |  |  | EVALUATED |  |  | Historical |  |  | Proposed Original |  |  | EVALUATED |  |  | Variance (Aw vs Ak) |  | Justifikasi Teknis | Data Pendukung
[22 empty] | 0 | 0 | 0 | [72 empty] | Quantity | Unit price
| 50 | Land Transportation | Qty | Unit Price | 0 | Unit | Qty | Unit Price | 32204 | Qty | Unit Price | 31660.0135 | Qty | Unit Price | 0 | Qty | Unit Price | 5156.375 | Qty | Unit Price | 5069.2741 | 0 | 0 | -87.1009 | Qty | Unit Price | 0 | Qty | Unit Price | 5156.375 | Qty | Unit Price | 5069.2741 | Qty | Unit Price | 0 | Qty | Unit Price | 5156.375 | Qty | Unit Price | 5069.2741 | Qty | Unit Price | 0 | Qty | Unit Price | 5156.375 | Qty | Unit Price | 5069.2741 | Qty | Unit Price | 0 | Qty | Unit Price | 5789.25 | Qty | Unit Price | 5691.4586 | Qty | Unit Price | 0 | Qty | Unit Price | 5789.25 | Qty | Unit Price | 5691.4586 | Qty | Unit Price | 0 | Qty | Unit Price | 0 | Qty | Unit Price | 0 | Qty | Unit Price | 0 | Qty | Unit Price | 0 | Qty | Unit Price | 0 | Qty | Unit Price | 0 | Qty | Unit Price | 0 | Qty | Unit Price | 0
|  | Vacuum Truck 6M3 | 0 | 0 | 0 |  | 129.3333 | 249 | 32204 | 129.3333 | 244.7939 | 31660.0135 | 0 | 0 | 0 | 20.7083 | 249 | 5156.375 | 20.7083 | 244.7939 | 5069.2741 | 0 | -4.2061 | -87.1009 | 0 | 0 | 0 | 20.7083 | 249 | 5156.375 | 20.7083 | 244.7939 | 5069.2741 | 0 | 0 | 0 | 20.7083 | 249 | 5156.375 | 20.7083 | 244.7939 | 5069.2741 | 0 | 0 | 0 | 20.7083 | 249 | 5156.375 | 20.7083 | 244.7939 | 5069.2741 | 0 | 0 | 0 | 23.25 | 249 | 5789.25 | 23.25 | 244.7939 | 5691.4586 | 0 | 0 | 0 | 23.25 | 249 | 5789.25 | 23.25 | 244.7939 | 5691.4586 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 244.7939 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 244.7939 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 244.7939 | 0 | 0 | -4.2061
|  |  | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
` |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[22 empty] | 0 | 0 | 0
| Line | DESCRIPTION | Historical |  |  | Proposed Original |  |  |  | EVALUATED |  |  | Historical |  |  | Proposed Original |  |  | EVALUATED |  |  | 0 | 0 | 0 | Historical |  |  | Proposed Original |  |  | EVALUATED |  |  | Historical |  |  | Proposed Original |  |  | EVALUATED |  |  | Historical |  |  | Proposed Original |  |  | EVALUATED |  |  | Historical |  |  | Proposed Original |  |  | EVALUATED |  |  | Historical |  |  | Proposed Original |  |  | EVALUATED |  |  | Historical |  |  | Proposed Original |  |  | EVALUATED |  |  | Historical |  |  | Proposed Original |  |  | EVALUATED |  |  | Historical |  |  | Proposed Original |  |  | EVALUATED |  |  | Variance (Aw vsAk) |  | Justifikasi Teknis | Data Pendukung
[22 empty] | 0 | 0 | 0 | [72 empty] | Quantity | Unit price
| 51 | Other Transportation | Qty | Unit Price | 0 | Unit | Qty | Unit Price | 0 | Qty | Unit Price | 0 | Qty | Unit Price | 0 | Qty | Unit Price | 0 | Qty | Unit Price | 0 | 0 | 0 | 0 | Qty | Unit Price | 0 | Qty | Unit Price | 0 | Qty | Unit Price | 0 | Qty | Unit Price | 0 | Qty | Unit Price | 0 | Qty | Unit Price | 0 | Qty | Unit Price | 0 | Qty | Unit Price | 0 | Qty | Unit Price | 0 | Qty | Unit Price | 0 | Qty | Unit Price | 0 | Qty | Unit Price | 0 | Qty | Unit Price | 0 | Qty | Unit Price | 0 | Qty | Unit Price | 0 | Qty | Unit Price | 0 | Qty | Unit Price | 0 | Qty | Unit Price | 0 | Qty | Unit Price | 0 | Qty | Unit Price | 0 | Qty | Unit Price | 0 | Qty | Unit Price | 0 | Qty | Unit Price | 0 | Qty | Unit Price | 0
|  | Dry Hole Based | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[22 empty] | 0 | 0 | 0
| Line | DESCRIPTION | Historical |  |  | Proposed Original |  |  |  | EVALUATED |  |  | Historical |  |  | Proposed Original |  |  | EVALUATED |  |  | 0 | 0 | 0 | Historical |  |  | Proposed Original |  |  | EVALUATED |  |  | Historical |  |  | Proposed Original |  |  | EVALUATED |  |  | Historical |  |  | Proposed Original |  |  | EVALUATED |  |  | Historical |  |  | Proposed Original |  |  | EVALUATED |  |  | Historical |  |  | Proposed Original |  |  | EVALUATED |  |  | Historical |  |  | Proposed Original |  |  | EVALUATED |  |  | Historical |  |  | Proposed Original |  |  | EVALUATED |  |  | Historical |  |  | Proposed Original |  |  | EVALUATED |  |  | Variance (Aw vs Ak) |  | Justifikasi Teknis | Data Pendukung
[22 empty] | 0 | 0 | 0 | [72 empty] | Quantity | Unit price
| 52 | Fuel and Lubricant | Qty | Unit Price | 0 | Unit | Qty | Unit Price | 136841.5808 | Qty | Unit Price | 129313.3333 | Qty | Unit Price | 0 | Qty | Unit Price | 22876.89 | Qty | Unit Price | 21618.3333 | 0 | 0 | -1258.5567 | Qty | Unit Price | 0 | Qty | Unit Price | 22876.89 | Qty | Unit Price | 21618.3333 | Qty | Unit Price | 0 | Qty | Unit Price | 22876.89 | Qty | Unit Price | 21618.3333 | Qty | Unit Price | 0 | Qty | Unit Price | 22876.89 | Qty | Unit Price | 21618.3333 | Qty | Unit Price | 0 | Qty | Unit Price | 22667.0103 | Qty | Unit Price | 21420 | Qty | Unit Price | 0 | Qty | Unit Price | 22667.0103 | Qty | Unit Price | 21420 | Qty | Unit Price | 0 | Qty | Unit Price | 0 | Qty | Unit Price | 0 | Qty | Unit Price | 0 | Qty | Unit Price | 0 | Qty | Unit Price | 0 | Qty | Unit Price | 0 | Qty | Unit Price | 0 | Qty | Unit Price | 0
|  | Dry Hole Based | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Solar Operasi Rig 350 HP | 530296.8245 | 0 | 0 |  | 95083.3333 | 1.4392 | 136841.5808 | 95083.3333 | 1.36 | 129313.3333 | 530296.8245 |  | 0 | 15895.8333 | 1.4392 | 22876.89 | 15895.8333 | 1.36 | 21618.3333 | 0 | -0.079175 | -1258.5567 | 0 | 0 | 0 | 15895.8333 | 1.4392 | 22876.89 | 15895.8333 | 1.36 | 21618.3333 | 0 | 0 | 0 | 15895.8333 | 1.4392 | 22876.89 | 15895.8333 | 1.36 | 21618.3333 | 0 | 0 | 0 | 15895.8333 | 1.4392 | 22876.89 | 15895.8333 | 1.36 | 21618.3333 | 0 | 0 | 0 | 15750 | 1.4392 | 22667.0103 | 15750 | 1.36 | 21420 | 0 | 0 | 0 | 15750 | 1.4392 | 22667.0103 | 15750 | 1.36 | 21420 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.36 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -0.079175 | Update Harga Solar
|  |  | 13833.8302 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 13833.8302 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  | 232300 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 232300 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
` |  |  | 6970.2655 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 6970.2655 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[22 empty] | 0 | 0 | 0
| Line | DESCRIPTION | Historical |  |  | Proposed Original |  |  |  | EVALUATED |  |  | Historical |  |  | Proposed Original |  |  | EVALUATED |  |  | 0 | 0 | 0 | Historical |  |  | Proposed Original |  |  | EVALUATED |  |  | Historical |  |  | Proposed Original |  |  | EVALUATED |  |  | Historical |  |  | Proposed Original |  |  | EVALUATED |  |  | Historical |  |  | Proposed Original |  |  | EVALUATED |  |  | Historical |  |  | Proposed Original |  |  | EVALUATED |  |  | Historical |  |  | Proposed Original |  |  | EVALUATED |  |  | Historical |  |  | Proposed Original |  |  | EVALUATED |  |  | Historical |  |  | Proposed Original |  |  | EVALUATED |  |  | Variance (Aw vs Ak) |  | Justifikasi Teknis | Data Pendukung
[22 empty] | 0 | 0 | 0 | [72 empty] | Quantity | Unit price
| 53 | Camp Facilities | Qty | Unit Price | 0 | Unit | Qty | Unit Price | 34920 | Qty | Unit Price | 34330.1351 | Qty | Unit Price | 0 | Qty | Unit Price | 5591.25 | Qty | Unit Price | 5496.8032 | 0 | 0 | -94.4468 | Qty | Unit Price | 0 | Qty | Unit Price | 5591.25 | Qty | Unit Price | 5496.8032 | Qty | Unit Price | 0 | Qty | Unit Price | 5591.25 | Qty | Unit Price | 5496.8032 | Qty | Unit Price | 0 | Qty | Unit Price | 5591.25 | Qty | Unit Price | 5496.8032 | Qty | Unit Price | 0 | Qty | Unit Price | 6277.5 | Qty | Unit Price | 6171.4611 | Qty | Unit Price | 0 | Qty | Unit Price | 6277.5 | Qty | Unit Price | 6171.4611 | Qty | Unit Price | 0 | Qty | Unit Price | 0 | Qty | Unit Price | 0 | Qty | Unit Price | 0 | Qty | Unit Price | 0 | Qty | Unit Price | 0 | Qty | Unit Price | 0 | Qty | Unit Price | 0 | Qty | Unit Price | 0
|  | Dry Hole Based | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | FASILITAS KESEHATAN RIG SITE | 0 | 0 | 0 |  | 129.3333 | 270 | 34920 | 129.3333 | 265.4392 | 34330.1351 | 0 |  | 0 | 20.7083 | 270 | 5591.25 | 20.7083 | 265.4392 | 5496.8032 | 0 | -4.5608 | -94.4468 | 0 | 0 | 0 | 20.7083 | 270 | 5591.25 | 20.7083 | 265.4392 | 5496.8032 | 0 | 0 | 0 | 20.7083 | 270 | 5591.25 | 20.7083 | 265.4392 | 5496.8032 | 0 | 0 | 0 | 20.7083 | 270 | 5591.25 | 20.7083 | 265.4392 | 5496.8032 | 0 | 0 | 0 | 23.25 | 270 | 6277.5 | 23.25 | 265.4392 | 6171.4611 | 0 | 0 | 0 | 23.25 | 270 | 6277.5 | 23.25 | 265.4392 | 6171.4611 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -4.5608
|  |  | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[22 empty] | 0 | 0 | 0
| Line | DESCRIPTION | Historical |  |  | Proposed Original |  |  |  | EVALUATED |  |  | Historical |  |  | Proposed Original |  |  | EVALUATED |  |  | 0 | 0 | 0 | Historical |  |  | Proposed Original |  |  | EVALUATED |  |  | Historical |  |  | Proposed Original |  |  | EVALUATED |  |  | Historical |  |  | Proposed Original |  |  | EVALUATED |  |  | Historical |  |  | Proposed Original |  |  | EVALUATED |  |  | Historical |  |  | Proposed Original |  |  | EVALUATED |  |  | Historical |  |  | Proposed Original |  |  | EVALUATED |  |  | Historical |  |  | Proposed Original |  |  | EVALUATED |  |  | Historical |  |  | Proposed Original |  |  | EVALUATED |  |  | Variance (Aw vs Ak) |  | Justifikasi Teknis | Data Pendukung
[22 empty] | 0 | 0 | 0 | [72 empty] | Quantity | Unit price
| 54 | ALLOCATED OVERHEADS - FIELD OFFICE | Qty | Unit Price | 0 | Unit | Qty | Unit Price | 10576.3693 | Qty | Unit Price | 10397.7144 | Qty | Unit Price | 0 | Qty | Unit Price | 1926.7023 | Qty | Unit Price | 1894.1567 | 0 | 0 | -32.5456 | Qty | Unit Price | 0 | Qty | Unit Price | 1926.7023 | Qty | Unit Price | 1894.1567 | Qty | Unit Price | 0 | Qty | Unit Price | 1926.7023 | Qty | Unit Price | 1894.1567 | Qty | Unit Price | 0 | Qty | Unit Price | 1926.7023 | Qty | Unit Price | 1894.1567 | Qty | Unit Price | 0 | Qty | Unit Price | 1434.78 | Qty | Unit Price | 1410.5439 | Qty | Unit Price | 0 | Qty | Unit Price | 1434.78 | Qty | Unit Price | 1410.5439 | Qty | Unit Price | 0 | Qty | Unit Price | 0 | Qty | Unit Price | 0 | Qty | Unit Price | 0 | Qty | Unit Price | 0 | Qty | Unit Price | 0 | Qty | Unit Price | 0 | Qty | Unit Price | 0 | Qty | Unit Price | 0
|  |  | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | FIELD OFFICE | 0 | 0 | 0 |  | 6 | 881.3641 | 5288.1847 | 6 | 866.4762 | 5198.8572 | 0 |  | 0 | 1 | 963.3512 | 963.3512 | 1 | 947.0783 | 947.0783 | 0 | -16.2728 | -16.2728 | 0 | 0 | 0 | 1 | 963.3512 | 963.3512 | 1 | 947.0783 | 947.0783 | 0 | 0 | 0 | 1 | 963.3512 | 963.3512 | 1 | 947.0783 | 947.0783 | 0 | 0 | 0 | 1 | 963.3512 | 963.3512 | 1 | 947.0783 | 947.0783 | 0 | 0 | 0 | 1 | 717.39 | 717.39 | 1 | 705.2719 | 705.2719 | 0 | 0 | 0 | 1 | 717.39 | 717.39 | 1 | 705.2719 | 705.2719 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -14.8879
|  | JAKARTA OFFICE | 0 | 0 | 0 |  | 6 | 881.3641 | 5288.1847 | 6 | 866.4762 | 5198.8572 | 0 | 0 | 0 | 1 | 963.3512 | 963.3512 | 1 | 947.0783 | 947.0783 | 0 | -16.2728 | -16.2728 | 0 | 0 | 0 | 1 | 963.3512 | 963.3512 | 1 | 947.0783 | 947.0783 | 0 | 0 | 0 | 1 | 963.3512 | 963.3512 | 1 | 947.0783 | 947.0783 | 0 | 0 | 0 | 1 | 963.3512 | 963.3512 | 1 | 947.0783 | 947.0783 | 0 | 0 | 0 | 1 | 717.39 | 717.39 | 1 | 705.2719 | 705.2719 | 0 | 0 | 0 | 1 | 717.39 | 717.39 | 1 | 705.2719 | 705.2719 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -14.8879
|  |  | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | TOTAL | 0 | [5 empty] | 3573640.8148 | 3419773.0047 |  |  | 0 |  |  | 497796.2417 |  |  | 470258.4928 | [5 empty] | 0 |  |  | 497796.2417 |  |  | 470258.4928 |  |  | 0 |  |  | 497796.2417 |  |  | 470258.4928 |  |  | 0 |  |  | 497796.2417 |  |  | 470258.4928 |  |  | 0 |  |  | 791227.9241 |  |  | 769369.5168 |  |  | 0 |  |  | 791227.9241 |  |  | 769369.5168 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0
94.47%
Note on U55: Windows User: spec mengacu persetujuan teknis

## BS19 Detail 2 (hidden)
[6 empty] | SUM of Wells | [6 empty] | 6. Sumur Pendopo Tipe 4 | [8 empty] | 0 | [8 empty] | 0 | [8 empty] | 0 | [8 empty] | 0
DEPARTEMEN AFE
DIVISI RENCANA ANGGARAN
BUDGET SCHEDULE 19_ DETAIL
| Line | DESCRIPTION | Historical |  |  | Proposed Original |  |  |  | EVALUATED |  |  | Historical |  |  | Proposed Original |  |  | EVALUATED |  |  | Historical |  |  | Proposed Original |  |  | EVALUATED |  |  | Historical |  |  | Proposed Original |  |  | EVALUATED |  |  | Historical |  |  | Proposed Original |  |  | EVALUATED |  |  | Historical |  |  | Proposed Original |  |  | EVALUATED |  |  | Variance (Aw vs Ak) |  | Justifikasi Teknis | Data Pendukung
[58 empty] | Quantity | Unit price
| 1 | TANGIBLE COST |  |  | 0 |  |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0
| 2 | Casing | Qty | Unit Price | 0 | Unit | Qty | Unit Price | 0 | Qty | Unit Price | 0 | Qty | Unit Price | 0 | Qty | Unit Price | 0 | Qty | Unit Price | 0 | Qty | Unit Price | 0 | Qty | Unit Price | 0 | Qty | Unit Price | 0 | Qty | Unit Price | 0 | Qty | Unit Price | 0 | Qty | Unit Price | 0 | Qty | Unit Price | 0 | Qty | Unit Price | 0 | Qty | Unit Price | 0 | Qty | Unit Price | 0 | Qty | Unit Price | 0 | Qty | Unit Price | 0
|  |  | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| Line | DESCRIPTION | Historical |  |  | Proposed Original |  |  |  | EVALUATED |  |  | Historical |  |  | Proposed Original |  |  | EVALUATED |  |  | Historical |  |  | Proposed Original |  |  | EVALUATED |  |  | Historical |  |  | Proposed Original |  |  | EVALUATED |  |  | Historical |  |  | Proposed Original |  |  | EVALUATED |  |  | Historical |  |  | Proposed Original |  |  | EVALUATED |  |  | Variance (Aw vs Ak) |  | Justifikasi Teknis | Data Pendukung
[58 empty] | Quantity | Unit price
| 3 | Casing Accessories | Qty | Unit Price | 0 | Unit | Qty | Unit Price | 0 | Qty | Unit Price | 0 | Qty | Unit Price | 0 | Qty | Unit Price | 0 | Qty | Unit Price | 0 | Qty | Unit Price | 0 | Qty | Unit Price | 0 | Qty | Unit Price | 0 | Qty | Unit Price | 0 | Qty | Unit Price | 0 | Qty | Unit Price | 0 | Qty | Unit Price | 0 | Qty | Unit Price | 0 | Qty | Unit Price | 0 | Qty | Unit Price | 0 | Qty | Unit Price | 0 | Qty | Unit Price | 0
|  | Dry Hole Based | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  | 0 | 0 | 0 | PCS | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  | 0 | 0 | 0 | PCS | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  | 0 | 0 | 0 | PCS | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  | 0 | 0 | 0 | PCS | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  | 0 | 0 | 0 | PCS | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  | 0 | 0 | 0 | PCS | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  | 0 | 0 | 0 | PCS | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| Line | DESCRIPTION | Historical |  |  | Proposed Original |  |  |  | EVALUATED |  |  | Historical |  |  | Proposed Original |  |  | EVALUATED |  |  | Historical |  |  | Proposed Original |  |  | EVALUATED |  |  | Historical |  |  | Proposed Original |  |  | EVALUATED |  |  | Historical |  |  | Proposed Original |  |  | EVALUATED |  |  | Historical |  |  | Proposed Original |  |  | EVALUATED |  |  | Variance (Aw vs Ak) |  | Justifikasi Teknis | Data Pendukung
[58 empty] | Quantity | Unit price
| 4 | Tubing | Qty | Unit Price | 0 | Unit | Qty | Unit Price | 0 | Qty | Unit Price | 0 | Qty | Unit Price | 0 | Qty | Unit Price | 0 | Qty | Unit Price | 0 | Qty | Unit Price | 0 | Qty | Unit Price | 0 | Qty | Unit Price | 0 | Qty | Unit Price | 0 | Qty | Unit Price | 0 | Qty | Unit Price | 0 | Qty | Unit Price | 0 | Qty | Unit Price | 0 | Qty | Unit Price | 0 | Qty | Unit Price | 0 | Qty | Unit Price | 0 | Qty | Unit Price | 0
|  |  | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| Line | DESCRIPTION | Historical |  |  | Proposed Original |  |  |  | EVALUATED |  |  | Historical |  |  | Proposed Original |  |  | EVALUATED |  |  | Historical |  |  | Proposed Original |  |  | EVALUATED |  |  | Historical |  |  | Proposed Original |  |  | EVALUATED |  |  | Historical |  |  | Proposed Original |  |  | EVALUATED |  |  | Historical |  |  | Proposed Original |  |  | EVALUATED |  |  | Variance (Aw vs Ak) |  | Justifikasi Teknis | Data Pendukung
[58 empty] | Quantity | Unit price
| 5 | Well Equipment Surface | Qty | Unit Price | 0 | Unit | Qty | Unit Price | 0 | Qty | Unit Price | 0 | Qty | Unit Price | 0 | Qty | Unit Price | 0 | Qty | Unit Price | 0 | Qty | Unit Price | 0 | Qty | Unit Price | 0 | Qty | Unit Price | 0 | Qty | Unit Price | 0 | Qty | Unit Price | 0 | Qty | Unit Price | 0 | Qty | Unit Price | 0 | Qty | Unit Price | 0 | Qty | Unit Price | 0 | Qty | Unit Price | 0 | Qty | Unit Price | 0 | Qty | Unit Price | 0
|  | Dry Hole Based | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| Line | DESCRIPTION | Historical |  |  | Proposed Original |  |  |  | EVALUATED |  |  | Historical |  |  | Proposed Original |  |  | EVALUATED |  |  | Historical |  |  | Proposed Original |  |  | EVALUATED |  |  | Historical |  |  | Proposed Original |  |  | EVALUATED |  |  | Historical |  |  | Proposed Original |  |  | EVALUATED |  |  | Historical |  |  | Proposed Original |  |  | EVALUATED |  |  | Variance (Aw vs Ak) |  | Justifikasi Teknis | Data Pendukung
[58 empty] | Quantity | Unit price
| 6 | Well Equipment Sub-surface | Qty | Unit Price | 0 | Unit | Qty | Unit Price | 0 | Qty | Unit Price | 0 | Qty | Unit Price | 0 | Qty | Unit Price | 0 | Qty | Unit Price | 0 | Qty | Unit Price | 0 | Qty | Unit Price | 0 | Qty | Unit Price | 0 | Qty | Unit Price | 0 | Qty | Unit Price | 0 | Qty | Unit Price | 0 | Qty | Unit Price | 0 | Qty | Unit Price | 0 | Qty | Unit Price | 0 | Qty | Unit Price | 0 | Qty | Unit Price | 0 | Qty | Unit Price | 0
|  |  | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| Line | DESCRIPTION | Historical |  |  | Proposed Original |  |  |  | EVALUATED |  |  | Historical |  |  | Proposed Original |  |  | EVALUATED |  |  | Historical |  |  | Proposed Original |  |  | EVALUATED |  |  | Historical |  |  | Proposed Original |  |  | EVALUATED |  |  | Historical |  |  | Proposed Original |  |  | EVALUATED |  |  | Historical |  |  | Proposed Original |  |  | EVALUATED |  |  | Variance (Aw vs Ak) |  | Justifikasi Teknis | Data Pendukung
[58 empty] | Quantity | Unit price
| 7 | Other Tangible Cost | Qty | Unit Price | 0 | Unit | Qty | Unit Price | 0 | Qty | Unit Price | 0 | Qty | Unit Price | 0 | Qty | Unit Price | 0 | Qty | Unit Price | 0 | Qty | Unit Price | 0 | Qty | Unit Price | 0 | Qty | Unit Price | 0 | Qty | Unit Price | 0 | Qty | Unit Price | 0 | Qty | Unit Price | 0 | Qty | Unit Price | 0 | Qty | Unit Price | 0 | Qty | Unit Price | 0 | Qty | Unit Price | 0 | Qty | Unit Price | 0 | Qty | Unit Price | 0
|  | Dry Hole Based | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | INTANGIBLE COST |  |  | 0 |  |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0
| Line | DESCRIPTION | Historical |  |  | Proposed Original |  |  |  | EVALUATED |  |  | Historical |  |  | Proposed Original |  |  | EVALUATED |  |  | Historical |  |  | Proposed Original |  |  | EVALUATED |  |  | Historical |  |  | Proposed Original |  |  | EVALUATED |  |  | Historical |  |  | Proposed Original |  |  | EVALUATED |  |  | Historical |  |  | Proposed Original |  |  | EVALUATED |  |  | Variance (Aw vs Ak) |  | Justifikasi Teknis | Data Pendukung
[58 empty] | Quantity | Unit price
| 10 | PREPARATION AND TERMINATION |  |  | 0 |  |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0
| 11 | Survey | Qty | Unit Price | 0 | Unit | Qty | Unit Price | 0 | Qty | Unit Price | 0 | Qty | Unit Price | 0 | Qty | Unit Price | 0 | Qty | Unit Price | 0 | Qty | Unit Price | 0 | Qty | Unit Price | 0 | Qty | Unit Price | 0 | Qty | Unit Price | 0 | Qty | Unit Price | 0 | Qty | Unit Price | 0 | Qty | Unit Price | 0 | Qty | Unit Price | 0 | Qty | Unit Price | 0 | Qty | Unit Price | 0 | Qty | Unit Price | 0 | Qty | Unit Price | 0
|  |  | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| Line | DESCRIPTION | Historical |  |  | Proposed Original |  |  |  | EVALUATED |  |  | Historical |  |  | Proposed Original |  |  | EVALUATED |  |  | Historical |  |  | Proposed Original |  |  | EVALUATED |  |  | Historical |  |  | Proposed Original |  |  | EVALUATED |  |  | Historical |  |  | Proposed Original |  |  | EVALUATED |  |  | Historical |  |  | Proposed Original |  |  | EVALUATED |  |  | Variance (Aw vs Ak) |  | Justifikasi Teknis | Data Pendukung
[58 empty] | Quantity | Unit price
| 12 | LOCATION STACKING AND POSITIONING | Qty | Unit Price | 0 | Unit | Qty | Unit Price | 0 | Qty | Unit Price | 0 | Qty | Unit Price | 0 | Qty | Unit Price | 0 | Qty | Unit Price | 0 | Qty | Unit Price | 0 | Qty | Unit Price | 0 | Qty | Unit Price | 0 | Qty | Unit Price | 0 | Qty | Unit Price | 0 | Qty | Unit Price | 0 | Qty | Unit Price | 0 | Qty | Unit Price | 0 | Qty | Unit Price | 0 | Qty | Unit Price | 0 | Qty | Unit Price | 0 | Qty | Unit Price | 0
|  |  | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| Line | DESCRIPTION | Historical |  |  | Proposed Original |  |  |  | EVALUATED |  |  | Historical |  |  | Proposed Original |  |  | EVALUATED |  |  | Historical |  |  | Proposed Original |  |  | EVALUATED |  |  | Historical |  |  | Proposed Original |  |  | EVALUATED |  |  | Historical |  |  | Proposed Original |  |  | EVALUATED |  |  | Historical |  |  | Proposed Original |  |  | EVALUATED |  |  | Variance (Aw vs Ak) |  | Justifikasi Teknis | Data Pendukung
[58 empty] | Quantity | Unit price
| 13 | Wellsite and Access Road Preparation | Qty | Unit Price | 0 | Unit | Qty | Unit Price | 0 | Qty | Unit Price | 0 | Qty | Unit Price | 0 | Qty | Unit Price | 0 | Qty | Unit Price | 0 | Qty | Unit Price | 0 | Qty | Unit Price | 0 | Qty | Unit Price | 0 | Qty | Unit Price | 0 | Qty | Unit Price | 0 | Qty | Unit Price | 0 | Qty | Unit Price | 0 | Qty | Unit Price | 0 | Qty | Unit Price | 0 | Qty | Unit Price | 0 | Qty | Unit Price | 0 | Qty | Unit Price | 0
|  | Dry Hole Based | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| Line | DESCRIPTION | Historical |  |  | Proposed Original |  |  |  | EVALUATED |  |  | Historical |  |  | Proposed Original |  |  | EVALUATED |  |  | Historical |  |  | Proposed Original |  |  | EVALUATED |  |  | Historical |  |  | Proposed Original |  |  | EVALUATED |  |  | Historical |  |  | Proposed Original |  |  | EVALUATED |  |  | Historical |  |  | Proposed Original |  |  | EVALUATED |  |  | Variance (Aw vs Ak) |  | Justifikasi Teknis | Data Pendukung
[58 empty] | Quantity | Unit price
| 14 | Service Lines & Communications | Qty | Unit Price | 0 | Unit | Qty | Unit Price | 0 | Qty | Unit Price | 0 | Qty | Unit Price | 0 | Qty | Unit Price | 0 | Qty | Unit Price | 0 | Qty | Unit Price | 0 | Qty | Unit Price | 0 | Qty | Unit Price | 0 | Qty | Unit Price | 0 | Qty | Unit Price | 0 | Qty | Unit Price | 0 | Qty | Unit Price | 0 | Qty | Unit Price | 0 | Qty | Unit Price | 0 | Qty | Unit Price | 0 | Qty | Unit Price | 0 | Qty | Unit Price | 0
|  | Dry Hole Based | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| Line | DESCRIPTION | Historical |  |  | Proposed Original |  |  |  | EVALUATED |  |  | Historical |  |  | Proposed Original |  |  | EVALUATED |  |  | Historical |  |  | Proposed Original |  |  | EVALUATED |  |  | Historical |  |  | Proposed Original |  |  | EVALUATED |  |  | Historical |  |  | Proposed Original |  |  | EVALUATED |  |  | Historical |  |  | Proposed Original |  |  | EVALUATED |  |  | Variance (Aw vs Ak) |  | Justifikasi Teknis | Data Pendukung
[58 empty] | Quantity | Unit price
| 15 | Water System | Qty | Unit Price | 0 | Unit | Qty | Unit Price | 0 | Qty | Unit Price | 0 | Qty | Unit Price | 0 | Qty | Unit Price | 0 | Qty | Unit Price | 0 | Qty | Unit Price | 0 | Qty | Unit Price | 0 | Qty | Unit Price | 0 | Qty | Unit Price | 0 | Qty | Unit Price | 0 | Qty | Unit Price | 0 | Qty | Unit Price | 0 | Qty | Unit Price | 0 | Qty | Unit Price | 0 | Qty | Unit Price | 0 | Qty | Unit Price | 0 | Qty | Unit Price | 0
|  | Dry Hole Based | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| Line | DESCRIPTION | Historical |  |  | Proposed Original |  |  |  | EVALUATED |  |  | Historical |  |  | Proposed Original |  |  | EVALUATED |  |  | Historical |  |  | Proposed Original |  |  | EVALUATED |  |  | Historical |  |  | Proposed Original |  |  | EVALUATED |  |  | Historical |  |  | Proposed Original |  |  | EVALUATED |  |  | Historical |  |  | Proposed Original |  |  | EVALUATED |  |  | Variance (Aw vs Ak) |  | Justifikasi Teknis | Data Pendukung
[58 empty] | Quantity | Unit price
| 16 | Rigging Up / Rigging Down | Qty | Unit Price | 0 | Unit | Qty | Unit Price | 0 | Qty | Unit Price | 0 | Qty | Unit Price | 0 | Qty | Unit Price | 0 | Qty | Unit Price | 0 | Qty | Unit Price | 0 | Qty | Unit Price | 0 | Qty | Unit Price | 0 | Qty | Unit Price | 0 | Qty | Unit Price | 0 | Qty | Unit Price | 0 | Qty | Unit Price | 0 | Qty | Unit Price | 0 | Qty | Unit Price | 0 | Qty | Unit Price | 0 | Qty | Unit Price | 0 | Qty | Unit Price | 0
|  |  | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| Line | DESCRIPTION | Historical |  |  | Proposed Original |  |  |  | EVALUATED |  |  | Historical |  |  | Proposed Original |  |  | EVALUATED |  |  | Historical |  |  | Proposed Original |  |  | EVALUATED |  |  | Historical |  |  | Proposed Original |  |  | EVALUATED |  |  | Historical |  |  | Proposed Original |  |  | EVALUATED |  |  | Historical |  |  | Proposed Original |  |  | EVALUATED |  |  | Variance (Aw vs Ak) |  | Justifikasi Teknis | Data Pendukung
[58 empty] | Quantity | Unit price
| 18 | DRILLING/WORKOVER OPERATIONS |  |  | 0 |  |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0
| 19 | Contract Rig | Qty | Unit Price | 0 | Unit | Qty | Unit Price | 0 | Qty | Unit Price | 0 | Qty | Unit Price | 0 | Qty | Unit Price | 0 | Qty | Unit Price | 0 | Qty | Unit Price | 0 | Qty | Unit Price | 0 | Qty | Unit Price | 0 | Qty | Unit Price | 0 | Qty | Unit Price | 0 | Qty | Unit Price | 0 | Qty | Unit Price | 0 | Qty | Unit Price | 0 | Qty | Unit Price | 0 | Qty | Unit Price | 0 | Qty | Unit Price | 0 | Qty | Unit Price | 0
|  | Dry Hole Based | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| Line | DESCRIPTION | Historical |  |  | Proposed Original |  |  |  | EVALUATED |  |  | Historical |  |  | Proposed Original |  |  | EVALUATED |  |  | Historical |  |  | Proposed Original |  |  | EVALUATED |  |  | Historical |  |  | Proposed Original |  |  | EVALUATED |  |  | Historical |  |  | Proposed Original |  |  | EVALUATED |  |  | Historical |  |  | Proposed Original |  |  | EVALUATED |  |  | Variance (Aw vs Ak) |  | Justifikasi Teknis | Data Pendukung
[58 empty] | Quantity | Unit price
| 20 | Drilling Rig Crew/ Contract Rig Crew | Qty | Unit Price | 0 | Unit | Qty | Unit Price | 0 | Qty | Unit Price | 0 | Qty | Unit Price | 0 | Qty | Unit Price | 0 | Qty | Unit Price | 0 | Qty | Unit Price | 0 | Qty | Unit Price | 0 | Qty | Unit Price | 0 | Qty | Unit Price | 0 | Qty | Unit Price | 0 | Qty | Unit Price | 0 | Qty | Unit Price | 0 | Qty | Unit Price | 0 | Qty | Unit Price | 0 | Qty | Unit Price | 0 | Qty | Unit Price | 0 | Qty | Unit Price | 0
|  |  | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| Line | DESCRIPTION | Historical |  |  | Proposed Original |  |  |  | EVALUATED |  |  | Historical |  |  | Proposed Original |  |  | EVALUATED |  |  | Historical |  |  | Proposed Original |  |  | EVALUATED |  |  | Historical |  |  | Proposed Original |  |  | EVALUATED |  |  | Historical |  |  | Proposed Original |  |  | EVALUATED |  |  | Historical |  |  | Proposed Original |  |  | EVALUATED |  |  | Variance (Aw vs Ak) |  | Justifikasi Teknis | Data Pendukung
[58 empty] | Quantity | Unit price
| 21 | Mud, Chemical & Engin. Services | Qty | Unit Price | 0 | Unit | Qty | Unit Price | 0 | Qty | Unit Price | 0 | Qty | Unit Price | 0 | Qty | Unit Price | 0 | Qty | Unit Price | 0 | Qty | Unit Price | 0 | Qty | Unit Price | 0 | Qty | Unit Price | 0 | Qty | Unit Price | 0 | Qty | Unit Price | 0 | Qty | Unit Price | 0 | Qty | Unit Price | 0 | Qty | Unit Price | 0 | Qty | Unit Price | 0 | Qty | Unit Price | 0 | Qty | Unit Price | 0 | Qty | Unit Price | 0
|  | Dry Hole Based | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | MUD, CHEMICAL & ENG SERVICES | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| Line | DESCRIPTION | Historical |  |  | Proposed Original |  |  |  | EVALUATED |  |  | Historical |  |  | Proposed Original |  |  | EVALUATED |  |  | Historical |  |  | Proposed Original |  |  | EVALUATED |  |  | Historical |  |  | Proposed Original |  |  | EVALUATED |  |  | Historical |  |  | Proposed Original |  |  | EVALUATED |  |  | Historical |  |  | Proposed Original |  |  | EVALUATED |  |  | Variance (Aw vs Ak) |  | Justifikasi Teknis | Data Pendukung
[58 empty] | Quantity | Unit price
| 22 | Water | Qty | Unit Price | 0 | Unit | Qty | Unit Price | 0 | Qty | Unit Price | 0 | Qty | Unit Price | 0 | Qty | Unit Price | 0 | Qty | Unit Price | 0 | Qty | Unit Price | 0 | Qty | Unit Price | 0 | Qty | Unit Price | 0 | Qty | Unit Price | 0 | Qty | Unit Price | 0 | Qty | Unit Price | 0 | Qty | Unit Price | 0 | Qty | Unit Price | 0 | Qty | Unit Price | 0 | Qty | Unit Price | 0 | Qty | Unit Price | 0 | Qty | Unit Price | 0
|  | Dry Hole Based | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| Line | DESCRIPTION | Historical |  |  | Proposed Original |  |  |  | EVALUATED |  |  | Historical |  |  | Proposed Original |  |  | EVALUATED |  |  | Historical |  |  | Proposed Original |  |  | EVALUATED |  |  | Historical |  |  | Proposed Original |  |  | EVALUATED |  |  | Historical |  |  | Proposed Original |  |  | EVALUATED |  |  | Historical |  |  | Proposed Original |  |  | EVALUATED |  |  | Variance (Aw vs Ak) |  | Justifikasi Teknis | Data Pendukung
[58 empty] | Quantity | Unit price
| 23 | Bit, Reamers and Coreheads | Qty | Unit Price | 0 | Unit | Qty | Unit Price | 0 | Qty | Unit Price | 0 | Qty | Unit Price | 0 | Qty | Unit Price | 0 | Qty | Unit Price | 0 | Qty | Unit Price | 0 | Qty | Unit Price | 0 | Qty | Unit Price | 0 | Qty | Unit Price | 0 | Qty | Unit Price | 0 | Qty | Unit Price | 0 | Qty | Unit Price | 0 | Qty | Unit Price | 0 | Qty | Unit Price | 0 | Qty | Unit Price | 0 | Qty | Unit Price | 0 | Qty | Unit Price | 0
|  |  | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| Line | DESCRIPTION | Historical |  |  | Proposed Original |  |  |  | EVALUATED |  |  | Historical |  |  | Proposed Original |  |  | EVALUATED |  |  | Historical |  |  | Proposed Original |  |  | EVALUATED |  |  | Historical |  |  | Proposed Original |  |  | EVALUATED |  |  | Historical |  |  | Proposed Original |  |  | EVALUATED |  |  | Historical |  |  | Proposed Original |  |  | EVALUATED |  |  | Variance (Aw vs Ak) |  | Justifikasi Teknis | Data Pendukung
[58 empty] | Quantity | Unit price
| 24 | Equipments Rental | Qty | Unit Price | 0 | Unit | Qty | Unit Price | 0 | Qty | Unit Price | 0 | Qty | Unit Price | 0 | Qty | Unit Price | 0 | Qty | Unit Price | 0 | Qty | Unit Price | 0 | Qty | Unit Price | 0 | Qty | Unit Price | 0 | Qty | Unit Price | 0 | Qty | Unit Price | 0 | Qty | Unit Price | 0 | Qty | Unit Price | 0 | Qty | Unit Price | 0 | Qty | Unit Price | 0 | Qty | Unit Price | 0 | Qty | Unit Price | 0 | Qty | Unit Price | 0
|  | Dry Hole Based | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| Line | DESCRIPTION | Historical |  |  | Proposed Original |  |  |  | EVALUATED |  |  | Historical |  |  | Proposed Original |  |  | EVALUATED |  |  | Historical |  |  | Proposed Original |  |  | EVALUATED |  |  | Historical |  |  | Proposed Original |  |  | EVALUATED |  |  | Historical |  |  | Proposed Original |  |  | EVALUATED |  |  | Historical |  |  | Proposed Original |  |  | EVALUATED |  |  | Variance (Aw vs Ak) |  | Justifikasi Teknis | Data Pendukung
[58 empty] | Quantity | Unit price
| 25 | Directional Drilling and Surveys | Qty | Unit Price | 0 | Unit | Qty | Unit Price | 0 | Qty | Unit Price | 0 | Qty | Unit Price | 0 | Qty | Unit Price | 0 | Qty | Unit Price | 0 | Qty | Unit Price | 0 | Qty | Unit Price | 0 | Qty | Unit Price | 0 | Qty | Unit Price | 0 | Qty | Unit Price | 0 | Qty | Unit Price | 0 | Qty | Unit Price | 0 | Qty | Unit Price | 0 | Qty | Unit Price | 0 | Qty | Unit Price | 0 | Qty | Unit Price | 0 | Qty | Unit Price | 0
|  |  | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| Line | DESCRIPTION | Historical |  |  | Proposed Original |  |  |  | EVALUATED |  |  | Historical |  |  | Proposed Original |  |  | EVALUATED |  |  | Historical |  |  | Proposed Original |  |  | EVALUATED |  |  | Historical |  |  | Proposed Original |  |  | EVALUATED |  |  | Historical |  |  | Proposed Original |  |  | EVALUATED |  |  | Historical |  |  | Proposed Original |  |  | EVALUATED |  |  | Variance (Aw vs Ak) |  | Justifikasi Teknis | Data Pendukung
[58 empty] | Quantity | Unit price
| 26 | Diving Service | Qty | Unit Price | 0 | Unit | Qty | Unit Price | 0 | Qty | Unit Price | 0 | Qty | Unit Price | 0 | Qty | Unit Price | 0 | Qty | Unit Price | 0 | Qty | Unit Price | 0 | Qty | Unit Price | 0 | Qty | Unit Price | 0 | Qty | Unit Price | 0 | Qty | Unit Price | 0 | Qty | Unit Price | 0 | Qty | Unit Price | 0 | Qty | Unit Price | 0 | Qty | Unit Price | 0 | Qty | Unit Price | 0 | Qty | Unit Price | 0 | Qty | Unit Price | 0
|  |  | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| Line | DESCRIPTION | Historical |  |  | Proposed Original |  |  |  | EVALUATED |  |  | Historical |  |  | Proposed Original |  |  | EVALUATED |  |  | Historical |  |  | Proposed Original |  |  | EVALUATED |  |  | Historical |  |  | Proposed Original |  |  | EVALUATED |  |  | Historical |  |  | Proposed Original |  |  | EVALUATED |  |  | Historical |  |  | Proposed Original |  |  | EVALUATED |  |  | Variance (Aw vs Ak) |  | Justifikasi Teknis | Data Pendukung
[58 empty] | Quantity | Unit price
| 27 | Casing Installation | Qty | Unit Price | 0 | Unit | Qty | Unit Price | 0 | Qty | Unit Price | 0 | Qty | Unit Price | 0 | Qty | Unit Price | 0 | Qty | Unit Price | 0 | Qty | Unit Price | 0 | Qty | Unit Price | 0 | Qty | Unit Price | 0 | Qty | Unit Price | 0 | Qty | Unit Price | 0 | Qty | Unit Price | 0 | Qty | Unit Price | 0 | Qty | Unit Price | 0 | Qty | Unit Price | 0 | Qty | Unit Price | 0 | Qty | Unit Price | 0 | Qty | Unit Price | 0
|  |  | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| Line | DESCRIPTION | Historical |  |  | Proposed Original |  |  |  | EVALUATED |  |  | Historical |  |  | Proposed Original |  |  | EVALUATED |  |  | Historical |  |  | Proposed Original |  |  | EVALUATED |  |  | Historical |  |  | Proposed Original |  |  | EVALUATED |  |  | Historical |  |  | Proposed Original |  |  | EVALUATED |  |  | Historical |  |  | Proposed Original |  |  | EVALUATED |  |  | Variance (Aw vs Ak) |  | Justifikasi Teknis | Data Pendukung
[58 empty] | Quantity | Unit price
| 28 | Cement, Cementing and Pump Fees | Qty | Unit Price | 0 | Unit | Qty | Unit Price | 0 | Qty | Unit Price | 0 | Qty | Unit Price | 0 | Qty | Unit Price | 0 | Qty | Unit Price | 0 | Qty | Unit Price | 0 | Qty | Unit Price | 0 | Qty | Unit Price | 0 | Qty | Unit Price | 0 | Qty | Unit Price | 0 | Qty | Unit Price | 0 | Qty | Unit Price | 0 | Qty | Unit Price | 0 | Qty | Unit Price | 0 | Qty | Unit Price | 0 | Qty | Unit Price | 0 | Qty | Unit Price | 0
|  | Dry Hole Based | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | CEMENTS AND MATERIALS | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| Line | DESCRIPTION | Historical |  |  | Proposed Original |  |  |  | EVALUATED |  |  | Historical |  |  | Proposed Original |  |  | EVALUATED |  |  | Historical |  |  | Proposed Original |  |  | EVALUATED |  |  | Historical |  |  | Proposed Original |  |  | EVALUATED |  |  | Historical |  |  | Proposed Original |  |  | EVALUATED |  |  | Historical |  |  | Proposed Original |  |  | EVALUATED |  |  | Variance (Aw vs Ak) |  | Justifikasi Teknis | Data Pendukung
[58 empty] | Quantity | Unit price
| 30 | FORMATION EVALUATION |  |  | 0 |  |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0
| 31 | Coring | Qty | Unit Price | 0 | Unit | Qty | Unit Price | 0 | Qty | Unit Price | 0 | Qty | Unit Price | 0 | Qty | Unit Price | 0 | Qty | Unit Price | 0 | Qty | Unit Price | 0 | Qty | Unit Price | 0 | Qty | Unit Price | 0 | Qty | Unit Price | 0 | Qty | Unit Price | 0 | Qty | Unit Price | 0 | Qty | Unit Price | 0 | Qty | Unit Price | 0 | Qty | Unit Price | 0 | Qty | Unit Price | 0 | Qty | Unit Price | 0 | Qty | Unit Price | 0
|  |  | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| Line | DESCRIPTION | Historical |  |  | Proposed Original |  |  |  | EVALUATED |  |  | Historical |  |  | Proposed Original |  |  | EVALUATED |  |  | Historical |  |  | Proposed Original |  |  | EVALUATED |  |  | Historical |  |  | Proposed Original |  |  | EVALUATED |  |  | Historical |  |  | Proposed Original |  |  | EVALUATED |  |  | Historical |  |  | Proposed Original |  |  | EVALUATED |  |  | Variance (Aw vs Ak) |  | Justifikasi Teknis | Data Pendukung
[58 empty] | Quantity | Unit price
| 32 | Mud Logging services | Qty | Unit Price | 0 | Unit | Qty | Unit Price | 0 | Qty | Unit Price | 0 | Qty | Unit Price | 0 | Qty | Unit Price | 0 | Qty | Unit Price | 0 | Qty | Unit Price | 0 | Qty | Unit Price | 0 | Qty | Unit Price | 0 | Qty | Unit Price | 0 | Qty | Unit Price | 0 | Qty | Unit Price | 0 | Qty | Unit Price | 0 | Qty | Unit Price | 0 | Qty | Unit Price | 0 | Qty | Unit Price | 0 | Qty | Unit Price | 0 | Qty | Unit Price | 0
|  | Dry Hole Based | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| Line | DESCRIPTION | Historical |  |  | Proposed Original |  |  |  | EVALUATED |  |  | Historical |  |  | Proposed Original |  |  | EVALUATED |  |  | Historical |  |  | Proposed Original |  |  | EVALUATED |  |  | Historical |  |  | Proposed Original |  |  | EVALUATED |  |  | Historical |  |  | Proposed Original |  |  | EVALUATED |  |  | Historical |  |  | Proposed Original |  |  | EVALUATED |  |  | Variance (Aw vs Ak) |  | Justifikasi Teknis | Data Pendukung
[58 empty] | Quantity | Unit price
| 33 | Drill Stem Test | Qty | Unit Price | 0 | Unit | Qty | Unit Price | 0 | Qty | Unit Price | 0 | Qty | Unit Price | 0 | Qty | Unit Price | 0 | Qty | Unit Price | 0 | Qty | Unit Price | 0 | Qty | Unit Price | 0 | Qty | Unit Price | 0 | Qty | Unit Price | 0 | Qty | Unit Price | 0 | Qty | Unit Price | 0 | Qty | Unit Price | 0 | Qty | Unit Price | 0 | Qty | Unit Price | 0 | Qty | Unit Price | 0 | Qty | Unit Price | 0 | Qty | Unit Price | 0
|  |  | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| Line | DESCRIPTION | Historical |  |  | Proposed Original |  |  |  | EVALUATED |  |  | Historical |  |  | Proposed Original |  |  | EVALUATED |  |  | Historical |  |  | Proposed Original |  |  | EVALUATED |  |  | Historical |  |  | Proposed Original |  |  | EVALUATED |  |  | Historical |  |  | Proposed Original |  |  | EVALUATED |  |  | Historical |  |  | Proposed Original |  |  | EVALUATED |  |  | Variance (Aw vs Ak) |  | Justifikasi Teknis | Data Pendukung
[58 empty] | Quantity | Unit price
| 34 | Open Hole Logging and Services | Qty | Unit Price | 0 | Unit | Qty | Unit Price | 0 | Qty | Unit Price | 0 | Qty | Unit Price | 0 | Qty | Unit Price | 0 | Qty | Unit Price | 0 | Qty | Unit Price | 0 | Qty | Unit Price | 0 | Qty | Unit Price | 0 | Qty | Unit Price | 0 | Qty | Unit Price | 0 | Qty | Unit Price | 0 | Qty | Unit Price | 0 | Qty | Unit Price | 0 | Qty | Unit Price | 0 | Qty | Unit Price | 0 | Qty | Unit Price | 0 | Qty | Unit Price | 0
|  |  | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| Line | DESCRIPTION | Historical |  |  | Proposed Original |  |  |  | EVALUATED |  |  | Historical |  |  | Proposed Original |  |  | EVALUATED |  |  | Historical |  |  | Proposed Original |  |  | EVALUATED |  |  | Historical |  |  | Proposed Original |  |  | EVALUATED |  |  | Historical |  |  | Proposed Original |  |  | EVALUATED |  |  | Historical |  |  | Proposed Original |  |  | EVALUATED |  |  | Variance (Aw vs Ak) |  | Justifikasi Teknis | Data Pendukung
[58 empty] | Quantity | Unit price
| 36 | COMPLETION |  |  | 0 |  |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0
| 37 | Casing, Liner and Tubing Installation | Qty | Unit Price | 0 | Unit | Qty | Unit Price | 0 | Qty | Unit Price | 0 | Qty | Unit Price | 0 | Qty | Unit Price | 0 | Qty | Unit Price | 0 | Qty | Unit Price | 0 | Qty | Unit Price | 0 | Qty | Unit Price | 0 | Qty | Unit Price | 0 | Qty | Unit Price | 0 | Qty | Unit Price | 0 | Qty | Unit Price | 0 | Qty | Unit Price | 0 | Qty | Unit Price | 0 | Qty | Unit Price | 0 | Qty | Unit Price | 0 | Qty | Unit Price | 0
|  |  | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| Line | DESCRIPTION | Historical |  |  | Proposed Original |  |  |  | EVALUATED |  |  | Historical |  |  | Proposed Original |  |  | EVALUATED |  |  | Historical |  |  | Proposed Original |  |  | EVALUATED |  |  | Historical |  |  | Proposed Original |  |  | EVALUATED |  |  | Historical |  |  | Proposed Original |  |  | EVALUATED |  |  | Historical |  |  | Proposed Original |  |  | EVALUATED |  |  | Variance (Aw vs Ak) |  | Justifikasi Teknis | Data Pendukung
[58 empty] | Quantity | Unit price
| 38 | Cement, Cementing and Pump Fees | Qty | Unit Price | 0 | Unit | Qty | Unit Price | 0 | Qty | Unit Price | 0 | Qty | Unit Price | 0 | Qty | Unit Price | 0 | Qty | Unit Price | 0 | Qty | Unit Price | 0 | Qty | Unit Price | 0 | Qty | Unit Price | 0 | Qty | Unit Price | 0 | Qty | Unit Price | 0 | Qty | Unit Price | 0 | Qty | Unit Price | 0 | Qty | Unit Price | 0 | Qty | Unit Price | 0 | Qty | Unit Price | 0 | Qty | Unit Price | 0 | Qty | Unit Price | 0
|  | CEMENTS AND MATERIALS | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| Line | DESCRIPTION | Historical |  |  | Proposed Original |  |  |  | EVALUATED |  |  | Historical |  |  | Proposed Original |  |  | EVALUATED |  |  | Historical |  |  | Proposed Original |  |  | EVALUATED |  |  | Historical |  |  | Proposed Original |  |  | EVALUATED |  |  | Historical |  |  | Proposed Original |  |  | EVALUATED |  |  | Historical |  |  | Proposed Original |  |  | EVALUATED |  |  | Variance (Aw vs Ak) |  | Justifikasi Teknis | Data Pendukung
[58 empty] | Quantity | Unit price
| 39 | Cased Hole Electrical Logging Services | Qty | Unit Price | 0 | Unit | Qty | Unit Price | 0 | Qty | Unit Price | 0 | Qty | Unit Price | 0 | Qty | Unit Price | 0 | Qty | Unit Price | 0 | Qty | Unit Price | 0 | Qty | Unit Price | 0 | Qty | Unit Price | 0 | Qty | Unit Price | 0 | Qty | Unit Price | 0 | Qty | Unit Price | 0 | Qty | Unit Price | 0 | Qty | Unit Price | 0 | Qty | Unit Price | 0 | Qty | Unit Price | 0 | Qty | Unit Price | 0 | Qty | Unit Price | 0
|  |  | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| Line | DESCRIPTION | Historical |  |  | Proposed Original |  |  |  | EVALUATED |  |  | Historical |  |  | Proposed Original |  |  | EVALUATED |  |  | Historical |  |  | Proposed Original |  |  | EVALUATED |  |  | Historical |  |  | Proposed Original |  |  | EVALUATED |  |  | Historical |  |  | Proposed Original |  |  | EVALUATED |  |  | Historical |  |  | Proposed Original |  |  | EVALUATED |  |  | Variance (Aw vs Ak) |  | Justifikasi Teknis | Data Pendukung
[58 empty] | Quantity | Unit price
| 40 | Perforating and Wireline Services | Qty | Unit Price | 0 | Unit | Qty | Unit Price | 0 | Qty | Unit Price | 0 | Qty | Unit Price | 0 | Qty | Unit Price | 0 | Qty | Unit Price | 0 | Qty | Unit Price | 0 | Qty | Unit Price | 0 | Qty | Unit Price | 0 | Qty | Unit Price | 0 | Qty | Unit Price | 0 | Qty | Unit Price | 0 | Qty | Unit Price | 0 | Qty | Unit Price | 0 | Qty | Unit Price | 0 | Qty | Unit Price | 0 | Qty | Unit Price | 0 | Qty | Unit Price | 0
|  |  | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| Line | DESCRIPTION | Historical |  |  | Proposed Original |  |  |  | EVALUATED |  |  | Historical |  |  | Proposed Original |  |  | EVALUATED |  |  | Historical |  |  | Proposed Original |  |  | EVALUATED |  |  | Historical |  |  | Proposed Original |  |  | EVALUATED |  |  | Historical |  |  | Proposed Original |  |  | EVALUATED |  |  | Historical |  |  | Proposed Original |  |  | EVALUATED |  |  | Variance (Aw vs Ak) |  | Justifikasi Teknis | Data Pendukung
[58 empty] | Quantity | Unit price
| 41 | Stimulation Treatment / Completion Fluids | Qty | Unit Price | 0 | Unit | Qty | Unit Price | 0 | Qty | Unit Price | 0 | Qty | Unit Price | 0 | Qty | Unit Price | 0 | Qty | Unit Price | 0 | Qty | Unit Price | 0 | Qty | Unit Price | 0 | Qty | Unit Price | 0 | Qty | Unit Price | 0 | Qty | Unit Price | 0 | Qty | Unit Price | 0 | Qty | Unit Price | 0 | Qty | Unit Price | 0 | Qty | Unit Price | 0 | Qty | Unit Price | 0 | Qty | Unit Price | 0 | Qty | Unit Price | 0
|  |  | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| Line | DESCRIPTION | Historical |  |  | Proposed Original |  |  |  | EVALUATED |  |  | Historical |  |  | Proposed Original |  |  | EVALUATED |  |  | Historical |  |  | Proposed Original |  |  | EVALUATED |  |  | Historical |  |  | Proposed Original |  |  | EVALUATED |  |  | Historical |  |  | Proposed Original |  |  | EVALUATED |  |  | Historical |  |  | Proposed Original |  |  | EVALUATED |  |  | Variance (Aw vs Ak) |  | Justifikasi Teknis | Data Pendukung
[58 empty] | Quantity | Unit price
| 42 | Production Test | Qty | Unit Price | 0 | Unit | Qty | Unit Price | 0 | Qty | Unit Price | 0 | Qty | Unit Price | 0 | Qty | Unit Price | 0 | Qty | Unit Price | 0 | Qty | Unit Price | 0 | Qty | Unit Price | 0 | Qty | Unit Price | 0 | Qty | Unit Price | 0 | Qty | Unit Price | 0 | Qty | Unit Price | 0 | Qty | Unit Price | 0 | Qty | Unit Price | 0 | Qty | Unit Price | 0 | Qty | Unit Price | 0 | Qty | Unit Price | 0 | Qty | Unit Price | 0
|  |  | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| Line | DESCRIPTION | Historical |  |  | Proposed Original |  |  |  | EVALUATED |  |  | Historical |  |  | Proposed Original |  |  | EVALUATED |  |  | Historical |  |  | Proposed Original |  |  | EVALUATED |  |  | Historical |  |  | Proposed Original |  |  | EVALUATED |  |  | Historical |  |  | Proposed Original |  |  | EVALUATED |  |  | Historical |  |  | Proposed Original |  |  | EVALUATED |  |  | Variance (Aw vs Ak) |  | Justifikasi Teknis | Data Pendukung
[58 empty] | Quantity | Unit price
| 44 | GENERAL |  |  | 0 |  |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0
| 45 | Project Management Team | Qty | Unit Price | 0 | Unit | Qty | Unit Price | 0 | Qty | Unit Price | 0 | Qty | Unit Price | 0 | Qty | Unit Price | 0 | Qty | Unit Price | 0 | Qty | Unit Price | 0 | Qty | Unit Price | 0 | Qty | Unit Price | 0 | Qty | Unit Price | 0 | Qty | Unit Price | 0 | Qty | Unit Price | 0 | Qty | Unit Price | 0 | Qty | Unit Price | 0 | Qty | Unit Price | 0 | Qty | Unit Price | 0 | Qty | Unit Price | 0 | Qty | Unit Price | 0
|  | Dry Hole Based | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| Line | DESCRIPTION | Historical |  |  | Proposed Original |  |  |  | EVALUATED |  |  | Historical |  |  | Proposed Original |  |  | EVALUATED |  |  | Historical |  |  | Proposed Original |  |  | EVALUATED |  |  | Historical |  |  | Proposed Original |  |  | EVALUATED |  |  | Historical |  |  | Proposed Original |  |  | EVALUATED |  |  | Historical |  |  | Proposed Original |  |  | EVALUATED |  |  | Variance (Aw vs Ak) |  | Justifikasi Teknis | Data Pendukung
[58 empty] | Quantity | Unit price
| 46 | Insurance | Qty | Unit Price | 0 | Unit | Qty | Unit Price | 0 | Qty | Unit Price | 0 | Qty | Unit Price | 0 | Qty | Unit Price | 0 | Qty | Unit Price | 0 | Qty | Unit Price | 0 | Qty | Unit Price | 0 | Qty | Unit Price | 0 | Qty | Unit Price | 0 | Qty | Unit Price | 0 | Qty | Unit Price | 0 | Qty | Unit Price | 0 | Qty | Unit Price | 0 | Qty | Unit Price | 0 | Qty | Unit Price | 0 | Qty | Unit Price | 0 | Qty | Unit Price | 0
|  |  | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| Line | DESCRIPTION | Historical |  |  | Proposed Original |  |  |  | EVALUATED |  |  | Historical |  |  | Proposed Original |  |  | EVALUATED |  |  | Historical |  |  | Proposed Original |  |  | EVALUATED |  |  | Historical |  |  | Proposed Original |  |  | EVALUATED |  |  | Historical |  |  | Proposed Original |  |  | EVALUATED |  |  | Historical |  |  | Proposed Original |  |  | EVALUATED |  |  | Variance (Aw vs Ak) |  | Justifikasi Teknis | Data Pendukung
[58 empty] | Quantity | Unit price
| 47 | Permit and Fees | Qty | Unit Price | 0 | Unit | Qty | Unit Price | 0 | Qty | Unit Price | 0 | Qty | Unit Price | 0 | Qty | Unit Price | 0 | Qty | Unit Price | 0 | Qty | Unit Price | 0 | Qty | Unit Price | 0 | Qty | Unit Price | 0 | Qty | Unit Price | 0 | Qty | Unit Price | 0 | Qty | Unit Price | 0 | Qty | Unit Price | 0 | Qty | Unit Price | 0 | Qty | Unit Price | 0 | Qty | Unit Price | 0 | Qty | Unit Price | 0 | Qty | Unit Price | 0
|  |  | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| Line | DESCRIPTION | Historical |  |  | Proposed Original |  |  |  | EVALUATED |  |  | Historical |  |  | Proposed Original |  |  | EVALUATED |  |  | Historical |  |  | Proposed Original |  |  | EVALUATED |  |  | Historical |  |  | Proposed Original |  |  | EVALUATED |  |  | Historical |  |  | Proposed Original |  |  | EVALUATED |  |  | Historical |  |  | Proposed Original |  |  | EVALUATED |  |  | Variance (Aw vsAk) |  | Justifikasi Teknis | Data Pendukung
[58 empty] | Quantity | Unit price
| 48 | Marine Rental & charter | Qty | Unit Price | 0 | Unit | Qty | Unit Price | 0 | Qty | Unit Price | 0 | Qty | Unit Price | 0 | Qty | Unit Price | 0 | Qty | Unit Price | 0 | Qty | Unit Price | 0 | Qty | Unit Price | 0 | Qty | Unit Price | 0 | Qty | Unit Price | 0 | Qty | Unit Price | 0 | Qty | Unit Price | 0 | Qty | Unit Price | 0 | Qty | Unit Price | 0 | Qty | Unit Price | 0 | Qty | Unit Price | 0 | Qty | Unit Price | 0 | Qty | Unit Price | 0
|  |  | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| Line | DESCRIPTION | Historical |  |  | Proposed Original |  |  |  | EVALUATED |  |  | Historical |  |  | Proposed Original |  |  | EVALUATED |  |  | Historical |  |  | Proposed Original |  |  | EVALUATED |  |  | Historical |  |  | Proposed Original |  |  | EVALUATED |  |  | Historical |  |  | Proposed Original |  |  | EVALUATED |  |  | Historical |  |  | Proposed Original |  |  | EVALUATED |  |  | Variance (Aw vs Ak) |  | Justifikasi Teknis | Data Pendukung
[58 empty] | Quantity | Unit price
| 49 | Helicopter / charter flight | Qty | Unit Price | 0 | Unit | Qty | Unit Price | 0 | Qty | Unit Price | 0 | Qty | Unit Price | 0 | Qty | Unit Price | 0 | Qty | Unit Price | 0 | Qty | Unit Price | 0 | Qty | Unit Price | 0 | Qty | Unit Price | 0 | Qty | Unit Price | 0 | Qty | Unit Price | 0 | Qty | Unit Price | 0 | Qty | Unit Price | 0 | Qty | Unit Price | 0 | Qty | Unit Price | 0 | Qty | Unit Price | 0 | Qty | Unit Price | 0 | Qty | Unit Price | 0
|  |  | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| Line | DESCRIPTION | Historical |  |  | Proposed Original |  |  |  | EVALUATED |  |  | Historical |  |  | Proposed Original |  |  | EVALUATED |  |  | Historical |  |  | Proposed Original |  |  | EVALUATED |  |  | Historical |  |  | Proposed Original |  |  | EVALUATED |  |  | Historical |  |  | Proposed Original |  |  | EVALUATED |  |  | Historical |  |  | Proposed Original |  |  | EVALUATED |  |  | Variance (Aw vs Ak) |  | Justifikasi Teknis | Data Pendukung
[58 empty] | Quantity | Unit price
| 50 | Land Transportation | Qty | Unit Price | 0 | Unit | Qty | Unit Price | 0 | Qty | Unit Price | 0 | Qty | Unit Price | 0 | Qty | Unit Price | 0 | Qty | Unit Price | 0 | Qty | Unit Price | 0 | Qty | Unit Price | 0 | Qty | Unit Price | 0 | Qty | Unit Price | 0 | Qty | Unit Price | 0 | Qty | Unit Price | 0 | Qty | Unit Price | 0 | Qty | Unit Price | 0 | Qty | Unit Price | 0 | Qty | Unit Price | 0 | Qty | Unit Price | 0 | Qty | Unit Price | 0
|  | Dry Hole Based | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
` |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| Line | DESCRIPTION | Historical |  |  | Proposed Original |  |  |  | EVALUATED |  |  | Historical |  |  | Proposed Original |  |  | EVALUATED |  |  | Historical |  |  | Proposed Original |  |  | EVALUATED |  |  | Historical |  |  | Proposed Original |  |  | EVALUATED |  |  | Historical |  |  | Proposed Original |  |  | EVALUATED |  |  | Historical |  |  | Proposed Original |  |  | EVALUATED |  |  | Variance (Aw vsAk) |  | Justifikasi Teknis | Data Pendukung
[58 empty] | Quantity | Unit price
| 51 | Other Transportation | Qty | Unit Price | 0 | Unit | Qty | Unit Price | 0 | Qty | Unit Price | 0 | Qty | Unit Price | 0 | Qty | Unit Price | 0 | Qty | Unit Price | 0 | Qty | Unit Price | 0 | Qty | Unit Price | 0 | Qty | Unit Price | 0 | Qty | Unit Price | 0 | Qty | Unit Price | 0 | Qty | Unit Price | 0 | Qty | Unit Price | 0 | Qty | Unit Price | 0 | Qty | Unit Price | 0 | Qty | Unit Price | 0 | Qty | Unit Price | 0 | Qty | Unit Price | 0
|  | Dry Hole Based | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| Line | DESCRIPTION | Historical |  |  | Proposed Original |  |  |  | EVALUATED |  |  | Historical |  |  | Proposed Original |  |  | EVALUATED |  |  | Historical |  |  | Proposed Original |  |  | EVALUATED |  |  | Historical |  |  | Proposed Original |  |  | EVALUATED |  |  | Historical |  |  | Proposed Original |  |  | EVALUATED |  |  | Historical |  |  | Proposed Original |  |  | EVALUATED |  |  | Variance (Aw vs Ak) |  | Justifikasi Teknis | Data Pendukung
[58 empty] | Quantity | Unit price
| 52 | Fuel and Lubricant | Qty | Unit Price | 0 | Unit | Qty | Unit Price | 0 | Qty | Unit Price | 0 | Qty | Unit Price | 0 | Qty | Unit Price | 0 | Qty | Unit Price | 0 | Qty | Unit Price | 0 | Qty | Unit Price | 0 | Qty | Unit Price | 0 | Qty | Unit Price | 0 | Qty | Unit Price | 0 | Qty | Unit Price | 0 | Qty | Unit Price | 0 | Qty | Unit Price | 0 | Qty | Unit Price | 0 | Qty | Unit Price | 0 | Qty | Unit Price | 0 | Qty | Unit Price | 0
|  | Dry Hole Based | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
` |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| Line | DESCRIPTION | Historical |  |  | Proposed Original |  |  |  | EVALUATED |  |  | Historical |  |  | Proposed Original |  |  | EVALUATED |  |  | Historical |  |  | Proposed Original |  |  | EVALUATED |  |  | Historical |  |  | Proposed Original |  |  | EVALUATED |  |  | Historical |  |  | Proposed Original |  |  | EVALUATED |  |  | Historical |  |  | Proposed Original |  |  | EVALUATED |  |  | Variance (Aw vs Ak) |  | Justifikasi Teknis | Data Pendukung
[58 empty] | Quantity | Unit price
| 53 | Camp Facilities | Qty | Unit Price | 0 | Unit | Qty | Unit Price | 0 | Qty | Unit Price | 0 | Qty | Unit Price | 0 | Qty | Unit Price | 0 | Qty | Unit Price | 0 | Qty | Unit Price | 0 | Qty | Unit Price | 0 | Qty | Unit Price | 0 | Qty | Unit Price | 0 | Qty | Unit Price | 0 | Qty | Unit Price | 0 | Qty | Unit Price | 0 | Qty | Unit Price | 0 | Qty | Unit Price | 0 | Qty | Unit Price | 0 | Qty | Unit Price | 0 | Qty | Unit Price | 0
|  | Dry Hole Based | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| Line | DESCRIPTION | Historical |  |  | Proposed Original |  |  |  | EVALUATED |  |  | Historical |  |  | Proposed Original |  |  | EVALUATED |  |  | Historical |  |  | Proposed Original |  |  | EVALUATED |  |  | Historical |  |  | Proposed Original |  |  | EVALUATED |  |  | Historical |  |  | Proposed Original |  |  | EVALUATED |  |  | Historical |  |  | Proposed Original |  |  | EVALUATED |  |  | Variance (Aw vs Ak) |  | Justifikasi Teknis | Data Pendukung
[58 empty] | Quantity | Unit price
| 54 | ALLOCATED OVERHEADS - FIELD OFFICE | Qty | Unit Price | 0 | Unit | Qty | Unit Price | 0 | Qty | Unit Price | 0 | Qty | Unit Price | 0 | Qty | Unit Price | 0 | Qty | Unit Price | 0 | Qty | Unit Price | 0 | Qty | Unit Price | 0 | Qty | Unit Price | 0 | Qty | Unit Price | 0 | Qty | Unit Price | 0 | Qty | Unit Price | 0 | Qty | Unit Price | 0 | Qty | Unit Price | 0 | Qty | Unit Price | 0 | Qty | Unit Price | 0 | Qty | Unit Price | 0 | Qty | Unit Price | 0
|  |  | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | TOTAL | 0 | [5 empty] | 0 | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0

## BS19
nilai yang tertera pada BS-19 merupakan total nilai dari seluruh sumur yang termasuk di dalam AFE ini
BUDGET SCHEDULE 19
|  |  |  | A | B |  |  | C
LINE | DESCRIPTION |  |  | Historical | Proposed Original | VARIANCE | % (B vs A) | EVALUATED | VARIANCE | % (C vs B) | REMARKS
1 | TANGIBLE COST
2 |  | CASING |  | 0 | 0 | 0 |  | 0 | 0
3 |  | CASING ACCESSORIES |  | 0 | 0 | 0 |  | 0 | 0
4 |  | TUBING |  | 0 | 162513.6278 | 162513.6278 |  | 124058.7146 | -38454.9132 | -23.66%
5 |  | WELL EQUIPMENT + SURFACE |  | 0 | 83904.344 | 83904.344 |  | 82487.0409 | -1417.3031 | -1.689%
6 |  | WELL EQUIPMENT + SUBSURFACE |  | 0 | 248319.2675 | 248319.2675 |  | 244124.6853 | -4194.5822 | -1.689%
7 |  | OTHER TANGIBLE COST |  | 0 | 0 | 0 |  | 0 | 0
8 | [8 empty] | 0
9 |  | TOTAL TANGIBLE COST |  | 0 | 494737.2393 | 494737.2393 |  | 450670.4408 | -44066.7986 | -8.907%
| INTANGIBLE COST |  |  |  |  | VARIANCE | % (B vs A) |  | VARIANCE | % (C vs B)
10 |  | PREPARATION AND TERMINATION
11 |  |  | SURVEYS | 0 | 0 | 0 |  | 0 | 0
12 |  |  | LOCATION STACKING AND POSITIONING | 0 | 0 | 0 |  | 0 | 0
13 |  |  | WELLSITE AND ACCESS ROAD PREPARATION | 0 | 240000 | 240000 |  | 235945.9459 | -4054.0541 | -1.689%
14 |  |  | SERVICE LINES & COMMUNICATIONS | 0 | 18518.3734 | 18518.3734 |  | 18205.5631 | -312.8104 | -1.689%
15 |  |  | WATER SYSTEMS | 0 | 0 | 0 |  | 0 | 0
16 |  |  | RIGGING UP/RIGGING DOWN | 0 | 105341.5808 | 105341.5808 |  | 105341.5808 | 0 | 0%
17 |  |  | SUB TOTAL | 0 | 363859.9542 | 363859.9542 |  | 359493.0898 | -4366.8644 | -1.2%
18 |  | DRILLING/WORKOVER OPERATIONS
19 |  |  | CONTRACT RIG | 0 | 672416.953 | 672416.953 |  | 672416.953 | 0 | 0%
20 |  |  | DRILLING RIG CREW / CONTRACT RIG CREW | 0 | 0 | 0 |  | 0 | 0
21 |  |  | MUD, CHEMICAL & ENGINEERING SERVICES | 0 | 38664.0862 | 38664.0862 |  | 38010.9767 | -653.1096 | -1.689%
22 |  |  | WATER | 0 | 0 | 0 |  | 0 | 0
23 |  |  | BITS, REAMER AND CORE HEADS | 0 | 23248.9873 | 23248.9873 |  | 22856.2679 | -392.7194 | -1.689%
24 |  |  | EQUIPMENT RENT | 0 | 0 | 0 |  | 0 | 0
25 |  |  | DIRECTIONAL DRILLING AND SURVEYS | 0 | 0 | 0 |  | 0 | 0
26 |  |  | DIVING SERVICES | 0 | 0 | 0 |  | 0 | 0
27 |  |  | CASING INSTALLATION | 0 | 0 | 0 |  | 0 | 0
28 |  |  | CEMENT, CEMENTING AND PUMP FEES | 0 | 0 | 0 |  | 0 | 0
29 |  |  | SUB TOTAL | 0 | 734330.0266 | 734330.0266 |  | 733284.1976 | -1045.8289 | -0.1424%
30 |  | FORMATION EVALUATION
31 |  |  | CORING | 0 | 0 | 0 |  | 0 | 0
32 |  |  | MUD LOGGING SERVICES | 0 | 0 | 0 |  | 0 | 0
33 |  |  | DRILL STEM TEST | 0 | 0 | 0 |  | 0 | 0
34 |  |  | OPENHOLE ELECTRICAL LOGGING SERVICES | 0 | 0 | 0 |  | 0 | 0
35 |  |  | SUB TOTAL | 0 | 0 | 0 |  | 0 | 0
36 |  | COMPLETION
37 |  |  | CASING LINER AND TUBING INSTALLATION | 0 | 0 | 0 |  | 0 | 0
38 |  |  | CEMENT, CEMENTING AND PUMP FEES | 0 | 132000 | 132000 |  | 132000 | 0 | 0%
39 |  |  | CASED HOLE ELECTRICAL LOGGING SERVICES | 0 | 354000 | 354000 |  | 313218.2432 | -40781.7568 | -11.52%
40 |  |  | PERFORATING AND WIRELINE SERVICES | 0 | 162000 | 162000 |  | 159263.5135 | -2736.4865 | -1.689%
41 |  |  | STIMULATON TREATMENT | 0 | 840000 | 840000 |  | 816000 | -24000 | -2.857%
42 |  |  | PRODUCTION TEST | 0 | 77547.7715 | 77547.7715 |  | 76237.8429 | -1309.9286 | -1.689%
43 |  |  | SUB TOTAL | 0 | 1565547.7715 | 1565547.7715 |  | 1496719.5997 | -68828.1718 | -4.396%
44 |  | GENERAL
45 |  |  | PROJECT MANAGEMENT TEAM | 0 | 122476.929 | 122476.929 |  | 120408.0619 | -2068.867 | -1.689%
46 |  |  | INSURANCE | 0 | 24415.6009 | 24415.6009 |  | 24003.1752 | -412.4257 | -1.689%
47 |  |  | PERMITS & FEES | 0 | 53731.3433 | 53731.3433 |  | 29493.2432 | -24238.1 | -45.11%
48 |  |  | MARINE RENTAL AND CHARTERS | 0 | 0 | 0 |  | 0 | 0
49 |  |  | HELICOPTER AVIATION AND CHARGERS | 0 | 0 | 0 |  | 0 | 0
50 |  |  | LAND TRANSPORTATION | 0 | 32204 | 32204 |  | 31660.0135 | -543.9865 | -1.689%
51 |  |  | OTHER TRANSPORTATION | 0 | 0 | 0 |  | 0 | 0
52 |  |  | FUEL AND LUBRICANTS | 0 | 136841.5808 | 136841.5808 |  | 129313.3333 | -7528.2474 | -5.501%
53 |  |  | CAMP FACILITIES | 0 | 34920 | 34920 |  | 34330.1351 | -589.8649 | -1.689%
54 |  |  | ALLOCATED OVERHEAD - FIELD OFFICE | 0 | 10576.3693 | 10576.3693 |  | 10397.7144 | -178.6549 | -1.689%
55 |  |  | - JAKARTA OFFICE |  |  | 0 |  |  | 0
|  |  | - OVERSEAS |  |  | 0 |  |  | 0
|  |  | TECHNICAL SERVICES FROM ABROAD |  |  | 0 |  |  | 0
56 |  |  | SUB TOTAL | 0 | 415165.8232 | 415165.8232 |  | 379605.6768 | -35560.1464 | -8.565%
57 |  | TOTAL INTANGIBLE COST |  | 0 | 3078903.5755 | 3078903.5755 |  | 2969102.5639 | -109801.0116 | -3.566%
58 | TOTAL COST |  |  | 0 | 3573640.8148 | 3573640.8148 |  | 3419773.0047 | -153867.8102 | -4.306%

## BS19 Print
[5 empty] | SKK Migas | [6 empty] | SCHEDULE NO. 19
[5 empty] | PRODUCTION SHARING CONTRACT | [6 empty] | AFE NO. : 23-190-221-OO
AUTHORIZATION FOR EXPENDITURES - DRILLING / WORKOVER / WELL SERVICE
[5 empty] | PROJECT TYPE | : DRILLING / WORKOVER / WELL SERVICE
[5 empty] | WELL NAME | : WO Bundling PENDOPO (6 sumur WO terdiri dari 4 sumur Tipe 2 dan 2 sumur Tipe 4)
OPERATOR |  |  | : PERTAMINA EP |  | WELL TYPE | : EXPLORATION/DELINEATION/DEVELOPMENT
CONTRACT AREA |  |  | : INDONESIA |  | PLATFORM/TRIPOD | : Land Rig
[5 empty] | FIELD/STRUCTURE | : PENDOPO
[5 empty] | BASIN | : Central Sumatra Basin
[5 empty] | Oil AND GAS RESERVOIR | : CONVENTIONAL / UNCONVENTIONAL
LOCATION |  |  | : Onshore |  | SURFACE COORDINATE | LAT : |  | LONG | :
WATER DEPTH |  |  | : 000 |  | ELEVATION | GL : _____Ft KB: ______Ft
|  |  | PROGRAM | [8 empty] | PROGRAM
SPUD DATE : |  |  | 2023-02-08 | [7 empty] | RIG DAYS
COMPLETION DATE : |  |  | 2023-09-21 | [7 empty] | Mob/Demob Days :
PLACED INTO SERVICE : |  |  | 2023-12-20 | [7 empty] | Moving Days : | 24
DRILLING DAYS : |  |  | 117.3333 | [7 empty] | Operation Days : | 117.3333
CLOSED OUT DATE : |  |  | 2024-06-17 | [7 empty] | TOTAL DEPTH : | 50199.3
[11 empty] | WELL COST PER FOOT $/Ft : | 68.1239
[11 empty] | WELL COST PER DAY $/DAY : | 24196.5071
WELL STATUS :
STRING TYPE : SINGLE / DUAL / TRIPLE
EXPRESSED IN U.S. DOLLARS
LINE | DESCRIPTION | [8 empty] | ORIGINAL BUDGET | REVISED BUDGET
[10 empty] | 1 | 2 | 3
1 | TANGIBLE COST
2 | CASING | [8 empty] | 0
3 | CASING ACCESSORIES | [8 empty] | 0
4 | TUBING | [8 empty] | 162513.6278 | 124058.7146
5 | WELL EQUIPMENT - SURFACE | [8 empty] | 83904.344 | 82487.0409
6 | WELL EQUIPMENT - SUBSURFACE | [8 empty] | 248319.2675 | 244124.6853
7 | OTHER TANGIBLE COST | [8 empty] | 0 | 0
8 | TOTAL TANGIBLE COST | [8 empty] | 494737.2393 | 450670.4408
9 | INTANGIBLE COST
10 | PREPARATION AND TERMINATION | [8 empty] | 0
11 | - SURVEYS | [8 empty] | 0 | 0
12 | - LOCATION STAKING AND POSITIONING | [8 empty] | 0 | 0
13 | - WELLSITE AND ACCESS ROAD PREPARATION | [8 empty] | 240000 | 235945.9459
14 | - SERVICE LINES & COMMUNICATIONS | [8 empty] | 18518.3734 | 18205.5631
15 | - WATER SYSTEMS | [8 empty] | 0 | 0
16 | - RIGGING UP / RIGGING DOWN | [8 empty] | 105341.5808 | 105341.5808
17 |  | Subtotal | [7 empty] | 363859.9542 | 359493.0898
18 | DRILLING / WORKOVER /WELL SERVICE OPERATIONS
19 | - CONTRACT RIG | [8 empty] | 672416.953 | 672416.953
20 | - DRILLING RIG CREW / CONTRACT RIG CREW | [8 empty] | 0 | 0
21 | - MUD, CHEMICAL & ENGINEERING SERVICES | [8 empty] | 38664.0862 | 38010.9767
22 | - WATER | [8 empty] | 0 | 0
23 | - BITS, REAMER AND CORE HEADS | [8 empty] | 23248.9873 | 22856.2679
24 | - EQUIPMENT RENT | [8 empty] | 0 | 0
25 | - DIRECTIONAL DRILLING AND SURVEYS | [8 empty] | 0 | 0
26 | - DIVING SERVICES | [8 empty] | 0 | 0
27 | - CASING INSTALLATION | [8 empty] | 0 | 0
28 | - CEMENT, CEMENTING AND PUMP FEES | [8 empty] | 0 | 0
29 |  | Subtotal | [7 empty] | 734330.0266 | 733284.1976
30 | FORMATION EVALUATION
31 | - CORING | [8 empty] | 0 | 0
32 | - MUD LOGGING SERVICES | [8 empty] | 0 | 0
33 | - DRILL STEM TEST | [8 empty] | 0 | 0
34 | - OPEN HOLE ELECTRICAL LOGGING SERVICES | [8 empty] | 0 | 0
35 |  | Subtotal | [7 empty] | 0 | 0
36 | COMPLETION
37 | - CASING LINER AND TUBING INSTALLATION | [8 empty] | 0 | 0
38 | - CEMENT, CEMENTING AND PUMP FEES | [8 empty] | 132000 | 132000
39 | - CASED HOLE ELECTRICAL LOGGING SERVICES | [8 empty] | 354000 | 313218.2432
40 | - PERFORATING AND WIRELINE SERVICES | [8 empty] | 162000 | 159263.5135
41 | - STIMULATION TREATMENT | [8 empty] | 840000 | 816000
42 | - PRODUCTION TEST | [8 empty] | 77547.7715 | 76237.8429
43 |  | Subtotal | [7 empty] | 1565547.7715 | 1496719.5997
44 | GENERAL
45 | - PROJECT MANAGEMENT TEAM | [8 empty] | 122476.929 | 120408.0619
46 | - INSURANCE | [8 empty] | 24415.6009 | 24003.1752
47 | - PERMITS AND FEES | [8 empty] | 53731.3433 | 29493.2432
48 | - MARINE RENTAL AND CHARTERS | [8 empty] | 0 | 0
49 | - HELICOPTER AVIATION AND CHARGES | [8 empty] | 0 | 0
50 | - LAND TRANSPORTATION | [8 empty] | 32204 | 31660.0135
51 | - OTHER TRANSPORTATION | [8 empty] | 0 | 0
52 | - FUEL AND LUBRICANTS | [8 empty] | 136841.5808 | 129313.3333
53 | - CAMP FACILITIES | [8 empty] | 34920 | 34330.1351
54 | - ALLOCATED OVERHEAD |  | - FIELD OFFICE | [6 empty] | 10576.3693 | 10397.7144
55 |  |  | - JAKARTA OFFICE | [6 empty] | 0 | 0
56 |  | Subtotal | [7 empty] | 415165.8232 | 379605.6768
57 | TOTAL INTANGIBLE COST | [8 empty] | 3078903.5755 | 2969102.5639
58 | TOTAL COSTS | [8 empty] | 3573640.8148 | 3419773.0047
59 | TIME PHASED EXPENDITURES :
60 | -2023 | [8 empty] | 3573640.8148 | 3419773.0047
61 | -2024
62 | -2025
63 | TOTAL | [8 empty] | 3573640.8148 | 3419773.0047 | 0
REMARKS
OPERATOR : |  | APPROVED BY | [7 empty] | US$ 1 = Rp. 14.800
Workover Bundling Pendopo (6 sumur WO) : 1. Pendopo Tipe 2 2. Pendopo Tipe 2 3. Pendopo Tipe 2 4. Pendopo Tipe 2 5. Pendopo Tipe 4 6. Pendopo Tipe 4
|  | NAME & POSITION |  | Tri Sasongko VP Development & Drilling |  |  | Darman Ruisani Sr. Manager Finance
DATE
SKK Migas |  | APPROVED BY
NAME & POSITION
DATE

## BS20
[5 empty] | SKK Migas |  |  |  | SCHEDULE NO. 20
[5 empty] | PRODUCTION SHARING CONTRACT |  |  |  | ATTACHMENT TO SCHEDULE NO. 19
[5 empty] | AUTHORIZATION FOR EXPENDITURES - MATERIAL LIST - DRILLING / WORKOVER / WELL SERVICE |  |  |  | AFE NO. : 23-190-221-OO
:
|  |  | PROJECT TYPE |  | : DRILLING / WORKOVER / WELL SERVICE
OPERATOR |  | : PERTAMINA EP | WELL TYPE |  | : EXPLORATION/DELINEATION/DEVELOPMENT
CONTRACT AREA |  | : INDONESIA | FIELD STRUCTURE |  | : PENDOPO
|  |  | WELL NAME |  | : WO Bundling PENDOPO (6 sumur WO terdiri dari 4 sumur Tipe 2 dan 2 sumur Tipe 4)
EXPRESSED IN U.S. DOLLARS
LINE | DESCRIPTION |  | UNIT OF MEASUREMENT | BUDGET | [7 empty] | `
|  |  |  | ISSUED FROM STOCK |  |  | NEW PURCHASE |  |  | GRAND TOTAL
|  |  |  | QTY | U.P. | TOTAL | QTY | U.P. | TOTAL | QTY | AMOUNT
| 1 |  | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10
1 | TANGIBLE COST
2 | CASING
2 | Free standing drill column |  | Joint | 0 | - | 0 | 0 | - | 0 | 0 | 0
2 | Drive pipe |  | Joint | 0 | - | 0 | 0 | - | 0 | 0 | 0
2 | Conductor casing |  | Joint | 0 | - | 0 | 0 | - | 0 | 0 | 0
2 | Surface Casing |  | Joint | 0 | - | 0 | 0 | - | 0 | 0 | 0
2 | Intermediate casing |  | Joint | 0 | - | 0 | 0 | - | 0 | 0 | 0
2 | Production casing |  | Joint | 0 | - | 0 | 0 | - | 0 | 0 | 0
2 | Casing nipples |  | Joint | 0 | - | 0 | 0 | - | 0 | 0 | 0
2 | Casing liners |  | Joint | 0 | - | 0 | 0 | - | 0 | 0 | 0
2 | Casing crossover joints |  | Joint | 0 | - | 0 | 0 | - | 0 | 0 | 0
|  | Subtotal | 5: 0; 8: 0; 10: 0
3 | CASING ACCESSORIES
3 | Casing Shoes/Float Shoes |  | Piece | 0 | - | 0 | 0 | - | 0 | 0 | 0
3 | Casing collars/Float Collars |  | Piece | 0 | - | 0 | 0 | - | 0 | 0 | 0
3 | Stage cementing collars |  | Piece | 0 | - | 0 | 0 | - | 0 | 0 | 0
3 | Liner hangers |  | Piece | 0 | - | 0 | 0 | - | 0 | 0 | 0
3 | Liner packer hangers |  | Piece | 0 | - | 0 | 0 | - | 0 | 0 | 0
3 | External casing packers |  | Piece | 0 | - | 0 | 0 | - | 0 | 0 | 0
3 | Other |  | Piece | 0 | - | 0 | 0 | - | 0 | 0 | 0
|  | Subtotal | 5: 0; 8: 0; 10: 0
4 | TUBING
4 | Tubing 2 7/8 in, J-55, 6,5 PPF, EUE, R2 |  | Joint | 0 | - | 0 | 760 | 153 | 116280 | 760 | 116280
4 | Pup Joint 2-7/8" x 2 ft |  | Joint | 0 | - | 0 | 12 | 129.3707 | 1552.4489 | 12 | 1552.4489
4 | Pup Joint 2-7/8" x 4 ft |  | Joint | 0 | - | 0 | 12 | 146.8707 | 1762.4489 | 12 | 1762.4489
4 | Pup Joint 2-7/8" x 6 ft |  | Joint | 0 | - | 0 | 12 | 172.614 | 2071.3678 | 12 | 2071.3678
4 | Pup Joint 2-7/8" x 8 ft |  | Joint | 0 | - | 0 | 12 | 199.3707 | 2392.4489 | 12 | 2392.4489
4 | Pup Joint over 2" and under 5" OD |  | Joint | 0 | - | 0 | 0 | - | 0 | 0 | 0
|  | Subtotal | 5: 0; 8: 124058.7146; 10: 124058.7146
5 | WELL EQUIPMENT - SURFACE
5 | X-MASTREE,7.1/16 X 3.1/8 IN,3.000 BB |  | Piece | 0 | - | 0 | 2 | 29359.6502 | 58719.3003 | 2 | 58719.3003
5 | ADAPTER FLANGE |  | Piece | 0 | - | 0 | 4 | 3939.0973 | 15756.3892 | 4 | 15756.3892
5 | GATE VLV, X-MAST TREE,3.1/8 IN, 3000 PSI |  | Piece | 0 | - | 0 | 4 | 2002.8378 | 8011.3514 | 4 | 8011.3514
5 | Crossover flanges |  | Piece | 0 | - | 0 | 0 | - | 0 | 0 | 0
5 | Tubing head spools |  | Piece | 0 | - | 0 | 0 | - | 0 | 0 | 0
5 | Tubing hangers |  | Piece | 0 | - | 0 | 0 | - | 0 | 0 | 0
5 | Well head unit |  | Piece | 0 | - | 0 | 0 | - | 0 | 0 | 0
5 | Complete christmas-tree |  | Piece | 0 | - | 0 | 0 | - | 0 | 0 | 0
|  | Subtotal | 5: 0; 8: 82487.0409; 10: 82487.0409
6 | WELL EQUIPMENT - SUBSURFACE
6 | Packer 7", SG, 20-26 PPF, 2 7/8" EU |  | Piece | 0 | - | 0 | 6 | 6394.6069 | 38367.6412 | 6 | 38367.6412
6 | Redress Kit Packer 5-1/2 in |  | Piece | 0 | - | 0 | 8 | 129.2693 | 1034.1546 | 8 | 1034.1546
6 | Redress Kit Packer 6-5/8 in |  | Piece | 0 | - | 0 | 8 | 189.1894 | 1513.5151 | 8 | 1513.5151
6 | Redress Kit Packer 7 in SG |  | Piece | 0 | - | 0 | 8 | 478.9234 | 3831.3876 | 8 | 3831.3876
6 | REDRESS KIT,PACKER 4-1/2 IN-2-3/8 IN |  | Piece | 0 | - | 0 | 8 | 99.6858 | 797.4865 | 8 | 797.4865
6 | SRP Equipment |  | Piece | 0 | - | 0 | 6 | 33096.7501 | 198580.5003 | 6 | 198580.5003
6 | Blast joints |  | Piece | 0 | - | 0 | 0 | - | 0 | 0 | 0
6 | Seal assemblies |  | Piece | 0 | - | 0 | 0 | - | 0 | 0 | 0
6 | Crossovers |  | Piece | 0 | - | 0 | 0 | - | 0 | 0 | 0
6 | Expansion joints |  | Piece | 0 | - | 0 | 0 | - | 0 | 0 | 0
6 | Liners/Slotted liners (run as part of tubing) |  | Piece | 0 | - | 0 | 0 | - | 0 | 0 | 0
6 | Sand screen (wire wrapped screen/gravel packed) |  | Piece | 0 | - | 0 | 0 | - | 0 | 0 | 0
6 | Perforated nipples |  | Piece | 0 | - | 0 | 0 | - | 0 | 0 | 0
6 | Hydrotrip pressure subs |  | Piece | 0 | - | 0 | 0 | - | 0 | 0 | 0
6 | Perforated spear tubes |  | Piece | 0 | - | 0 | 0 | - | 0 | 0 | 0
6 | Snap catch seal nipples |  | Piece | 0 | - | 0 | 0 | - | 0 | 0 | 0
6 | Differential displacing valves |  | Piece | 0 | - | 0 | 0 | - | 0 | 0 | 0
6 | Sucker rod pumps |  | Piece | 0 | - | 0 | 0 | - | 0 | 0 | 0
6 | Pumps rods |  | Piece | 0 | - | 0 | 0 | - | 0 | 0 | 0
6 | Plunger pumps |  | Piece | 0 | - | 0 | 0 | - | 0 | 0 | 0
6 | Submersible pumps |  | Piece | 0 | - | 0 | 0 | - | 0 | 0 | 0
6 | Pump cables |  | Piece | 0 | - | 0 | 0 | - | 0 | 0 | 0
6 | Jet pumps |  | Piece | 0 | - | 0 | 0 | - | 0 | 0 | 0
6 | Gas lift valves |  | Piece | 0 | - | 0 | 0 | - | 0 | 0 | 0
|  | Subtotal | 5: 0; 8: 244124.6853; 10: 244124.6853
7 | OTHER TANGIBLE COST
7 | Hydraulic pumping unit |  | Piece | 0 | - | 0 | 0 | - | 0 | 0 | 0
7 | Swab material |  | Piece | 0 | - | 0 | 0 | - | 0 | 0 | 0
|  | Subtotal | 5: 0; 8: 0; 10: 0
8 | TOTAL TANGIBLE COST |  | 5: 0; 8: 450670.4408; 10: 450670.4408
9 | INTANGIBLE COST
18 | DRILLING/WORKOVER OPERATIONS
21 | Mud material products |  |  | 0 | - | 0 | 0 | - | 0 | 0 | 0
21 | Pottasium Chloride (KCl) |  | Sack | 0 | - | 0 | 1200 | 20.6256 | 24750.7297 | 1200 | 24750.7297
21 | Corrosion Inhibitor (BEKA-4612) |  | Sack | 0 | - | 0 | 6 | 1068.5798 | 6411.4789 | 6 | 6411.4789
21 | Tawas |  | Sack | 0 | - | 0 | 3000 | 0.29311 | 879.3356 | 3000 | 879.3356
21 | XCD |  | Sack | 0 | - | 0 | 60 | 99.4905 | 5969.4324 | 60 | 5969.4324
23 | Rock Bit 6 in, IADC 217 |  | Sack | 0 | - | 0 | 6 | 2727.9591 | 16367.7544 | 6 | 16367.7544
23 | Rock Bit 5 1/4 in, IADC 211 |  | Piece | 0 | - | 0 | 4 | 1179.7297 | 4718.9189 | 4 | 4718.9189
23 | Rock Bit 3 3/4 in, IADC 211 |  | Piece | 0 | - | 0 | 4 | 442.3986 | 1769.5946 | 4 | 1769.5946
|  | Subtotal | 5: 0; 8: 60867.2446; 10: 60867.2446
36 | COMPLETION
42 | PRODUCTION TEST |  |  | 0 | - | 0 | 0 | - | 0 | 0 | 0
42 | Rubber Swab 2.7/8" MV |  | Piece | 0 | - | 0 | 60 | 40.2706 | 2416.2332 | 60 | 2416.2332
42 | MIT-PBU TESTING |  | Piece | 0 | - | 0 | 4 | 18455.4024 | 73821.6097 | 4 | 73821.6097
44 | GENERAL
52 | Fuel |  | Litres | 0 | - | 0 | 95083.3333 | 1.36 | 129313.3333 | 95083.3333 | 129313.3333
57 | TOTAL INTANGIBLE COST |  | 5: 0; 8: 266418.4209; 10: 266418.4209
58 | TOTAL COSTS |  | 5: 0; 8: 717088.8616; 10: 717088.8616
PT. PERTAMINA EP
APPROVED BY Tri Sasongko Position VP Development & Drilling Date __________
APPROVED BY Darman Ruisani Position Sr. Manager Finance Date __________

## Supporting Document
Pendopo Type 2 | Pendopo Type 4
DIISI DENGAN SNAPSHOT PERSETUJUAN TEKNIS DAN REFERENSI BIAYA (KONTRAK ATAU QUOTATION)

## Drilling_Input_Summary
DEPARTEMEN AFE
DIVISI RENCANA ANGGARAN
DRILLING INPUT SUMMARY
GENERAL INFORMATION
KKKS |  | PERTAMINA EP |  |  |  | No. AFE | 23-190-221-OO
WILAYAH KERJA |  | INDONESIA |  |  |  | STATUS AFE | Proposed Original
FIELD |  | Pendopo |  |  |  | WELLS NAME | 1. Sumur Pendopo Tipe 2
POD |  | POFD Lapangan Benakat Barat POFD Lapangan Talang Akar dan Pendopo |  |  |  |  | 2. Sumur Pendopo Tipe 2
Year of POD Approved | [6 empty] | 3. Sumur Pendopo Tipe 2
4. Sumur Pendopo Tipe 2
LOCATION |  | Onshore |  |  |  |  | 5. Sumur Pendopo Tipe 4
BASIN/PLAY |  | Central Sumatra Basin |  |  |  |  | 6. Sumur Pendopo Tipe 4
MAIN PRODUCT |  | Oil
Number of Well in AFE |  | 6
Information |  | short description about the changes in technical/cost paramater for proposed Revision
DRILLING PARAMETER
1. Sumur Pendopo Tipe 2 |  | Historical | Proposed Original | Evaluated | 2. Sumur Pendopo Tipe 2 |  | Historical | Proposed Original | Evaluated
WELL PARAMETER |  |  |  |  | WELL PARAMETER
PROGRAM TYPE |  | Conventional | Conventional | Conventional | PROGRAM TYPE |  | Conventional | Conventional | Conventional
PROJECT TYPE |  | Workover | Workover | Workover | PROJECT TYPE |  | Workover | Workover | Workover
WELL TYPE |  | Development | Development | Development | WELL TYPE |  | Development | Development | Development
WELL SUB-TYPE |  | Production | Production | Production | WELL SUB-TYPE |  | Production | Production | Production
WELL DESIGN |  | Slim Hole | Slim Hole | Slim Hole | WELL DESIGN |  | Slim Hole | Slim Hole | Slim Hole
DRILLING PROGRAM |  |  |  |  | DRILLING PROGRAM
SIDE TRACK |  |  |  |  | SIDE TRACK
CORING |  |  |  |  | CORING
CORING TYPE |  | 0 | 0 | Side Wall Core | CORING TYPE |  | 0 | 0 | Side Wall Core
COMPLETION |  |  |  |  | COMPLETION
COMPLETION TYPE |  | Single | Single | Single | COMPLETION TYPE |  | Single | Single | Single
DST |  |  |  |  | DST
TRAJECTORY |  | Vertical | Vertical | Vertical | TRAJECTORY |  | Vertical | Vertical | Vertical
MUD TYPE [1] |  | Completion Fluid | Completion Fluid | Completion Fluid | MUD TYPE [1] |  | Completion Fluid | Completion Fluid | Completion Fluid
MUD TYPE [2] |  | Completion Fluid | Completion Fluid | Completion Fluid | MUD TYPE [2] |  | Completion Fluid | Completion Fluid | Completion Fluid
RIG TYPE |  | Workover Rig | Workover Rig | Workover Rig | RIG TYPE |  | Workover Rig | Workover Rig | Workover Rig
RIG POWER [HP] |  | 350 | 350 | 350 | RIG POWER [HP] |  | 350 | 350 | 350
Notes : keterangan tambahan terkait sumur ini |  |  |  |  | Notes : keterangan tambahan terkait sumur ini
3. Sumur Pendopo Tipe 2 |  | Historical | Proposed Original | Evaluated | 4. Sumur Pendopo Tipe 2 |  | Historical | Proposed Original | Evaluated
WELL PARAMETER |  |  |  |  | WELL PARAMETER
PROGRAM TYPE |  | Conventional | Conventional | Conventional | PROGRAM TYPE |  | Conventional | Conventional | Conventional
PROJECT TYPE |  | Workover | Workover | Workover | PROJECT TYPE |  | Workover | Workover | Workover
WELL TYPE |  | Development | Development | Development | WELL TYPE |  | Development | Development | Development
WELL SUB-TYPE |  | Production | Production | Production | WELL SUB-TYPE |  | Production | Production | Production
WELL DESIGN |  | 0 | Slim Hole | Slim Hole | WELL DESIGN |  | 0 | Slim Hole | Slim Hole
DRILLING PROGRAM |  |  |  |  | DRILLING PROGRAM
SIDE TRACK |  |  |  |  | SIDE TRACK
CORING |  |  |  |  | CORING
CORING TYPE |  | 0 | 0 | Side Wall Core | CORING TYPE |  | 0 | 0 | Side Wall Core
COMPLETION |  |  |  |  | COMPLETION
COMPLETION TYPE |  | Single | Single | Single | COMPLETION TYPE |  | Single | Single | Single
DST |  |  |  |  | DST
TRAJECTORY |  | Vertical | Vertical | Vertical | TRAJECTORY |  | Vertical | Vertical | Vertical
MUD TYPE [1] |  | Completion Fluid | Completion Fluid | Completion Fluid | MUD TYPE [1] |  | Completion Fluid | Completion Fluid | Completion Fluid
MUD TYPE [2] |  | Completion Fluid | Completion Fluid | Completion Fluid | MUD TYPE [2] |  | Completion Fluid | Completion Fluid | Completion Fluid
RIG TYPE |  | Workover Rig | Workover Rig | Workover Rig | RIG TYPE |  | Workover Rig | Workover Rig | Workover Rig
RIG POWER [HP] |  | 350 | 350 | 350 | RIG POWER [HP] |  | 350 | 350 | 350
Notes : keterangan tambahan terkait sumur ini |  |  |  |  | Notes : keterangan tambahan terkait sumur ini
5. Sumur Pendopo Tipe 4 |  | Historical | Proposed Original | Evaluated | 6. Sumur Pendopo Tipe 4 |  | Historical | Proposed Original | Evaluated
WELL PARAMETER |  |  |  |  | WELL PARAMETER
PROGRAM TYPE |  | Conventional | Conventional | Conventional | PROGRAM TYPE |  | Conventional | Conventional | Conventional
PROJECT TYPE |  | Workover | Workover | Workover | PROJECT TYPE |  | Workover | Workover | Workover
WELL TYPE |  | Development | Development | Development | WELL TYPE |  | Development | Development | Development
WELL SUB-TYPE |  | Production | Production | Production | WELL SUB-TYPE |  | Production | Production | Production
WELL DESIGN |  | 3078903.5755 | Slim Hole | Slim Hole | WELL DESIGN |  | 0 | Slim Hole | Slim Hole
DRILLING PROGRAM |  |  |  |  | DRILLING PROGRAM
SIDE TRACK |  |  |  |  | SIDE TRACK
CORING |  |  |  |  | CORING
CORING TYPE |  | 0 | 0 | Side Wall Core | CORING TYPE |  | 0 | 0 | Side Wall Core
COMPLETION |  |  |  |  | COMPLETION
COMPLETION TYPE |  | Single | Single | Single | COMPLETION TYPE |  | Single | Single | Single
DST |  |  |  |  | DST
TRAJECTORY |  | Vertical | Vertical | Vertical | TRAJECTORY |  | Vertical | Vertical | Vertical
MUD TYPE [1] |  | Completion Fluid | Completion Fluid | Completion Fluid | MUD TYPE [1] |  | Completion Fluid | Completion Fluid | Completion Fluid
MUD TYPE [2] |  | Completion Fluid | Completion Fluid | Completion Fluid | MUD TYPE [2] |  | Completion Fluid | Completion Fluid | Completion Fluid
RIG TYPE |  | Workover Rig | Workover Rig | Workover Rig | RIG TYPE |  | Workover Rig | Workover Rig | Workover Rig
RIG POWER [HP] |  | 350 | 350 | 350 | RIG POWER [HP] |  | 350 | 350 | 350
Notes : keterangan tambahan terkait sumur ini |  |  |  |  | Notes : keterangan tambahan terkait sumur ini
0 |  | Historical | Proposed Original | Evaluated | 0 |  | Historical | Proposed Original | Evaluated
WELL PARAMETER |  |  |  |  | WELL PARAMETER
PROGRAM TYPE |  | Conventional | Conventional | Conventional | PROGRAM TYPE |  | Conventional | Conventional | Conventional
PROJECT TYPE |  | Workover | Workover | Workover | PROJECT TYPE |  | Workover | Workover | Workover
WELL TYPE |  | Development | Development | Development | WELL TYPE |  | Development | Development | Development
WELL SUB-TYPE |  | Production | Production | Production | WELL SUB-TYPE |  | Production | Production | Production
WELL DESIGN |  | 0 | Slim Hole | Slim Hole | WELL DESIGN |  | 0 | Slim Hole | Slim Hole
DRILLING PROGRAM |  |  |  |  | DRILLING PROGRAM
SIDE TRACK |  |  |  |  | SIDE TRACK
CORING |  |  |  |  | CORING
CORING TYPE |  | 0 | 0 | Side Wall Core | CORING TYPE |  | 0 | 0 | Side Wall Core
COMPLETION |  |  |  |  | COMPLETION
COMPLETION TYPE |  | Single | Single | Single | COMPLETION TYPE |  | Single | Single | Single
DST |  |  |  |  | DST
TRAJECTORY |  | Vertical | Vertical | Vertical | TRAJECTORY |  | Vertical | Vertical | Vertical
MUD TYPE [1] |  | Completion Fluid | Completion Fluid | Completion Fluid | MUD TYPE [1] |  | Completion Fluid | Completion Fluid | Completion Fluid
MUD TYPE [2] |  | Completion Fluid | Completion Fluid | Completion Fluid | MUD TYPE [2] |  | Completion Fluid | Completion Fluid | Completion Fluid
RIG TYPE |  | Workover Rig | Workover Rig | Workover Rig | RIG TYPE |  | Workover Rig | Workover Rig | Workover Rig
RIG POWER [HP] |  | 350 | 350 | 350 | RIG POWER [HP] |  | 350 | 350 | 350
Notes : keterangan tambahan terkait sumur ini |  |  |  |  | Notes : keterangan tambahan terkait sumur ini
0 |  | Historical | Proposed Original | Evaluated | 0 |  | Historical | Proposed Original | Evaluated
WELL PARAMETER |  |  |  |  | WELL PARAMETER
PROGRAM TYPE |  | Conventional | Conventional | Conventional | PROGRAM TYPE |  | Conventional | Conventional | Conventional
PROJECT TYPE |  | Workover | Workover | Workover | PROJECT TYPE |  | Workover | Workover | Workover
WELL TYPE |  | Development | Development | Development | WELL TYPE |  | Development | Development | Development
WELL SUB-TYPE |  | Production | Production | Production | WELL SUB-TYPE |  |  |  | Production
WELL DESIGN |  | 0 | Slim Hole | Slim Hole | WELL DESIGN |  | 0
DRILLING PROGRAM |  |  |  |  | DRILLING PROGRAM
SIDE TRACK |  |  |  |  | SIDE TRACK
CORING |  |  |  |  | CORING
CORING TYPE |  | 0 | 0 | Side Wall Core | CORING TYPE |  | 0 | 0 | 0
COMPLETION |  |  |  |  | COMPLETION
COMPLETION TYPE |  | Single | Single | Single | COMPLETION TYPE
DST |  |  |  |  | DST
TRAJECTORY |  | Vertical | Vertical | Vertical | TRAJECTORY |  | Vertical | Vertical | Vertical
MUD TYPE [1] |  | Completion Fluid | Completion Fluid | Completion Fluid | MUD TYPE [1] |  | Water Basemud | Water Basemud | Water Basemud
MUD TYPE [2] |  | Completion Fluid | Completion Fluid | Completion Fluid | MUD TYPE [2] |  | Water Basemud | Water Basemud | Water Basemud
RIG TYPE |  | Workover Rig | Workover Rig | Workover Rig | RIG TYPE |  | Land Rig | Land Rig | Land Rig
RIG POWER [HP] |  | 350 | 350 | 350 | RIG POWER [HP] |  | 350 | 350 | 350
Notes : keterangan tambahan terkait sumur ini |  |  |  |  | Notes : keterangan tambahan terkait sumur ini
DURATION of PROJECT |  | Historical | Proposed Original | Evaluated
RIG DAYS |  | 141.3333 | 141.3333 | 141.3333 | COST
Moving |  | 6 | 6 | 6 | 0
Rig up |  | 12 | 12 | 12 | 0
Drilling |  | 117.3333 | 117.3333 | 117.3333 | 0
Coring |  |  |  |  | 0
Test |  |  |  |  | 0
Completion |  |  |  |  | 0
P & A |  |  |  |  | 0
Rig down |  | 6 | 6 | 6 | 0
DEPTH [ft] |  | 3648.472 | 3648.472 | 3648.472
RATE of PENETRATION [ROP]
PROJECT COST
PROJECT COST (US$) |  | Historical | Proposed Original | Evaluated
Tangible Cost |  | 494737.2393 | 494737.2393 | 450670.4408
Intangible Cost |  | 3078903.5755 | 3078903.5755 | 2969102.5639
Survey & Preparation |  | 363859.9542 | 363859.9542 | 359493.0898
Drilling/Workover |  | 734330.0266 | 734330.0266 | 733284.1976
Formation Evaluation |  | 0 | 0 | 0
Completion |  | 1565547.7715 | 1565547.7715 | 1496719.5997
General |  | 415165.8232 | 415165.8232 | 379605.6768
TOTAL COST |  | 3573640.8148 | 3573640.8148 | 3419773.0047
UNIT COST & TECHNICAL
Cost/day (US$/day) |  | 25285.1944 | 25285.1944 | 24196.5071
Cost/depth (US$/ft)
Tangible Cost/depth (US$/ft)
Intangible Cost/day (US$/day)
Intangible Cost/day (US$/day)*
Site Preparation |  | 0 | 0 | 0
* exclude site preparation
* Rig Days exclude Moving
RIG UNIT OPERATING RATE (US$/day) |  |  | #REF! | #REF! | #REF!
RIG UNIT Standby RATE (US$/day) |  |  |  | 0 | 0
information

## Workover Program
DEPARTEMEN AFE
DIVISI RENCANA ANGGARAN
WORKOVER PROGRAM
DRILLING SCHEDULE DETAILS 1. Sumur Pendopo Tipe 2 | Historical |  |  |  | Proposed Original |  |  |  | Evaluated |  |  |  | ACTUAL |  |  |  | REMARKS | MOM DATE | PERIHAL
Operation Details | HOUR | DAY | CUMMULATIVE | Depth (ft) | HOUR | DAY | CUMMULATIVE | Depth (ft) | HOUR | DAY | CUMMULATIVE | Depth (ft) | HOUR | DAY | CUMMULATIVE | Depth (ft)
Moving |  |  | 0 | [16 empty] | Activities |  | Proposed Original |  |  | Evaluated |  |  | ACTUAL
Tow Rig to well | 0 |  | 0 |  | 24 | 1 | 1 |  | 24 | 1 | 1 | [10 empty] | Day | Cum Days | Depth (Ft) | Day | Cum Days | Depth (Ft) | Day | Cum Days | Depth (Ft)
[20 empty] | Moving Tow Rig to well, |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Rig Up | 0 | [18 empty] | Rig-up, termasuk R/U Top Drive dan stand-up DP & DC. |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Rig-up |  |  | 0 |  | 48 | 2 | 3 |  | 48 | 2 | 3 | [8 empty] | Workover | Preparation (Kill well & POOH existing string) | 1.0208 | 1.0208 | 3648.472 | 1.0208 | 1.0208 | 3648.472 | 0 | 0 | 0
[21 empty] | Squeeze lapisan Eksisting. Run Scraper. Run GR-CBL-CNL | 3.8333 | 4.8542 | 3648.472 | 3.8333 | 4.8542 | 3648.472 | 0 | 0 | 0
Workover | 0 | [19 empty] | Perbaikan bonding. DOC. Run Scraper. Re run GR-CBL-VDL | 5.4375 | 10.2917 | 3648.472 | 5.4375 | 10.2917 | 3648.472 | 0 | 0 | 0
Preparation (Kill well & POOH existing string) | 0 |  | 0 |  | 24.5 | 1.0208 | 4.0208 | 3648.472 | 24.5 | 1.0208 | 4.0208 | 3648.472 | [8 empty] | Perforasi Produksi. RIH RPP. Swab dan BHP Job. POOH RPP | 6.1667 | 16.4583 | 3648.472 | 6.1667 | 16.4583 | 3648.472 | 0 | 0 | 0
Squeeze lapisan Eksisting. Run Scraper. Run GR-CBL-CNL | 0 |  | 0 |  | 92 | 3.8333 | 7.8542 | 3648.472 | 92 | 3.8333 | 7.8542 | 3648.472 | [8 empty] | RIH RPP. Put well on production | 2.25 | 18.7083 | 3648.472 | 2.25 | 18.7083 | 3648.472 | 0 | 0 | 0
Perbaikan bonding. DOC. Run Scraper. Re run GR-CBL-VDL | 0 |  | 0 |  | 130.5 | 5.4375 | 13.2917 | 3648.472 | 130.5 | 5.4375 | 13.2917 | 3648.472 | [8 empty] | 0 | 0 | 18.7083 | 0 | 0 | 18.7083 | 0 | 0 | 0 | 0
Perforasi Produksi. RIH RPP. Swab dan BHP Job. POOH RPP | 0 |  | 0 |  | 148 | 6.1667 | 19.4583 | 3648.472 | 148 | 6.1667 | 19.4583 | 3648.472 | [8 empty] | 0 | 0 | 18.7083 | 0 | 0 | 18.7083 | 0 | 0 | 0 | 0
RIH RPP. Put well on production | 0 |  | 0 |  | 54 | 2.25 | 21.7083 | 3648.472 | 54 | 2.25 | 21.7083 | 3648.472 | [8 empty] | 0 | 0 | 18.7083 | 0 | 0 | 18.7083 | 0 | 0 | 0 | 0
| 0 |  | 0 |  | 0 |  | 21.7083 |  | 0 |  | 21.7083 | [9 empty] | 0 | 4.1 | 22.8083 | 0 | 4.1 | 22.8083 | 0 | 0 | 0 | 0
| 0 |  | 0 |  | 0 |  | 21.7083 |  | 0 |  | 21.7083 | [9 empty] | 0 | 2.1 | 24.9083 | 0 | 2.1 | 24.9083 | 0 | 0 | 0 | 0
| 0 |  | 0 |  | 0 |  | 21.7083 |  | 0 |  | 21.7083 | [8 empty] | Coring |  | 0 | 24.9083 | 0 | 0 | 24.9083 | 0 | 0 | 0 | 0
| 0 |  | 0 |  | 98.4 | 4.1 | 25.8083 |  | 98.4 | 4.1 | 25.8083 | [8 empty] | Test |  | 0 | 24.9083 | 0 | 0 | 24.9083 | 0 | 0 | 0 | 0
| 0 |  | 0 |  | 50.4 | 2.1 | 27.9083 |  | 50.4 | 2.1 | 27.9083 | [8 empty] | Completion |  | 0 | 24.9083 | 0 | 0 | 24.9083 | 0 | 0 | 0 | 0
[5 empty] | 0 |  | 27.9083 |  | 0 |  | 27.9083 | [8 empty] | P & A |  | 0 | 24.9083 | 0 | 0 | 24.9083 | 0 | 0 | 0 | 0
[5 empty] | 0 |  | 27.9083 |  | 0 |  | 27.9083 | [8 empty] | Rig Down |  | 0 | 24.9083 | 0 | 0 | 24.9083 | 0 | 0 | 0 | 0
[5 empty] | 0 |  | 27.9083 |  | 0 |  | 27.9083
Coring | 0 |  |  |  | 0 |  | 27.9083 |  | 0 |  | 27.9083
RIH Scrapper to Liner depth interval, RIH and perform production casing cementing job |  |  | 0 |  | 0 |  | 27.9083 |  | 0 |  | 27.9083
RIH Casing Scrapper to perforated zone interval. Cased Hole Logging |  |  | 0 |  | 0 |  | 27.9083 | 0 | 0 |  | 27.9083 | 0
|  |  |  | 0 | 0 |  | 27.9083 |  | 0 |  | 27.9083
|  |  |  | 0 | 0 |  | 27.9083 |  | 0 |  | 27.9083
|  |  |  | 0 | 0 |  | 27.9083 |  | 0 |  | 27.9083
Test | 0 |  |  |  | 0 |  | 27.9083 |  | 0 |  | 27.9083
DST |  |  | 0 |  | 0 |  | 27.9083 | 0 | 0 |  | 27.9083 | 0
|  |  | 0 | 0 | 0 |  | 27.9083 |  | 0 |  | 27.9083
|  |  | 0 | 0 | 0 |  | 27.9083 |  | 0 |  | 27.9083
Completion | 0 |  |  |  | 0 |  | 27.9083 |  | 0 |  | 27.9083
Trip, RIH & cement casing, BOP Job, RIH bit, Run Scrapper, CHL, Perforation 1st target, N/D BOP & N/U X-Masstree. Production Test | 0 |  | 0 |  | 0 |  | 27.9083 |  | 0 |  | 27.9083
Kill well, BOP Job, POOH RPP, Squeeze Job, DOC, Run scrapper, Perforation 2nd target, RIH RPP, Production test | 0 |  | 0 |  | 0 |  | 27.9083 |  | 0 |  | 27.9083
Kill well, BOP Job, POOH RPP, Fracturing Job, RIH RPP, N/D BOP & N/U X-Masstree. Production Test | 0 |  | 0 |  | 0 |  | 27.9083 |  | 0 |  | 27.9083
P & A | 0 |  |  |  | 0 |  | 27.9083 |  | 0 |  | 27.9083
P&A cmt job. L/D string. N/D BOP. N/U THS & Cap Assy |  |  | 0 |  | 0 |  | 27.9083 | 0 | 0 |  | 27.9083 | 0
|  |  |  | 0 | 0 |  | 27.9083 |  | 0 |  | 27.9083
|  |  |  | 0 | 0 |  | 27.9083 |  | 0 |  | 27.9083
|  |  |  | 0 | 0 |  | 27.9083 |  | 0 |  | 27.9083
0
Rig Down | 0
Rig Down |  | 0 | 0 |  | 24 | 1 | 22.7083 |  | 24 | 1 | 22.7083 |  |  | 0 | 0 | 0
|  | 0 |  | 0 |  | 0 | 22.7083 |  |  | 0 | 22.7083 |  |  | 0 | 0 | 0
|  | 0 |  | 0 |  | 0 | 22.7083 |  |  | 0 | 22.7083 |  |  | 0 | 0 | 0
|  | 0 |  | 0 |  | 0 | 22.7083 |  |  | 0 | 22.7083 |  |  | 0 | 0 | 0
|  | 0 |  | 0 |  | 0 | 22.7083 |  |  | 0 | 22.7083 |  |  | 0 | 0 | 0
Total days |  |  | 0 |  | 0 | 0 | 22.7083 |  |  | 0 | 22.7083 |  |  | 0 | 0
DRILLING SCHEDULE DETAILS 2. Sumur Pendopo Tipe 2 | Historical |  |  |  | Proposed Original |  |  |  | Evaluated |  |  |  | ACTUAL |  |  |  | REMARKS | MOM DATE | PERIHAL
Operation Details | HOUR | DAY | CUMMULATIVE | Depth (ft) | HOUR | DAY | CUMMULATIVE | Depth (ft) | HOUR | DAY | CUMMULATIVE | Depth (ft) | HOUR | DAY | CUMMULATIVE | Depth (ft)
Moving |  |  | 0 | [16 empty] | Activities |  | Proposed Original |  |  | Evaluated |  |  | ACTUAL
Tow Rig to well | 0 |  | 0 |  | 24 | 1 | 1 |  | 24 | 1 | 1 | [10 empty] | Day | Cum Days | Depth (Ft) | Day | Cum Days | Depth (Ft) | Day | Cum Days | Depth (Ft)
[20 empty] | Moving Tow Rig to well, |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Rig Up | 0 | [18 empty] | Rig-up, termasuk R/U Top Drive dan stand-up DP & DC. |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Rig-up |  |  | 0 |  | 48 | 2 | 3 |  | 48 | 2 | 3 | [8 empty] | Workover | Preparation (Kill well & POOH existing string) | 1 | 1 | 3648.472 | 1.0208 | 1.0208 | 5577.7 | 0 | 0 | 0
[21 empty] | Squeeze lapisan Eksisting. Run Scraper. Run GR-CBL-CNL | 3.8333 | 4.8333 | 3648.472 | 3.8333 | 4.8542 | 5577.7 | 0 | 0 | 0
Workover | 0 | [19 empty] | Perbaikan bonding. DOC. Run Scraper. Re run GR-CBL-VDL | 5.4375 | 10.2708 | 3648.472 | 5.4375 | 10.2917 | 5577.7 | 0 | 0 | 0
Preparation (Kill well & POOH existing string) | 0 |  | 0 |  | 24.5 | 1.0208 | 4.0208 | 3648.472 | 24.5 | 1.0208 | 4.0208 | 5577.7 | [8 empty] | Perforasi Produksi. RIH RPP. Swab dan BHP Job. POOH RPP | 6.1667 | 16.4375 | 3648.472 | 6.1667 | 16.4583 | 5577.7 | 0 | 0 | 0
Squeeze lapisan Eksisting. Run Scraper. Run GR-CBL-CNL | 0 |  | 0 |  | 92 | 3.8333 | 7.8542 | 3648.472 | 92 | 3.8333 | 7.8542 | 5577.7 | [8 empty] | RIH RPP. Put well on production | 2.25 | 18.6875 | 3648.472 | 2.25 | 18.7083 | 5577.7 | 0 | 0 | 0
Perbaikan bonding. DOC. Run Scraper. Re run GR-CBL-VDL | 0 |  | 0 |  | 130.5 | 5.4375 | 13.2917 | 3648.472 | 130.5 | 5.4375 | 13.2917 | 5577.7 | [8 empty] | 0 | 0 | 18.6875 | 0 | 0 | 18.7083 | 0 | 0 | 0 | 0
Perforasi Produksi. RIH RPP. Swab dan BHP Job. POOH RPP | 0 |  | 0 |  | 148 | 6.1667 | 19.4583 | 3648.472 | 148 | 6.1667 | 19.4583 | 5577.7 | [8 empty] | 0 | 0 | 18.6875 | 0 | 0 | 18.7083 | 0 | 0 | 0 | 0
RIH RPP. Put well on production | 0 |  | 0 |  | 54 | 2.25 | 21.7083 | 3648.472 | 54 | 2.25 | 21.7083 | 5577.7 | [8 empty] | 0 | 0 | 18.6875 | 0 | 0 | 18.7083 | 0 | 0 | 0 | 0
| 0 |  | 0 |  | 0 |  | 21.7083 |  | 0 |  | 21.7083 | [9 empty] | 0 | 4.1 | 22.7875 | 0 | 4.1 | 22.8083 | 0 | 0 | 0 | 0
| 0 |  | 0 |  | 0 |  | 21.7083 |  | 0 |  | 21.7083 | [9 empty] | 0 | 2.1 | 24.8875 | 0 | 2.1 | 24.9083 | 0 | 0 | 0 | 0
| 0 |  | 0 |  | 0 |  | 21.7083 |  | 0 |  | 21.7083 | [8 empty] | Coring |  | 0 | 24.8875 | 0 | 0 | 24.9083 | 0 | 0 | 0 | 0
| 0 |  | 0 |  | 98.4 | 4.1 | 25.8083 |  | 98.4 | 4.1 | 25.8083 | [8 empty] | Test |  | 0 | 24.8875 | 0 | 0 | 24.9083 | 0 | 0 | 0 | 0
| 0 |  | 0 |  | 50.4 | 2.1 | 27.9083 |  | 50.4 | 2.1 | 27.9083 | [8 empty] | Completion |  | 0 | 24.8875 | 0 | 0 | 24.9083 | 0 | 0 | 0 | 0
[5 empty] | 0 |  | 27.9083 |  | 0 |  | 27.9083 | [8 empty] | P & A |  | 0 | 24.8875 | 0 | 0 | 24.9083 | 0 | 0 | 0 | 0
[5 empty] | 0 |  | 27.9083 |  | 0 |  | 27.9083 | [8 empty] | Rig Down |  | 0 | 24.8875 | 0 | 0 | 24.9083 | 0 | 0 | 0 | 0
[5 empty] | 0 |  | 27.9083 |  | 0 |  | 27.9083
Coring | 0 |  |  |  | 0 |  | 27.9083 |  | 0 |  | 27.9083
RIH Scrapper to Liner depth interval, RIH and perform production casing cementing job |  |  | 0 |  | 0 |  | 27.9083 |  | 0 |  | 27.9083
RIH Casing Scrapper to perforated zone interval. Cased Hole Logging |  |  | 0 |  | 0 |  | 27.9083 | 0 | 0 |  | 27.9083 | 0
|  |  |  | 0 | 0 |  | 27.9083 |  | 0 |  | 27.9083
|  |  |  | 0 | 0 |  | 27.9083 |  | 0 |  | 27.9083
|  |  |  | 0 | 0 |  | 27.9083 |  | 0 |  | 27.9083
Test | 0 |  |  |  | 0 |  | 27.9083 |  | 0 |  | 27.9083
DST |  |  | 0 |  | 0 |  | 27.9083 | 0 | 0 |  | 27.9083 | 0
|  |  | 0 | 0 | 0 |  | 27.9083 |  | 0 |  | 27.9083
|  |  | 0 | 0 | 0 |  | 27.9083 |  | 0 |  | 27.9083
Completion | 0 |  |  |  | 0 |  | 27.9083 |  | 0 |  | 27.9083
Trip, RIH & cement casing, BOP Job, RIH bit, Run Scrapper, CHL, Perforation 1st target, N/D BOP & N/U X-Masstree. Production Test | 0 |  | 0 |  | 0 |  | 27.9083 |  | 0 |  | 27.9083
Kill well, BOP Job, POOH RPP, Squeeze Job, DOC, Run scrapper, Perforation 2nd target, RIH RPP, Production test | 0 |  | 0 |  | 0 |  | 27.9083 |  | 0 |  | 27.9083
Kill well, BOP Job, POOH RPP, Fracturing Job, RIH RPP, N/D BOP & N/U X-Masstree. Production Test | 0 |  | 0 |  | 0 |  | 27.9083 |  | 0 |  | 27.9083
P & A | 0 |  |  |  | 0 |  | 27.9083 |  | 0 |  | 27.9083
P&A cmt job. L/D string. N/D BOP. N/U THS & Cap Assy |  |  | 0 |  | 0 |  | 27.9083 | 0 | 0 |  | 27.9083 | 0
|  |  |  | 0 | 0 |  | 27.9083 |  | 0 |  | 27.9083
|  |  |  | 0 | 0 |  | 27.9083 |  | 0 |  | 27.9083
|  |  |  | 0 | 0 |  | 27.9083 |  | 0 |  | 27.9083
0
Rig Down | 0
Rig Down |  | 0 | 0 |  | 24 | 1 | 22.7083 |  | 24 | 1 | 22.7083 |  |  | 0 | 0 | 0
|  | 0 |  | 0 |  | 0 | 22.7083 |  |  | 0 | 22.7083 |  |  | 0 | 0 | 0
|  | 0 |  | 0 |  | 0 | 22.7083 |  |  | 0 | 22.7083 |  |  | 0 | 0 | 0
|  | 0 |  | 0 |  | 0 | 22.7083 |  |  | 0 | 22.7083 |  |  | 0 | 0 | 0
|  | 0 |  | 0 |  | 0 | 22.7083 |  |  | 0 | 22.7083 |  |  | 0 | 0 | 0
Total days |  |  | 0 |  | 0 | 0 | 22.7083 |  |  | 0 | 22.7083 |  |  | 0 | 0
DRILLING SCHEDULE DETAILS 3. Sumur Pendopo Tipe 2 | Historical |  |  |  | Proposed Original |  |  |  | Evaluated |  |  |  | ACTUAL |  |  |  | REMARKS | MOM DATE | PERIHAL
Operation Details | HOUR | DAY | CUMMULATIVE | Depth (ft) | HOUR | DAY | CUMMULATIVE | Depth (ft) | HOUR | DAY | CUMMULATIVE | Depth (ft) | HOUR | DAY | CUMMULATIVE | Depth (ft)
Moving |  |  | 0 | [16 empty] | Activities |  | Proposed Original |  |  | Evaluated |  |  | ACTUAL
Tow Rig to well | 0 |  | 0 |  | 24 | 1 | 1 |  | 24 | 1 | 1 | [10 empty] | Day | Cum Days | Depth (Ft) | Day | Cum Days | Depth (Ft) | Day | Cum Days | Depth (Ft)
[20 empty] | Moving Tow Rig to well, |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Rig Up | 0 | [18 empty] | Rig-up, termasuk R/U Top Drive dan stand-up DP & DC. |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Rig-up |  |  | 0 |  | 48 | 2 | 3 |  | 48 | 2 | 3 | [8 empty] | Workover | Preparation (Kill well & POOH existing string) | 1 | 1 | 3648.472 | 1.0208 | 1.0208 | 5577.7 | 0 | 0 | 0
[21 empty] | Squeeze lapisan Eksisting. Run Scraper. Run GR-CBL-CNL | 3.8333 | 4.8333 | 3648.472 | 3.8333 | 4.8542 | 5577.7 | 0 | 0 | 0
Workover | 0 | [19 empty] | Perbaikan bonding. DOC. Run Scraper. Re run GR-CBL-VDL | 5.4375 | 10.2708 | 3648.472 | 5.4375 | 10.2917 | 5577.7 | 0 | 0 | 0
Preparation (Kill well & POOH existing string) | 0 |  | 0 |  | 24.5 | 1.0208 | 4.0208 | 3648.472 | 24.5 | 1.0208 | 4.0208 | 5577.7 | [8 empty] | Perforasi Produksi. RIH RPP. Swab dan BHP Job. POOH RPP | 6.1667 | 16.4375 | 3648.472 | 6.1667 | 16.4583 | 5577.7 | 0 | 0 | 0
Squeeze lapisan Eksisting. Run Scraper. Run GR-CBL-CNL | 0 |  | 0 |  | 92 | 3.8333 | 7.8542 | 3648.472 | 92 | 3.8333 | 7.8542 | 5577.7 | [8 empty] | RIH RPP. Put well on production | 2.25 | 18.6875 | 3648.472 | 2.25 | 18.7083 | 5577.7 | 0 | 0 | 0
Perbaikan bonding. DOC. Run Scraper. Re run GR-CBL-VDL | 0 |  | 0 |  | 130.5 | 5.4375 | 13.2917 | 3648.472 | 130.5 | 5.4375 | 13.2917 | 5577.7 | [8 empty] | 0 | 0 | 18.6875 | 0 | 0 | 18.7083 | 0 | 0 | 0 | 0
Perforasi Produksi. RIH RPP. Swab dan BHP Job. POOH RPP | 0 |  | 0 |  | 148 | 6.1667 | 19.4583 | 3648.472 | 148 | 6.1667 | 19.4583 | 5577.7 | [8 empty] | 0 | 0 | 18.6875 | 0 | 0 | 18.7083 | 0 | 0 | 0 | 0
RIH RPP. Put well on production | 0 |  | 0 |  | 54 | 2.25 | 21.7083 | 3648.472 | 54 | 2.25 | 21.7083 | 5577.7 | [8 empty] | 0 | 0 | 18.6875 | 0 | 0 | 18.7083 | 0 | 0 | 0 | 0
| 0 |  | 0 |  | 0 |  | 21.7083 |  | 0 |  | 21.7083 | [9 empty] | 0 | 4.1 | 22.7875 | 0 | 4.1 | 22.8083 | 0 | 0 | 0 | 0
| 0 |  | 0 |  | 0 |  | 21.7083 |  | 0 |  | 21.7083 | [9 empty] | 0 | 2.1 | 24.8875 | 0 | 2.1 | 24.9083 | 0 | 0 | 0 | 0
| 0 |  | 0 |  | 0 |  | 21.7083 |  | 0 |  | 21.7083 | [8 empty] | Coring |  | 0 | 24.8875 | 0 | 0 | 24.9083 | 0 | 0 | 0 | 0
| 0 |  | 0 |  | 98.4 | 4.1 | 25.8083 |  | 98.4 | 4.1 | 25.8083 | [8 empty] | Test |  | 0 | 24.8875 | 0 | 0 | 24.9083 | 0 | 0 | 0 | 0
| 0 |  | 0 |  | 50.4 | 2.1 | 27.9083 |  | 50.4 | 2.1 | 27.9083 | [8 empty] | Completion |  | 0 | 24.8875 | 0 | 0 | 24.9083 | 0 | 0 | 0 | 0
[5 empty] | 0 |  | 27.9083 |  | 0 |  | 27.9083 | [8 empty] | P & A |  | 0 | 24.8875 | 0 | 0 | 24.9083 | 0 | 0 | 0 | 0
[5 empty] | 0 |  | 27.9083 |  | 0 |  | 27.9083 | [8 empty] | Rig Down |  | 0 | 24.8875 | 0 | 0 | 24.9083 | 0 | 0 | 0 | 0
[5 empty] | 0 |  | 27.9083 |  | 0 |  | 27.9083
Coring | 0 |  |  |  | 0 |  | 27.9083 |  | 0 |  | 27.9083
RIH Scrapper to Liner depth interval, RIH and perform production casing cementing job |  |  | 0 |  | 0 |  | 27.9083 |  | 0 |  | 27.9083
RIH Casing Scrapper to perforated zone interval. Cased Hole Logging |  |  | 0 |  | 0 |  | 27.9083 | 0 | 0 |  | 27.9083 | 0
|  |  |  | 0 | 0 |  | 27.9083 |  | 0 |  | 27.9083
|  |  |  | 0 | 0 |  | 27.9083 |  | 0 |  | 27.9083
|  |  |  | 0 | 0 |  | 27.9083 |  | 0 |  | 27.9083
Test | 0 |  |  |  | 0 |  | 27.9083 |  | 0 |  | 27.9083
DST |  |  | 0 |  | 0 |  | 27.9083 | 0 | 0 |  | 27.9083 | 0
|  |  | 0 | 0 | 0 |  | 27.9083 |  | 0 |  | 27.9083
|  |  | 0 | 0 | 0 |  | 27.9083 |  | 0 |  | 27.9083
Completion | 0 |  |  |  | 0 |  | 27.9083 |  | 0 |  | 27.9083
Trip, RIH & cement casing, BOP Job, RIH bit, Run Scrapper, CHL, Perforation 1st target, N/D BOP & N/U X-Masstree. Production Test | 0 |  | 0 |  | 0 |  | 27.9083 |  | 0 |  | 27.9083
Kill well, BOP Job, POOH RPP, Squeeze Job, DOC, Run scrapper, Perforation 2nd target, RIH RPP, Production test | 0 |  | 0 |  | 0 |  | 27.9083 |  | 0 |  | 27.9083
Kill well, BOP Job, POOH RPP, Fracturing Job, RIH RPP, N/D BOP & N/U X-Masstree. Production Test | 0 |  | 0 |  | 0 |  | 27.9083 |  | 0 |  | 27.9083
P & A | 0 |  |  |  | 0 |  | 27.9083 |  | 0 |  | 27.9083
P&A cmt job. L/D string. N/D BOP. N/U THS & Cap Assy |  |  | 0 |  | 0 |  | 27.9083 | 0 | 0 |  | 27.9083 | 0
|  |  |  | 0 | 0 |  | 27.9083 |  | 0 |  | 27.9083
|  |  |  | 0 | 0 |  | 27.9083 |  | 0 |  | 27.9083
|  |  |  | 0 | 0 |  | 27.9083 |  | 0 |  | 27.9083
0
Rig Down | 0
Rig Down |  | 0 | 0 |  | 24 | 1 | 22.7083 |  | 24 | 1 | 22.7083 |  |  | 0 | 0 | 0
|  | 0 |  | 0 |  | 0 | 22.7083 |  |  | 0 | 22.7083 |  |  | 0 | 0 | 0
|  | 0 |  | 0 |  | 0 | 22.7083 |  |  | 0 | 22.7083 |  |  | 0 | 0 | 0
|  | 0 |  | 0 |  | 0 | 22.7083 |  |  | 0 | 22.7083 |  |  | 0 | 0 | 0
|  | 0 |  | 0 |  | 0 | 22.7083 |  |  | 0 | 22.7083 |  |  | 0 | 0 | 0
Total days |  |  | 0 |  | 0 | 0 | 22.7083 |  |  | 0 | 22.7083 |  |  | 0 | 0
DRILLING SCHEDULE DETAILS 4. Sumur Pendopo Tipe 2 | Historical |  |  |  | Proposed Original |  |  |  | Evaluated |  |  |  | ACTUAL |  |  |  | REMARKS | MOM DATE | PERIHAL
Operation Details | HOUR | DAY | CUMMULATIVE | Depth (ft) | HOUR | DAY | CUMMULATIVE | Depth (ft) | HOUR | DAY | CUMMULATIVE | Depth (ft) | HOUR | DAY | CUMMULATIVE | Depth (ft)
Moving |  |  | 0 | [12 empty] | 0 |  |  |  | Activities |  | Proposed Original |  |  | Evaluated |  |  | ACTUAL
Tow Rig to well | 0 |  | 0 |  | 24 | 1 | 1 |  | 24 | 1 | 1 |  |  |  |  | 0 | [5 empty] | Day | Cum Days | Depth (Ft) | Day | Cum Days | Depth (Ft) | Day | Cum Days | Depth (Ft)
[16 empty] | 0 |  |  |  | Moving Tow Rig to well, |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Rig Up | 0 | [14 empty] | 0 |  |  |  | Rig-up, termasuk R/U Top Drive dan stand-up DP & DC. |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Rig-up |  |  | 0 |  | 48 | 2 | 3 |  | 48 | 2 | 3 |  |  |  |  | 0 |  |  |  | Workover | Preparation (Kill well & POOH existing string) | 1 | 1 | 3648.472 | 1.0208 | 1.0208 | 5577.7 | 0 | 0 | 5577.7
[16 empty] | 0 |  |  |  |  | Squeeze lapisan Eksisting. Run Scraper. Run GR-CBL-CNL | 3.8333 | 4.8333 | 3648.472 | 3.8333 | 4.8542 | 5577.7 | 0 | 0 | 5577.7
Workover | 0 | [14 empty] | 0 |  |  |  |  | Perbaikan bonding. DOC. Run Scraper. Re run GR-CBL-VDL | 5.4375 | 10.2708 | 3648.472 | 5.4375 | 10.2917 | 5577.7 | 0 | 0 | 5577.7
Preparation (Kill well & POOH existing string) | 0 |  | 0 |  | 24.5 | 1.0208 | 4.0208 | 3648.472 | 24.5 | 1.0208 | 4.0208 | 5577.7 |  |  |  | 5577.7 |  |  |  |  | Perforasi Produksi. RIH RPP. Swab dan BHP Job. POOH RPP | 6.1667 | 16.4375 | 3648.472 | 6.1667 | 16.4583 | 5577.7 | 0 | 0 | 5577.7
Squeeze lapisan Eksisting. Run Scraper. Run GR-CBL-CNL | 0 |  | 0 |  | 92 | 3.8333 | 7.8542 | 3648.472 | 92 | 3.8333 | 7.8542 | 5577.7 |  |  |  | 5577.7 |  |  |  |  | RIH RPP. Put well on production | 2.25 | 18.6875 | 3648.472 | 2.25 | 18.7083 | 5577.7 | 0 | 0 | 5577.7
Perbaikan bonding. DOC. Run Scraper. Re run GR-CBL-VDL | 0 |  | 0 |  | 130.5 | 5.4375 | 13.2917 | 3648.472 | 130.5 | 5.4375 | 13.2917 | 5577.7 |  |  |  | 5577.7 |  |  |  |  | 0 | 0 | 18.6875 | 0 | 0 | 18.7083 | 0 | 0 | 0 | 0
Perforasi Produksi. RIH RPP. Swab dan BHP Job. POOH RPP | 0 |  | 0 |  | 148 | 6.1667 | 19.4583 | 3648.472 | 148 | 6.1667 | 19.4583 | 5577.7 |  |  |  | 5577.7 |  |  |  |  | 0 | 0 | 18.6875 | 0 | 0 | 18.7083 | 0 | 0 | 0 | 0
RIH RPP. Put well on production | 0 |  | 0 |  | 54 | 2.25 | 21.7083 | 3648.472 | 54 | 2.25 | 21.7083 | 5577.7 |  |  |  | 5577.7 |  |  |  |  | 0 | 0 | 18.6875 | 0 | 0 | 18.7083 | 0 | 0 | 0 | 0
| 0 |  | 0 |  | 0 |  | 21.7083 |  | 0 |  | 21.7083 |  |  |  |  | 0 |  |  |  |  | 0 | 4.1 | 22.7875 | 0 | 4.1 | 22.8083 | 0 | 0 | 0 | 0
| 0 |  | 0 |  | 0 |  | 21.7083 |  | 0 |  | 21.7083 |  |  |  |  | 0 |  |  |  |  | 0 | 2.1 | 24.8875 | 0 | 2.1 | 24.9083 | 0 | 0 | 0 | 0
| 0 |  | 0 |  | 0 |  | 21.7083 |  | 0 |  | 21.7083 |  |  |  |  | 0 |  |  |  | Coring |  | 0 | 24.8875 | 0 | 0 | 24.9083 | 0 | 0 | 0 | 0
| 0 |  | 0 |  | 98.4 | 4.1 | 25.8083 |  | 98.4 | 4.1 | 25.8083 |  |  |  |  | 0 |  |  |  | Test |  | 0 | 24.8875 | 0 | 0 | 24.9083 | 0 | 0 | 0 | 0
| 0 |  | 0 |  | 50.4 | 2.1 | 27.9083 |  | 50.4 | 2.1 | 27.9083 |  |  |  |  | 0 |  |  |  | Completion |  | 0 | 24.8875 | 0 | 0 | 24.9083 | 0 | 0 | 0 | 0
[5 empty] | 0 |  | 27.9083 |  | 0 |  | 27.9083 |  |  |  |  | 0 |  |  |  | P & A |  | 0 | 24.8875 | 0 | 0 | 24.9083 | 0 | 0 | 0 | 0
[5 empty] | 0 |  | 27.9083 |  | 0 |  | 27.9083 |  |  |  |  | 0 |  |  |  | Rig Down |  | 0 | 24.8875 | 0 | 0 | 24.9083 | 0 | 0 | 0 | 0
[5 empty] | 0 |  | 27.9083 |  | 0 |  | 27.9083 |  |  |  |  | 0
Coring | 0 |  |  |  | 0 |  | 27.9083 |  | 0 |  | 27.9083 |  |  |  |  | 0
RIH Scrapper to Liner depth interval, RIH and perform production casing cementing job |  |  | 0 |  | 0 |  | 27.9083 |  | 0 |  | 27.9083 |  |  |  |  | 0
RIH Casing Scrapper to perforated zone interval. Cased Hole Logging |  |  | 0 |  | 0 |  | 27.9083 | 0 | 0 |  | 27.9083 | 0 |  |  |  | 0
|  |  |  | 0 | 0 |  | 27.9083 |  | 0 |  | 27.9083 |  |  |  |  | 0
|  |  |  | 0 | 0 |  | 27.9083 |  | 0 |  | 27.9083 |  |  |  |  | 0
|  |  |  | 0 | 0 |  | 27.9083 |  | 0 |  | 27.9083 |  |  |  |  | 0
Test | 0 |  |  |  | 0 |  | 27.9083 |  | 0 |  | 27.9083 |  |  |  |  | 0
DST |  |  | 0 |  | 0 |  | 27.9083 | 0 | 0 |  | 27.9083 | 0 |  |  |  | 0
|  |  | 0 | 0 | 0 |  | 27.9083 |  | 0 |  | 27.9083 |  |  |  |  | 0
|  |  | 0 | 0 | 0 |  | 27.9083 |  | 0 |  | 27.9083 |  |  |  |  | 0
Completion | 0 |  |  |  | 0 |  | 27.9083 |  | 0 |  | 27.9083 |  |  |  |  | 0
Trip, RIH & cement casing, BOP Job, RIH bit, Run Scrapper, CHL, Perforation 1st target, N/D BOP & N/U X-Masstree. Production Test | 0 |  | 0 |  | 0 |  | 27.9083 |  | 0 |  | 27.9083 |  |  |  |  | 0
Kill well, BOP Job, POOH RPP, Squeeze Job, DOC, Run scrapper, Perforation 2nd target, RIH RPP, Production test | 0 |  | 0 |  | 0 |  | 27.9083 |  | 0 |  | 27.9083 |  |  |  |  | 0
Kill well, BOP Job, POOH RPP, Fracturing Job, RIH RPP, N/D BOP & N/U X-Masstree. Production Test | 0 |  | 0 |  | 0 |  | 27.9083 |  | 0 |  | 27.9083 |  |  |  |  | 0
P & A | 0 |  |  |  | 0 |  | 27.9083 |  | 0 |  | 27.9083 |  |  |  |  | 0
P&A cmt job. L/D string. N/D BOP. N/U THS & Cap Assy |  |  | 0 |  | 0 |  | 27.9083 | 0 | 0 |  | 27.9083 | 0 |  |  |  | 0
|  |  |  | 0 | 0 |  | 27.9083 |  | 0 |  | 27.9083 |  |  |  |  | 0
|  |  |  | 0 | 0 |  | 27.9083 |  | 0 |  | 27.9083 |  |  |  |  | 0
|  |  |  | 0 | 0 |  | 27.9083 |  | 0 |  | 27.9083 |  |  |  |  | 0
|  |  |  | 0 | [11 empty] | 0
Rig Down | 0 | [14 empty] | 0
Rig Down |  | 0 | 0 |  | 24 | 1 | 22.7083 |  | 24 | 1 | 22.7083 |  |  | 0 | 0 | 0
|  | 0 |  | 0 |  | 0 | 22.7083 |  |  | 0 | 22.7083 |  |  | 0 | 0 | 0
|  | 0 |  | 0 |  | 0 | 22.7083 |  |  | 0 | 22.7083 |  |  | 0 | 0 | 0
|  | 0 |  | 0 |  | 0 | 22.7083 |  |  | 0 | 22.7083 |  |  | 0 | 0 | 0
|  | 0 |  | 0 |  | 0 | 22.7083 |  |  | 0 | 22.7083 |  |  | 0 | 0 | 0
Total days |  |  | 0 |  | 0 | 0 | 22.7083 |  |  | 0 | 22.7083 |  |  | 0 | 0
DRILLING SCHEDULE DETAILS 5. Sumur Pendopo Tipe 4 | Historical |  |  |  | Proposed Original |  |  |  | Evaluated |  |  |  | ACTUAL |  |  |  | REMARKS | MOM DATE | PERIHAL
Operation Details | HOUR | DAY | CUMMULATIVE | Depth (ft) | HOUR | DAY | CUMMULATIVE | Depth (ft) | HOUR | DAY | CUMMULATIVE | Depth (ft) | HOUR | DAY | CUMMULATIVE | Depth (ft)
Moving |  |  | 0 | [12 empty] | 0 |  |  |  | Activities |  | Proposed Original |  |  | Evaluated |  |  | ACTUAL
Tow Rig to well | 0 |  | 0 |  | 24 | 1 | 1 |  | 24 | 1 | 1 |  |  |  |  | 0 | [5 empty] | Day | Cum Days | Depth (Ft) | Day | Cum Days | Depth (Ft) | Day | Cum Days | Depth (Ft)
[16 empty] | 0 |  |  |  | Moving Tow Rig to well, |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Rig Up | 0 | [14 empty] | 0 |  |  |  | Rig-up, termasuk R/U Top Drive dan stand-up DP & DC. |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Rig-up |  |  | 0 |  | 48 | 2 | 3 |  | 48 | 2 | 3 |  |  |  |  | 0 |  |  |  | Workover | Preparation (Kill well & POOH existing string) | 1 | 1 | 2181.865 | 1.1042 | 1.1042 | 2181.865 | 0 | 0 | 2181.865
[16 empty] | 0 |  |  |  |  | Squeeze lapisan Eksisting. Run Scraper. Run GR-CBL-CNL | 4.0417 | 5.0417 | 2181.865 | 4.0417 | 5.1458 | 2181.865 | 0 | 0 | 2181.865
Workover | 0 | [14 empty] | 0 |  |  |  |  | Perbaikan bonding. DOC. Run Scraper. Re run GR-CBL-VDL | 5.6042 | 10.6458 | 2181.865 | 5.6042 | 10.75 | 2181.865 | 0 | 0 | 2181.865
Preparation (Kill well & POOH existing string) | 0 |  | 0 |  | 26.5 | 1.1042 | 4.1042 | 2181.865 | 26.5 | 1.1042 | 4.1042 | 2181.865 |  |  |  | 2181.865 |  |  |  |  | Perforasi Produksi. RIH RPP. Swab dan BHP Job. POOH RPP | 8.25 | 18.8958 | 2181.865 | 8.25 | 19 | 2181.865 | 0 | 0 | 2181.865
Squeeze lapisan Eksisting. Run Scraper. Run GR-CBL-CNL | 0 |  | 0 |  | 97 | 4.0417 | 8.1458 | 2181.865 | 97 | 4.0417 | 8.1458 | 2181.865 |  |  |  | 2181.865 |  |  |  |  | RIH RPP. Put well on production | 2.25 | 21.1458 | 2181.865 | 2.25 | 21.25 | 2181.865 | 0 | 0 | 2181.865
Perbaikan bonding. DOC. Run Scraper. Re run GR-CBL-VDL | 0 |  | 0 |  | 134.5 | 5.6042 | 13.75 | 2181.865 | 134.5 | 5.6042 | 13.75 | 2181.865 |  |  |  | 2181.865 |  |  |  |  | 0 | 0 | 21.1458 | 0 | 0 | 21.25 | 0 | 0 | 0 | 0
Perforasi Produksi. RIH RPP. Swab dan BHP Job. POOH RPP | 0 |  | 0 |  | 198 | 8.25 | 22 | 2181.865 | 198 | 8.25 | 22 | 2181.865 |  |  |  | 2181.865 |  |  |  |  | 0 | 0 | 21.1458 | 0 | 0 | 21.25 | 0 | 0 | 0 | 0
RIH RPP. Put well on production | 0 |  | 0 |  | 54 | 2.25 | 24.25 | 2181.865 | 54 | 2.25 | 24.25 | 2181.865 |  |  |  | 2181.865 |  |  |  |  | 0 | 0 | 21.1458 | 0 | 0 | 21.25 | 0 | 0 | 0 | 0
| 0 |  | 0 |  | 0 |  | 24.25 |  | 0 |  | 24.25 |  |  |  |  | 0 |  |  |  |  | 0 | 4.1 | 25.2458 | 0 | 4.1 | 25.35 | 0 | 0 | 0 | 0
| 0 |  | 0 |  | 0 |  | 24.25 |  | 0 |  | 24.25 |  |  |  |  | 0 |  |  |  |  | 0 | 2.1 | 27.3458 | 0 | 2.1 | 27.45 | 0 | 0 | 0 | 0
| 0 |  | 0 |  | 0 |  | 24.25 |  | 0 |  | 24.25 |  |  |  |  | 0 |  |  |  | Coring |  | 0 | 27.3458 | 0 | 0 | 27.45 | 0 | 0 | 0 | 0
| 0 |  | 0 |  | 98.4 | 4.1 | 28.35 |  | 98.4 | 4.1 | 28.35 |  |  |  |  | 0 |  |  |  | Test |  | 0 | 27.3458 | 0 | 0 | 27.45 | 0 | 0 | 0 | 0
| 0 |  | 0 |  | 50.4 | 2.1 | 30.45 |  | 50.4 | 2.1 | 30.45 |  |  |  |  | 0 |  |  |  | Completion |  | 0 | 27.3458 | 0 | 0 | 27.45 | 0 | 0 | 0 | 0
[5 empty] | 0 |  | 30.45 |  | 0 |  | 30.45 |  |  |  |  | 0 |  |  |  | P & A |  | 0 | 27.3458 | 0 | 0 | 27.45 | 0 | 0 | 0 | 0
[5 empty] | 0 |  | 30.45 |  | 0 |  | 30.45 |  |  |  |  | 0 |  |  |  | Rig Down |  | 0 | 27.3458 | 0 | 0 | 27.45 | 0 | 0 | 0 | 0
[5 empty] | 0 |  | 30.45 |  | 0 |  | 30.45 |  |  |  |  | 0
Coring | 0 |  |  |  | 0 |  | 30.45 |  | 0 |  | 30.45 |  |  |  |  | 0
RIH Scrapper to Liner depth interval, RIH and perform production casing cementing job |  |  | 0 |  | 0 |  | 30.45 |  | 0 |  | 30.45 |  |  |  |  | 0
RIH Casing Scrapper to perforated zone interval. Cased Hole Logging |  |  | 0 |  | 0 |  | 30.45 | 0 | 0 |  | 30.45 | 0 |  |  |  | 0
|  |  |  | 0 | 0 |  | 30.45 |  | 0 |  | 30.45 |  |  |  |  | 0
|  |  |  | 0 | 0 |  | 30.45 |  | 0 |  | 30.45 |  |  |  |  | 0
|  |  |  | 0 | 0 |  | 30.45 |  | 0 |  | 30.45 |  |  |  |  | 0
Test | 0 |  |  |  | 0 |  | 30.45 |  | 0 |  | 30.45 |  |  |  |  | 0
DST |  |  | 0 |  | 0 |  | 30.45 | 0 | 0 |  | 30.45 | 0 |  |  |  | 0
|  |  | 0 | 0 | 0 |  | 30.45 |  | 0 |  | 30.45 |  |  |  |  | 0
|  |  | 0 | 0 | 0 |  | 30.45 |  | 0 |  | 30.45 |  |  |  |  | 0
Completion | 0 |  |  |  | 0 |  | 30.45 |  | 0 |  | 30.45 |  |  |  |  | 0
Trip, RIH & cement casing, BOP Job, RIH bit, Run Scrapper, CHL, Perforation 1st target, N/D BOP & N/U X-Masstree. Production Test | 0 |  | 0 |  | 0 |  | 30.45 |  | 0 |  | 30.45 |  |  |  |  | 0
Kill well, BOP Job, POOH RPP, Squeeze Job, DOC, Run scrapper, Perforation 2nd target, RIH RPP, Production test | 0 |  | 0 |  | 0 |  | 30.45 |  | 0 |  | 30.45 |  |  |  |  | 0
Kill well, BOP Job, POOH RPP, Fracturing Job, RIH RPP, N/D BOP & N/U X-Masstree. Production Test | 0 |  | 0 |  | 0 |  | 30.45 |  | 0 |  | 30.45 |  |  |  |  | 0
P & A | 0 |  |  |  | 0 |  | 30.45 |  | 0 |  | 30.45 |  |  |  |  | 0
P&A cmt job. L/D string. N/D BOP. N/U THS & Cap Assy |  |  | 0 |  | 0 |  | 30.45 | 0 | 0 |  | 30.45 | 0 |  |  |  | 0
|  |  |  | 0 | 0 |  | 30.45 |  | 0 |  | 30.45 |  |  |  |  | 0
|  |  |  | 0 | 0 |  | 30.45 |  | 0 |  | 30.45 |  |  |  |  | 0
|  |  |  | 0 | 0 |  | 30.45 |  | 0 |  | 30.45 |  |  |  |  | 0
|  |  |  | 0 | [11 empty] | 0
Rig Down | 0 | [14 empty] | 0
Rig Down |  | 0 | 0 |  | 24 | 1 | 25.25 |  | 24 | 1 | 25.25 |  |  | 0 | 0 | 0
|  | 0 |  | 0 |  | 0 | 25.25 |  |  | 0 | 25.25 |  |  | 0 | 0 | 0
|  | 0 |  | 0 |  | 0 | 25.25 |  |  | 0 | 25.25 |  |  | 0 | 0 | 0
|  | 0 |  | 0 |  | 0 | 25.25 |  |  | 0 | 25.25 |  |  | 0 | 0 | 0
|  | 0 |  | 0 |  | 0 | 25.25 |  |  | 0 | 25.25 |  |  | 0 | 0 | 0
Total days |  |  | 0 |  | 0 | 0 | 25.25 |  |  | 0 | 25.25 |  |  | 0 | 0
DRILLING SCHEDULE DETAILS 6. Sumur Pendopo Tipe 4 | Historical |  |  |  | Proposed Original |  |  |  | Evaluated |  |  |  | ACTUAL |  |  |  | REMARKS | MOM DATE | PERIHAL
Operation Details | HOUR | DAY | CUMMULATIVE | Depth (ft) | HOUR | DAY | CUMMULATIVE | Depth (ft) | HOUR | DAY | CUMMULATIVE | Depth (ft) | HOUR | DAY | CUMMULATIVE | Depth (ft)
Moving |  |  | 0 | [12 empty] | 0 |  |  |  | Activities |  | Proposed Original |  |  | Evaluated |  |  | ACTUAL
Tow Rig to well | 0 |  | 0 |  | 24 | 1 | 1 |  | 24 | 1 | 1 |  |  |  |  | 0 | [5 empty] | Day | Cum Days | Depth (Ft) | Day | Cum Days | Depth (Ft) | Day | Cum Days | Depth (Ft)
[16 empty] | 0 |  |  |  | Moving Tow Rig to well, |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Rig Up | 0 | [14 empty] | 0 |  |  |  | Rig-up, termasuk R/U Top Drive dan stand-up DP & DC. |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Rig-up |  |  | 0 |  | 48 | 2 | 3 |  | 48 | 2 | 3 |  |  |  |  | 0 |  |  |  | Workover | Preparation (Kill well & POOH existing string) | 1 | 1 | 2181.865 | 1.1042 | 1.1042 | 2181.865 | 0 | 0 | 2181.865
[16 empty] | 0 |  |  |  |  | Squeeze lapisan Eksisting. Run Scraper. Run GR-CBL-CNL | 4.0417 | 5.0417 | 2181.865 | 4.0417 | 5.1458 | 2181.865 | 0 | 0 | 2181.865
Workover | 0 | [14 empty] | 0 |  |  |  |  | Perbaikan bonding. DOC. Run Scraper. Re run GR-CBL-VDL | 5.6042 | 10.6458 | 2181.865 | 5.6042 | 10.75 | 2181.865 | 0 | 0 | 2181.865
Preparation (Kill well & POOH existing string) | 0 |  | 0 |  | 26.5 | 1.1042 | 4.1042 | 2181.865 | 26.5 | 1.1042 | 4.1042 | 2181.865 |  |  |  | 2181.865 |  |  |  |  | Perforasi Produksi. Stimulation Job. POOH RPP | 8.25 | 18.8958 | 2181.865 | 8.25 | 19 | 2181.865 | 0 | 0 | 2181.865
Squeeze lapisan Eksisting. Run Scraper. Run GR-CBL-CNL | 0 |  | 0 |  | 97 | 4.0417 | 8.1458 | 2181.865 | 97 | 4.0417 | 8.1458 | 2181.865 |  |  |  | 2181.865 |  |  |  |  | RIH RPP. Put well on production | 2.25 | 21.1458 | 2181.865 | 2.25 | 21.25 | 2181.865 | 0 | 0 | 2181.865
Perbaikan bonding. DOC. Run Scraper. Re run GR-CBL-VDL | 0 |  | 0 |  | 134.5 | 5.6042 | 13.75 | 2181.865 | 134.5 | 5.6042 | 13.75 | 2181.865 |  |  |  | 2181.865 |  |  |  |  | 0 | 0 | 21.1458 | 0 | 0 | 21.25 | 0 | 0 | 0 | 0
Perforasi Produksi. Stimulation Job. POOH RPP | 0 |  | 0 |  | 198 | 8.25 | 22 | 2181.865 | 198 | 8.25 | 22 | 2181.865 |  |  |  | 2181.865 |  |  |  |  | 0 | 0 | 21.1458 | 0 | 0 | 21.25 | 0 | 0 | 0 | 0
RIH RPP. Put well on production | 0 |  | 0 |  | 54 | 2.25 | 24.25 | 2181.865 | 54 | 2.25 | 24.25 | 2181.865 |  |  |  | 2181.865 |  |  |  |  | 0 | 0 | 21.1458 | 0 | 0 | 21.25 | 0 | 0 | 0 | 0
| 0 |  | 0 |  | 0 |  | 24.25 |  | 0 |  | 24.25 |  |  |  |  | 0 |  |  |  |  | 0 | 4.1 | 25.2458 | 0 | 4.1 | 25.35 | 0 | 0 | 0 | 0
| 0 |  | 0 |  | 0 |  | 24.25 |  | 0 |  | 24.25 |  |  |  |  | 0 |  |  |  |  | 0 | 2.1 | 27.3458 | 0 | 2.1 | 27.45 | 0 | 0 | 0 | 0
| 0 |  | 0 |  | 0 |  | 24.25 |  | 0 |  | 24.25 |  |  |  |  | 0 |  |  |  | Coring |  | 0 | 27.3458 | 0 | 0 | 27.45 | 0 | 0 | 0 | 0
| 0 |  | 0 |  | 98.4 | 4.1 | 28.35 |  | 98.4 | 4.1 | 28.35 |  |  |  |  | 0 |  |  |  | Test |  | 0 | 27.3458 | 0 | 0 | 27.45 | 0 | 0 | 0 | 0
| 0 |  | 0 |  | 50.4 | 2.1 | 30.45 |  | 50.4 | 2.1 | 30.45 |  |  |  |  | 0 |  |  |  | Completion |  | 0 | 27.3458 | 0 | 0 | 27.45 | 0 | 0 | 0 | 0
[5 empty] | 0 |  | 30.45 |  | 0 |  | 30.45 |  |  |  |  | 0 |  |  |  | P & A |  | 0 | 27.3458 | 0 | 0 | 27.45 | 0 | 0 | 0 | 0
[5 empty] | 0 |  | 30.45 |  | 0 |  | 30.45 |  |  |  |  | 0 |  |  |  | Rig Down |  | 0 | 27.3458 | 0 | 0 | 27.45 | 0 | 0 | 0 | 0
[5 empty] | 0 |  | 30.45 |  | 0 |  | 30.45 |  |  |  |  | 0
Coring | 0 |  |  |  | 0 |  | 30.45 |  | 0 |  | 30.45 |  |  |  |  | 0
RIH Scrapper to Liner depth interval, RIH and perform production casing cementing job |  |  | 0 |  | 0 |  | 30.45 |  | 0 |  | 30.45 |  |  |  |  | 0
RIH Casing Scrapper to perforated zone interval. Cased Hole Logging |  |  | 0 |  | 0 |  | 30.45 | 0 | 0 |  | 30.45 | 0 |  |  |  | 0
|  |  |  | 0 | 0 |  | 30.45 |  | 0 |  | 30.45 |  |  |  |  | 0
|  |  |  | 0 | 0 |  | 30.45 |  | 0 |  | 30.45 |  |  |  |  | 0
|  |  |  | 0 | 0 |  | 30.45 |  | 0 |  | 30.45 |  |  |  |  | 0
Test | 0 |  |  |  | 0 |  | 30.45 |  | 0 |  | 30.45 |  |  |  |  | 0
DST |  |  | 0 |  | 0 |  | 30.45 | 0 | 0 |  | 30.45 | 0 |  |  |  | 0
|  |  | 0 | 0 | 0 |  | 30.45 |  | 0 |  | 30.45 |  |  |  |  | 0
|  |  | 0 | 0 | 0 |  | 30.45 |  | 0 |  | 30.45 |  |  |  |  | 0
Completion | 0 |  |  |  | 0 |  | 30.45 |  | 0 |  | 30.45 |  |  |  |  | 0
Trip, RIH & cement casing, BOP Job, RIH bit, Run Scrapper, CHL, Perforation 1st target, N/D BOP & N/U X-Masstree. Production Test | 0 |  | 0 |  | 0 |  | 30.45 |  | 0 |  | 30.45 |  |  |  |  | 0
Kill well, BOP Job, POOH RPP, Squeeze Job, DOC, Run scrapper, Perforation 2nd target, RIH RPP, Production test | 0 |  | 0 |  | 0 |  | 30.45 |  | 0 |  | 30.45 |  |  |  |  | 0
Kill well, BOP Job, POOH RPP, Fracturing Job, RIH RPP, N/D BOP & N/U X-Masstree. Production Test | 0 |  | 0 |  | 0 |  | 30.45 |  | 0 |  | 30.45 |  |  |  |  | 0
P & A | 0 |  |  |  | 0 |  | 30.45 |  | 0 |  | 30.45 |  |  |  |  | 0
P&A cmt job. L/D string. N/D BOP. N/U THS & Cap Assy |  |  | 0 |  | 0 |  | 30.45 | 0 | 0 |  | 30.45 | 0 |  |  |  | 0
|  |  |  | 0 | 0 |  | 30.45 |  | 0 |  | 30.45 |  |  |  |  | 0
|  |  |  | 0 | 0 |  | 30.45 |  | 0 |  | 30.45 |  |  |  |  | 0
|  |  |  | 0 | 0 |  | 30.45 |  | 0 |  | 30.45 |  |  |  |  | 0
|  |  |  | 0 | [11 empty] | 0
Rig Down | 0 | [14 empty] | 0
Rig Down |  | 0 | 0 |  | 24 | 1 | 25.25 |  | 24 | 1 | 25.25 |  |  | 0 | 0 | 0
|  | 0 |  | 0 |  | 0 | 25.25 |  |  | 0 | 25.25 |  |  | 0 | 0 | 0
|  | 0 |  | 0 |  | 0 | 25.25 |  |  | 0 | 25.25 |  |  | 0 | 0 | 0
|  | 0 |  | 0 |  | 0 | 25.25 |  |  | 0 | 25.25 |  |  | 0 | 0 | 0
|  | 0 |  | 0 |  | 0 | 25.25 |  |  | 0 | 25.25 |  |  | 0 | 0 | 0
Total days |  |  | 0 |  | 0 | 0 | 25.25 |  |  | 0 | 25.25 |  |  | 0 | 0
DRILLING SCHEDULE DETAILS | Historical |  |  |  | Proposed Original |  |  |  | Evaluated |  |  |  | ACTUAL |  |  |  | REMARKS | MOM DATE | PERIHAL
Operation Details | HOUR | DAY | CUMMULATIVE | Depth (ft) | HOUR | DAY | CUMMULATIVE | Depth (ft) | HOUR | DAY | CUMMULATIVE | Depth (ft) | HOUR | DAY | CUMMULATIVE | Depth (ft)
Moving |  |  | 0 | [16 empty] | Activities |  | Proposed Original |  |  | Evaluated |  |  | ACTUAL
Tow Rig to well | 0 |  | 0 |  | 0 |  | 1 |  | 0 | 0 | 1 | [10 empty] | Day | Cum Days | Depth (Ft) | Day | Cum Days | Depth (Ft) | Day | Cum Days | Depth (Ft)
[20 empty] | Moving Tow Rig to well, |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Rig Up | 0 | [18 empty] | Rig-up, termasuk R/U Top Drive dan stand-up DP & DC. |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Rig-up |  |  | 0 |  | 0 |  | 1 |  | 0 | 0 | 1 | [8 empty] | Workover | Preparation (Kill well & POOH existing string) | 1 | 1 | 0 | 0 | 0 | 5577.7 | 0 | 0 | 0
[21 empty] | Squeeze lapisan Eksisting. Run Scraper. Run GR-CBL-CNL | 0 | 1 | 0 | 0 | 0 | 5577.7 | 0 | 0 | 0
Workover | 0 | [19 empty] | Perbaikan bonding. DOC. Run Scraper. Re run GR-CBL-VDL | 0 | 1 | 0 | 0 | 0 | 5577.7 | 0 | 0 | 0
Preparation (Kill well & POOH existing string) | 0 |  | 0 |  | 0 |  | 1 | 0 | 0 | 0 | 1 | 5577.7 | [8 empty] | Perforasi Produksi. RIH RPP. Swab dan BHP Job. POOH RPP | 0 | 1 | 0 | 0 | 0 | 5577.7 | 0 | 0 | 0
Squeeze lapisan Eksisting. Run Scraper. Run GR-CBL-CNL | 0 |  | 0 |  | 0 |  | 1 | 0 | 0 | 0 | 1 | 5577.7 | [8 empty] | RIH RPP. Put well on production | 0 | 1 | 0 | 0 | 0 | 5577.7 | 0 | 0 | 0
Perbaikan bonding. DOC. Run Scraper. Re run GR-CBL-VDL | 0 |  | 0 |  | 0 |  | 1 | 0 | 0 | 0 | 1 | 5577.7 | [8 empty] | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Perforasi Produksi. RIH RPP. Swab dan BHP Job. POOH RPP | 0 |  | 0 |  | 0 |  | 1 | 0 | 0 | 0 | 1 | 5577.7 | [8 empty] | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0
RIH RPP. Put well on production | 0 |  | 0 |  | 0 |  | 1 | 0 | 0 | 0 | 1 | 5577.7 | [8 empty] | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| 0 |  | 0 |  | 0 |  | 1 |  | 0 |  | 1 | [9 empty] | 0 | 0 | 1 | 0 | 4.1 | 4.1 | 0 | 0 | 0 | 0
| 0 |  | 0 |  | 0 |  | 1 |  | 0 |  | 1 | [9 empty] | 0 | 0 | 1 | 0 | 2.1 | 6.2 | 0 | 0 | 0 | 0
| 0 |  | 0 |  | 0 |  | 1 |  | 0 |  | 1 | [8 empty] | Coring |  | 0 | 1 | 0 | 0 | 6.2 | 0 | 0 | 0 | 0
| 0 |  | 0 |  | 0 |  | 1 |  | 98.4 | 4.1 | 5.1 | [8 empty] | Test |  | 0 | 1 | 0 | 0 | 6.2 | 0 | 0 | 0 | 0
| 0 |  | 0 |  | 0 |  | 1 |  | 50.4 | 2.1 | 7.2 | [8 empty] | Completion |  | 0 | 1 | 0 | 0 | 6.2 | 0 | 0 | 0 | 0
[5 empty] | 0 |  | 1 |  | 0 |  | 7.2 | [8 empty] | P & A |  | 0 | 1 | 0 | 0 | 6.2 | 0 | 0 | 0 | 0
[5 empty] | 0 |  | 1 |  | 0 |  | 7.2 | [8 empty] | Rig Down |  | 0 | 1 | 0 | 0 | 6.2 | 0 | 0 | 0 | 0
[5 empty] | 0 |  | 1 |  | 0 |  | 7.2
Coring | 0 |  |  |  | 0 |  | 1 |  | 0 |  | 7.2
RIH Scrapper to Liner depth interval, RIH and perform production casing cementing job |  |  | 0 |  | 0 |  | 1 |  | 0 |  | 7.2
RIH Casing Scrapper to perforated zone interval. Cased Hole Logging |  |  | 0 |  | 0 |  | 1 | 0 | 0 |  | 7.2 | 0
|  |  |  | 0 | 0 |  | 1 |  | 0 |  | 7.2
|  |  |  | 0 | 0 |  | 1 |  | 0 |  | 7.2
|  |  |  | 0 | 0 |  | 1 |  | 0 |  | 7.2
Test | 0 |  |  |  | 0 |  | 1 |  | 0 |  | 7.2
DST |  |  | 0 |  | 0 |  | 1 | 0 | 0 |  | 7.2 | 0
|  |  | 0 | 0 | 0 |  | 1 |  | 0 |  | 7.2
|  |  | 0 | 0 | 0 |  | 1 |  | 0 |  | 7.2
Completion | 0 |  |  |  | 0 |  | 1 |  | 0 |  | 7.2
Trip, RIH & cement casing, BOP Job, RIH bit, Run Scrapper, CHL, Perforation 1st target, N/D BOP & N/U X-Masstree. Production Test | 0 |  | 0 |  | 0 |  | 1 |  | 0 |  | 7.2
Kill well, BOP Job, POOH RPP, Squeeze Job, DOC, Run scrapper, Perforation 2nd target, RIH RPP, Production test | 0 |  | 0 |  | 0 |  | 1 |  | 0 |  | 7.2
Kill well, BOP Job, POOH RPP, Fracturing Job, RIH RPP, N/D BOP & N/U X-Masstree. Production Test | 0 |  | 0 |  | 0 |  | 1 |  | 0 |  | 7.2
P & A | 0 |  |  |  | 0 |  | 1 |  | 0 |  | 7.2
P&A cmt job. L/D string. N/D BOP. N/U THS & Cap Assy |  |  | 0 |  | 0 |  | 1 | 0 | 0 |  | 7.2 | 0
|  |  |  | 0 | 0 |  | 1 |  | 0 |  | 7.2
|  |  |  | 0 | 0 |  | 1 |  | 0 |  | 7.2
|  |  |  | 0 | 0 |  | 1 |  | 0 |  | 7.2
0
Rig Down | 0
Rig Down |  | 0 | 0 |  | 0 |  | 1 |  | 0 | 0 | 1 |  |  | 0 | 0 | 0
|  | 0 |  | 0 |  | 0 | 1 |  |  | 0 | 1 |  |  | 0 | 0 | 0
|  | 0 |  | 0 |  | 0 | 1 |  |  | 0 | 1 |  |  | 0 | 0 | 0
|  | 0 |  | 0 |  | 0 | 1 |  |  | 0 | 1 |  |  | 0 | 0 | 0
|  | 0 |  | 0 |  | 0 | 1 |  |  | 0 | 1 |  |  | 0 | 0 | 0
Total days |  |  | 0 |  | 0 | 0 | 1 |  |  | 0 | 1 |  |  | 0 | 0
DRILLING SCHEDULE DETAILS | Historical |  |  |  | Proposed Original |  |  |  | Evaluated |  |  |  | ACTUAL |  |  |  | REMARKS | MOM DATE | PERIHAL
Operation Details | HOUR | DAY | CUMMULATIVE | Depth (ft) | HOUR | DAY | CUMMULATIVE | Depth (ft) | HOUR | DAY | CUMMULATIVE | Depth (ft) | HOUR | DAY | CUMMULATIVE | Depth (ft)
Moving |  |  | 0 | [16 empty] | Activities |  | Proposed Original |  |  | Evaluated |  |  | ACTUAL
Tow Rig to well | 0 |  | 0 |  | 0 |  | 1 |  | 0 | 0 | 1 | [10 empty] | Day | Cum Days | Depth (Ft) | Day | Cum Days | Depth (Ft) | Day | Cum Days | Depth (Ft)
[20 empty] | Moving Tow Rig to well, |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Rig Up | 0 | [18 empty] | Rig-up, termasuk R/U Top Drive dan stand-up DP & DC. |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Rig-up |  |  | 0 |  | 0 |  | 1 |  | 0 | 0 | 1 | [8 empty] | Workover | Preparation (Kill well & POOH existing string) | 1 | 1 | 0 | 0 | 0 | 5577.7 | 0 | 0 | 0
[21 empty] | Squeeze lapisan Eksisting. Run Scraper. Run GR-CBL-CNL | 0 | 1 | 0 | 0 | 0 | 5577.7 | 0 | 0 | 0
Workover | 0 | [19 empty] | Perbaikan bonding. DOC. Run Scraper. Re run GR-CBL-VDL | 0 | 1 | 0 | 0 | 0 | 5577.7 | 0 | 0 | 0
Preparation (Kill well & POOH existing string) | 0 |  | 0 |  | 0 |  | 1 | 0 | 0 | 0 | 1 | 5577.7 | [8 empty] | Perforasi Produksi. RIH RPP. Swab dan BHP Job. POOH RPP | 0 | 1 | 0 | 0 | 0 | 5577.7 | 0 | 0 | 0
Squeeze lapisan Eksisting. Run Scraper. Run GR-CBL-CNL | 0 |  | 0 |  | 0 |  | 1 | 0 | 0 | 0 | 1 | 5577.7 | [8 empty] | RIH RPP. Put well on production | 0 | 1 | 0 | 0 | 0 | 5577.7 | 0 | 0 | 0
Perbaikan bonding. DOC. Run Scraper. Re run GR-CBL-VDL | 0 |  | 0 |  | 0 |  | 1 | 0 | 0 | 0 | 1 | 5577.7 | [8 empty] | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Perforasi Produksi. RIH RPP. Swab dan BHP Job. POOH RPP | 0 |  | 0 |  | 0 |  | 1 | 0 | 0 | 0 | 1 | 5577.7 | [8 empty] | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0
RIH RPP. Put well on production | 0 |  | 0 |  | 0 |  | 1 | 0 | 0 | 0 | 1 | 5577.7 | [8 empty] | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| 0 |  | 0 |  | 0 |  | 1 |  | 0 |  | 1 | [9 empty] | 0 | 0 | 1 | 0 | 4.1 | 4.1 | 0 | 0 | 0 | 0
| 0 |  | 0 |  | 0 |  | 1 |  | 0 |  | 1 | [9 empty] | 0 | 0 | 1 | 0 | 2.1 | 6.2 | 0 | 0 | 0 | 0
| 0 |  | 0 |  | 0 |  | 1 |  | 0 |  | 1 | [8 empty] | Coring |  | 0 | 1 | 0 | 0 | 6.2 | 0 | 0 | 0 | 0
| 0 |  | 0 |  | 0 |  | 1 |  | 98.4 | 4.1 | 5.1 | [8 empty] | Test |  | 0 | 1 | 0 | 0 | 6.2 | 0 | 0 | 0 | 0
| 0 |  | 0 |  | 0 |  | 1 |  | 50.4 | 2.1 | 7.2 | [8 empty] | Completion |  | 0 | 1 | 0 | 0 | 6.2 | 0 | 0 | 0 | 0
[5 empty] | 0 |  | 1 |  | 0 |  | 7.2 | [8 empty] | P & A |  | 0 | 1 | 0 | 0 | 6.2 | 0 | 0 | 0 | 0
[5 empty] | 0 |  | 1 |  | 0 |  | 7.2 | [8 empty] | Rig Down |  | 0 | 1 | 0 | 0 | 6.2 | 0 | 0 | 0 | 0
[5 empty] | 0 |  | 1 |  | 0 |  | 7.2
Coring | 0 |  |  |  | 0 |  | 1 |  | 0 |  | 7.2
RIH Scrapper to Liner depth interval, RIH and perform production casing cementing job |  |  | 0 |  | 0 |  | 1 |  | 0 |  | 7.2
RIH Casing Scrapper to perforated zone interval. Cased Hole Logging |  |  | 0 |  | 0 |  | 1 | 0 | 0 |  | 7.2 | 0
|  |  |  | 0 | 0 |  | 1 |  | 0 |  | 7.2
|  |  |  | 0 | 0 |  | 1 |  | 0 |  | 7.2
|  |  |  | 0 | 0 |  | 1 |  | 0 |  | 7.2
Test | 0 |  |  |  | 0 |  | 1 |  | 0 |  | 7.2
DST |  |  | 0 |  | 0 |  | 1 | 0 | 0 |  | 7.2 | 0
|  |  | 0 | 0 | 0 |  | 1 |  | 0 |  | 7.2
|  |  | 0 | 0 | 0 |  | 1 |  | 0 |  | 7.2
Completion | 0 |  |  |  | 0 |  | 1 |  | 0 |  | 7.2
Trip, RIH & cement casing, BOP Job, RIH bit, Run Scrapper, CHL, Perforation 1st target, N/D BOP & N/U X-Masstree. Production Test | 0 |  | 0 |  | 0 |  | 1 |  | 0 |  | 7.2
Kill well, BOP Job, POOH RPP, Squeeze Job, DOC, Run scrapper, Perforation 2nd target, RIH RPP, Production test | 0 |  | 0 |  | 0 |  | 1 |  | 0 |  | 7.2
Kill well, BOP Job, POOH RPP, Fracturing Job, RIH RPP, N/D BOP & N/U X-Masstree. Production Test | 0 |  | 0 |  | 0 |  | 1 |  | 0 |  | 7.2
P & A | 0 |  |  |  | 0 |  | 1 |  | 0 |  | 7.2
P&A cmt job. L/D string. N/D BOP. N/U THS & Cap Assy |  |  | 0 |  | 0 |  | 1 | 0 | 0 |  | 7.2 | 0
|  |  |  | 0 | 0 |  | 1 |  | 0 |  | 7.2
|  |  |  | 0 | 0 |  | 1 |  | 0 |  | 7.2
|  |  |  | 0 | 0 |  | 1 |  | 0 |  | 7.2
0
Rig Down | 0
Rig Down |  | 0 | 0 |  | 0 |  | 1 |  | 0 | 0 | 1 |  |  | 0 | 0 | 0
|  | 0 |  | 0 |  | 0 | 1 |  |  | 0 | 1 |  |  | 0 | 0 | 0
|  | 0 |  | 0 |  | 0 | 1 |  |  | 0 | 1 |  |  | 0 | 0 | 0
|  | 0 |  | 0 |  | 0 | 1 |  |  | 0 | 1 |  |  | 0 | 0 | 0
|  | 0 |  | 0 |  | 0 | 1 |  |  | 0 | 1 |  |  | 0 | 0 | 0
Total days |  |  | 0 |  | 0 | 0 | 1 |  |  | 0 | 1 |  |  | 0 | 0
DRILLING SCHEDULE DETAILS | Historical |  |  |  | Proposed Original |  |  |  | Evaluated |  |  |  | ACTUAL |  |  |  | REMARKS | MOM DATE | PERIHAL
Operation Details | HOUR | DAY | CUMMULATIVE | Depth (ft) | HOUR | DAY | CUMMULATIVE | Depth (ft) | HOUR | DAY | CUMMULATIVE | Depth (ft) | HOUR | DAY | CUMMULATIVE | Depth (ft)
Moving |  |  | 0 | [16 empty] | Activities |  | Proposed Original |  |  | Evaluated |  |  | ACTUAL
Tow Rig to well | 0 |  | 0 |  | 0 |  | 1 |  | 0 | 0 | 1 | [10 empty] | Day | Cum Days | Depth (Ft) | Day | Cum Days | Depth (Ft) | Day | Cum Days | Depth (Ft)
[20 empty] | Moving Tow Rig to well, |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Rig Up | 0 | [18 empty] | Rig-up, termasuk R/U Top Drive dan stand-up DP & DC. |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Rig-up |  |  | 0 |  | 0 |  | 1 |  | 0 | 0 | 1 | [8 empty] | Workover | Preparation (Kill well & POOH existing string) | 1 | 1 | 0 | 0 | 0 | 5577.7 | 0 | 0 | 0
[21 empty] | Squeeze lapisan Eksisting. Run Scraper. Run GR-CBL-CNL | 0 | 1 | 0 | 0 | 0 | 5577.7 | 0 | 0 | 0
Workover | 0 | [19 empty] | Perbaikan bonding. DOC. Run Scraper. Re run GR-CBL-VDL | 0 | 1 | 0 | 0 | 0 | 5577.7 | 0 | 0 | 0
Preparation (Kill well & POOH existing string) | 0 |  | 0 |  | 0 |  | 1 | 0 | 0 | 0 | 1 | 5577.7 | [8 empty] | Perforasi Produksi. RIH RPP. Swab dan BHP Job. POOH RPP | 0 | 1 | 0 | 0 | 0 | 5577.7 | 0 | 0 | 0
Squeeze lapisan Eksisting. Run Scraper. Run GR-CBL-CNL | 0 |  | 0 |  | 0 |  | 1 | 0 | 0 | 0 | 1 | 5577.7 | [8 empty] | RIH RPP. Put well on production | 0 | 1 | 0 | 0 | 0 | 5577.7 | 0 | 0 | 0
Perbaikan bonding. DOC. Run Scraper. Re run GR-CBL-VDL | 0 |  | 0 |  | 0 |  | 1 | 0 | 0 | 0 | 1 | 5577.7 | [8 empty] | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Perforasi Produksi. RIH RPP. Swab dan BHP Job. POOH RPP | 0 |  | 0 |  | 0 |  | 1 | 0 | 0 | 0 | 1 | 5577.7 | [8 empty] | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0
RIH RPP. Put well on production | 0 |  | 0 |  | 0 |  | 1 | 0 | 0 | 0 | 1 | 5577.7 | [8 empty] | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| 0 |  | 0 |  | 0 |  | 1 |  | 0 |  | 1 | [9 empty] | 0 | 4.1 | 5.1 | 0 | 4.1 | 4.1 | 0 | 0 | 0 | 0
| 0 |  | 0 |  | 0 |  | 1 |  | 0 |  | 1 | [9 empty] | 0 | 2.1 | 7.2 | 0 | 2.1 | 6.2 | 0 | 0 | 0 | 0
| 0 |  | 0 |  | 0 |  | 1 |  | 0 |  | 1 | [8 empty] | Coring |  | 0 | 7.2 | 0 | 0 | 6.2 | 0 | 0 | 0 | 0
| 0 |  | 0 |  | 98.4 | 4.1 | 5.1 |  | 98.4 | 4.1 | 5.1 | [8 empty] | Test |  | 0 | 7.2 | 0 | 0 | 6.2 | 0 | 0 | 0 | 0
| 0 |  | 0 |  | 50.4 | 2.1 | 7.2 |  | 50.4 | 2.1 | 7.2 | [8 empty] | Completion |  | 0 | 7.2 | 0 | 0 | 6.2 | 0 | 0 | 0 | 0
[5 empty] | 0 |  | 7.2 |  | 0 |  | 7.2 | [8 empty] | P & A |  | 0 | 7.2 | 0 | 0 | 6.2 | 0 | 0 | 0 | 0
[5 empty] | 0 |  | 7.2 |  | 0 |  | 7.2 | [8 empty] | Rig Down |  | 0 | 7.2 | 0 | 0 | 6.2 | 0 | 0 | 0 | 0
[5 empty] | 0 |  | 7.2 |  | 0 |  | 7.2
Coring | 0 |  |  |  | 0 |  | 7.2 |  | 0 |  | 7.2
RIH Scrapper to Liner depth interval, RIH and perform production casing cementing job |  |  | 0 |  | 0 |  | 7.2 |  | 0 |  | 7.2
RIH Casing Scrapper to perforated zone interval. Cased Hole Logging |  |  | 0 |  | 0 |  | 7.2 | 0 | 0 |  | 7.2 | 0
|  |  |  | 0 | 0 |  | 7.2 |  | 0 |  | 7.2
|  |  |  | 0 | 0 |  | 7.2 |  | 0 |  | 7.2
|  |  |  | 0 | 0 |  | 7.2 |  | 0 |  | 7.2
Test | 0 |  |  |  | 0 |  | 7.2 |  | 0 |  | 7.2
DST |  |  | 0 |  | 0 |  | 7.2 | 0 | 0 |  | 7.2 | 0
|  |  | 0 | 0 | 0 |  | 7.2 |  | 0 |  | 7.2
|  |  | 0 | 0 | 0 |  | 7.2 |  | 0 |  | 7.2
Completion | 0 |  |  |  | 0 |  | 7.2 |  | 0 |  | 7.2
Trip, RIH & cement casing, BOP Job, RIH bit, Run Scrapper, CHL, Perforation 1st target, N/D BOP & N/U X-Masstree. Production Test | 0 |  | 0 |  | 0 |  | 7.2 |  | 0 |  | 7.2
Kill well, BOP Job, POOH RPP, Squeeze Job, DOC, Run scrapper, Perforation 2nd target, RIH RPP, Production test | 0 |  | 0 |  | 0 |  | 7.2 |  | 0 |  | 7.2
Kill well, BOP Job, POOH RPP, Fracturing Job, RIH RPP, N/D BOP & N/U X-Masstree. Production Test | 0 |  | 0 |  | 0 |  | 7.2 |  | 0 |  | 7.2
P & A | 0 |  |  |  | 0 |  | 7.2 |  | 0 |  | 7.2
P&A cmt job. L/D string. N/D BOP. N/U THS & Cap Assy |  |  | 0 |  | 0 |  | 7.2 | 0 | 0 |  | 7.2 | 0
|  |  |  | 0 | 0 |  | 7.2 |  | 0 |  | 7.2
|  |  |  | 0 | 0 |  | 7.2 |  | 0 |  | 7.2
|  |  |  | 0 | 0 |  | 7.2 |  | 0 |  | 7.2
0
Rig Down | 0
Rig Down |  | 0 | 0 |  | 0 |  | 1 |  | 0 | 0 | 1 |  |  | 0 | 0 | 0
|  | 0 |  | 0 |  | 0 | 1 |  |  | 0 | 1 |  |  | 0 | 0 | 0
|  | 0 |  | 0 |  | 0 | 1 |  |  | 0 | 1 |  |  | 0 | 0 | 0
|  | 0 |  | 0 |  | 0 | 1 |  |  | 0 | 1 |  |  | 0 | 0 | 0
|  | 0 |  | 0 |  | 0 | 1 |  |  | 0 | 1 |  |  | 0 | 0 | 0
Total days |  |  | 0 |  | 0 | 0 | 1 |  |  | 0 | 1 |  |  | 0 | 0

## Casing Design (hidden)
| TRAJECTORY |  | CASING | DEPTH RANGE (ft) |  | MUD | CEMENTING
|  |  | (inch) | From | To | Cost | Cost
| 1 | 36 | 30 | 0 | 0 | 0 | 0
| 2 | 26 | 20 | 0 | 0 | 0 | 0
| 3 | 17.5 | 13.375 | 0 | 0 | 0 | 0
| 4 | 12.25 | 9.625 | 0 | 328.1 | 0 | 0
| 5 | 8.5 | 7 | 0 | 2395 | 0 | 0
| ITEM | AFE CMS-XX1
| KOP, ft | 0
| EOC,ft | 0
9.625Inch | BUR, deg/100 m | 0
| Inclination, deg | 0
| TD, ft | 0
| Tangent Length, ft | 0
| Horizontal Displacement, ft | 0
7Inch

## Rig
* diisi dengan Bar Chart Rig | * diisi dengan data pore pressure

## Actual Cost Summary (hidden)
# tabel dibawah menunjukan actual cost AFE ini dari awal sampai selesainya pekerjaan. KKKS agar mengisi tabel dibawah untuk memonitor realisasi biaya atas AFE ini
|  |  | APPROVED (US$) |  | ACTUAL (US$)
Activities | Days | Cum Days | AFE Cost | AFE Cum Cost | Actual Cost | Actual Cum Cost
Preparation | 0 | 0 |  | 0 |  | 0
MIRU | #REF! | #VALUE! |  | 0 |  | 0
24" Conductor | #REF! | #VALUE! |  | 0 |  | 0
20" Drilling | #REF! | #VALUE! |  | 0 |  | 0
18-5/8" Casing | #REF! | #VALUE! |  | 0 |  | 0
17-1/2" Drilling | #REF! | #VALUE! |  | 0 |  | 0
13-3/8" Casing | #REF! | #VALUE! |  | 0 |  | 0
12-1/4" Drilling | #REF! | #VALUE! |  | 0 |  | 0
12-1/4" Washdown | #REF! | #VALUE! |  | 0 |  | 0
9-5/8" Casing | #REF! | #VALUE! |  | 0 |  | 0
8-1/2" Pilot Hole | #REF! | #VALUE! |  | 0 |  | 0
8-1/2" Drilling | #REF! | #VALUE! |  | 0 |  | 0
Lower Completion | #REF! | #VALUE! |  | 0 |  | 0
Kujung TCP | #REF! | #VALUE! |  | 0 |  | 0
Upper Completion | #REF! | #VALUE! |  | 0 |  | 0
Stimulation and Well Unloading | #REF! | #VALUE! |  | 0 |  | 0
RDMO | #REF! | #VALUE! |  | 0 |  | 0
Activities | Days | Cum Days | Cost | Cum Cost
Preparation | 0 | 0 | 0 | 0
Mob-Demob | #VALUE! | #VALUE! | 0 | 0
Drilling | 0 | #VALUE! | 0 | 0
Completion | #VALUE! | #VALUE! | 0 | 0
Kujung TCP | #REF! | #VALUE! | 0 | 0
Stimulation and Well Unloading | #REF! | #VALUE! | 0 | 0